## Slide 1
06
Delivery Timeline — Overview
IBM builds and releases the asset · Washington funds its deployment
CY2027–2031 · joint Connect360 + WPCO response
26 wks
MVP GO-LIVE
30 June 2027 · 103 MVP requirements
4
ASSET RELEASES
R1 wk8 · R2 wk14 · R3 wk20 · GA wk24
44%
OF CY2027 IS ASSET
31.35 of 71.5 FTE-months — IBM’s investment decision
6–8
PARTNERS IN PRODUCTION
cannot connect before R2
Jan 2027
Jan 2028
Jan 2029
Jan 2030
Jan 2031
Dec 2031
IBM PLATFORM ASSET
Connect360 + WPCO
IBM-funded
Platform hardened and released — then it keeps evolving: every engine Washington receives in Phase 2 and Phase 3 is asset capability, not bespoke development
R1
R2
R3
GA
R1 wk8 · R2 wk14 · R3 wk20 · GA wk24 released to delivery ↓
WASHINGTON FUNDS
CY2027
MVP
Deployment · configuration · 6–8 partner integrations · WaTech SDR · contract overhead
$2.23M
CY2028
Phase 2
◆ GATE 1 — shared care plan · granular consent · population & equity analytics
$2.25M
CY2029–31
Phase 3
◆ GATE 2 — event notification · knowledge graph · journey engine · WPC ranking · real-time dispatch · governed agents
$9.11M
Operations &
recertification
↻ tier-2/3 support · annual recertification · governance — continuous from go-live
DOES NOT FIT ANY FUNDING ROUTE
Client-facing portal · agentic marketplace · household thread · agent ROI — needs a second deal
$1.87M
Figures shown are scenario S1 — IBM funds asset development in the two committed years, Washington funds its own deployment throughout. Five-year Washington price $13.59M against a $17.3M envelope. IBM investment $2.00M. Every year clears its ceiling. Scenarios S2 and S3 are on the funding slide.
Detail follows — 06a: release and handover ladder · 06b: CY2027 MVP roadmap · 06c: what Washington funds and what IBM funds

## Slide 2
06a
Asset Release → Client Handover
the asset story told inside the delivery story
client work cannot start on a stream until its asset release exists
R1
wk 8
Write path complete
ASSET RELEASE
Identity with non-destructive merge · full R4 consent provision model · provenance and cross-org audit · RBAC · durable event log
cumulative asset 13.05 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
WA consent policy authoring · organisation hierarchy · identifier policy · retention and legal-hold rules
R2
wk 14
Contract surfaces frozen
ASSET RELEASE
Owned, versioned integration façade (US Core + SDOHCC) · domain-verb mutations and the statewide reason-code vocabulary
cumulative asset 17.55 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
Partner onboarding may begin. Nothing connects before this — and once it has, the surface cannot change.
R3
wk 20
MVP product complete
ASSET RELEASE
Worker portal · read-side reporting projection · citizenEverything resolver · directory federation adapter
cumulative asset 33.05 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
WA configuration completion · directory corpus load · referral pathway setup · user acceptance testing
GA
wk 24
Certified build
ASSET RELEASE
HITRUST r2 and SOC 2 Type II evidence · penetration test · accessibility conformance and published VPAT
cumulative asset 37.75 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
WaTech Security Design Review and Privacy Threshold Analysis submitted — gates every byte of HCA data
GO
wk 26
MVP GO-LIVE
ASSET RELEASE
—
cumulative asset —
hands to delivery
UNBLOCKS CLIENT DELIVERY
Production cutover · 6–8 partners live · tier-2/3 support begins
WHY THE WEEK NUMBERS ARE WHAT THEY ARE
R2 at week 14 is the binding release. The moment 6–8 independent organisations hold production integrations against the façade and the verb set, neither can change — so onboarding cannot start before week 14 and must finish by week 26. GA at week 24 is the certification release: the Security Design Review cannot be submitted against a build that is still moving, and two weeks of float to go-live is thin. Peak concurrency is about thirteen people in weeks 6–13; roughly $1.4M of CY2027 is out the door by week 14, against acceptance milestones worth far less.
IBM Consulting · Health & Human Services · WA CIE · release ladder ties to the Release handover tab

## Slide 3
06b
CY2027 MVP Roadmap (wk 1–34)
Sequenced by irreversibility, not by value · contract start 4 Jan 2027
Tiers 1 and 2 complete before any partner integrates
wk1
wk8
wk14
wk20
wk26
wk34
Tier 1 · write path
identity · consent · provenance & audit · RBAC · event log
9.5
Tier 2 · contract surfaces
integration façade · domain verbs + reason codes
6.0
Tier 3 · MVP product
participant portal · read-side projection · conform & write · citizenEverything · directory adapter · referral · HRSN
24.5
Tier 4 · compliance
508 / WCAG 2.1 AA + VPAT · Tribal & IHS data sovereignty
4.5
Certification lane
HITRUST / SOC 2 evidence · penetration test · WaTech SDR + Privacy Threshold Analysis
4.0
Partner onboarding
6–8 interoperability partners — a factory, not eight bespoke projects
10.0
Programme management
23 deliverables · bi-weekly plan · monthly reports · RAID · governance
8.0
Operations · tier 2/3
Comagine owns tier 1
5.0
DELETED
claims / X12 / NCPDP spine · HCC/CDPS & DRG groupers · HEDIS · total cost of care · CMS-0057-F · prior authorisation · Epic/Cerner SMART · ADF/Databricks · asset packaging — no WA CIE buyer at any phase
Milestones
surfaces frozen wk14
SDR passed wk24
MVP GO-LIVE wk26
impl. ends wk34
WORKSTREAM | WKS | FTE-mo | WHAT LANDS, AND WHEN
Tier 1 · irreversible write path | 1–14 | 9.5 | ◆ Stable CIE identifier, permanent source-ID retention, non-destructive merge/unmerge with link history and a stewardship queue. ◆ Full R4 consent provision shape, enforcement at the data layer, revoke-not-delete, securityLabel from the first record. ◆ Provenance per write and cross-org read audit. ◆ Durable event log — stable types, idempotency, ordering.
Tier 2 · contract surfaces | 4–14 | 6.0 | ◆ Owned, versioned integration façade profiled to US Core + SDOHCC. ◆ Domain-verb mutations with the statewide reason-code vocabulary. — Both land BEFORE the first partner integrates; once 6–8 organisations hold production integrations the surface cannot be taken away.
Tier 3 · MVP product | 6–26 | 24.5 | ◆ Participant portal extended to worker roles — match adjudication, record view, consent capture, HRSN screening, referral create/receive/track/close, directory search, org admin. ◆ Read-side projection with operational counts and a participant extract. ◆ citizenEverything resolver. ◆ Directory federation adapter.
Tier 4 + certification | 1–25 | 8.5 | ◆ 508 / WCAG 2.1 AA, VPAT / ACR and remediation. ◆ Tribal and IHS data sovereignty — 29 federally recognised tribes. ◆ HITRUST r2 and SOC 2 evidence, penetration test, WaTech SDR and Privacy Threshold Analysis — a pre-condition of launch with an immediate-termination trigger.
Onboarding · PM · operations | 1–34 | 23.0 | ◆ 6–8 partners in production at go-live, run as a repeatable factory with a per-partner acceptance milestone. ◆ 23 deliverables, bi-weekly plan updates, monthly reports, RAID. ◆ Tier-2/3 support from go-live; Comagine owns tier 1.
IBM Consulting · Health & Human Services · WA CIE CY2027 MVP · 71.5 FTE-months · $3,157,625 delivered cost · ties to the Gantt and Staffing tabs · US-only delivery per RFP Sec. 3.6.4 · illustrative rates

## Slide 4
06c
What Washington Funds · What IBM Funds
the split is a commercial dial, not a fact
where it is set decides the bid price, the investment and the exposure
CY2027 — WHERE EVERY FTE-MONTH SITS
Line
ASSET
CLIENT
Identity · consent · provenance · RBAC · event log
6.65
2.85
Integration façade · domain verbs
4.50
1.50
Worker portal · projection · resolver · directory adapter
15.50
9.00
Accessibility · Tribal sovereignty
2.70
1.80
HITRUST / SOC 2 · WaTech SDR + PTA
2.00
2.00
Partner onboarding (6–8)
—
10.00
Programme management · 23 deliverables
—
8.00
Operations · tier-2/3 support
—
5.00
CY2027 total
31.35
40.15
44% ASSET
56% CLIENT
THREE FUNDING POSTURES
S1
IBM funds the asset in the committed years only
IBM investment
$2.00M
WA five-year price
$13.59M
Cost-score gain
$2.2M
Low — exposure confined to CY2027–28. The posture that survives a renewal that is never exercised.
S2
IBM funds 50% throughout
IBM investment
$2.78M
WA five-year price
$12.72M
Cost-score gain
$3.1M
Live in every year — half of each year’s asset work still sits on the state’s money.
S3
IBM funds 100% throughout
IBM investment
$5.56M
WA five-year price
$9.63M
Cost-score gain
$6.2M
None. Strongest bid and cleanest defence — and the largest unfunded bet with no second deal behind it.
What Washington funds is Washington’s deployment. What IBM funds is the platform. Say it in the proposal rather than leaving it implicit.
A blended bid that charges all asset development to Washington does NOT clear the CY2027 ceiling — it is $108,472 over. Some IBM contribution is required whatever the strategy; the only question is how much. Cost is 300 of 1000 points, scored as (lowest evaluated cost ÷ ours) × 300 across the full five-year period.
IBM Consulting · Health & Human Services · ties to the Asset vs Client and Funding scenarios tabs

## Slide 5
ASK
The Executive Ask
commit two years → renewal options → decide this quarter
WA CIE · proposal due 23 October 2026
PROVEN Connect360 is live, deployed on Azure and Marketplace-listed, with a real HIE integration in production · WPCO supplies the governed intelligence layer. US-ONLY DELIVERY per RFP Sec. 3.6.4 — the prior 54.3% offshore blend is void for this bid and every figure below is repriced.
1
COMMIT THE TWO-YEAR TERM — CY2027–28 · the only years Washington commits to
Committed term — MVP + Phase 2 $6.70m
CY2027 MVP $3.51M (71.5 FTE-mo) — identity, consent, client record, referral, directory, operational reporting, participant portal, 6–8 partners. CY2028 Phase 2 $3.19M (65.0 FTE-mo) — shared care plan, granular consent, population & equity analytics.
2
THEN THE RENEWAL OPTIONS — CY2029–31 (at Comagine’s sole discretion · no right or expectation of renewal)
CY2029 · Phase 3 begins
$3.23M
Event notification ingest and exchange, the knowledge graph rebuilt by replaying the MVP event log, journey engine, WPC context ranking behind the existing seam.
CY2030 · Real-time & inference
$2.98M
Real-time dispatch, signal dispositioning engine, graph inference and household linkage, enrollment verification, remaining change subscriptions.
CY2031 · Agents & maturation
$2.90M
Governed agents over the MVP domain verbs and actor model, care-plan intelligence, forecasting and equity monitoring, advanced consent interoperability.
Operations, support & recertification
CONTINUOUS
Tier-2/3 application support, defect resolution and root-cause analysis; annual HITRUST and SOC 2 recertification and penetration testing; governance participation. Comagine owns tier 1. Runs from MVP go-live to the end of the programme — inside each year, not a separate ask.
wk 26 → end
FIVE-YEAR EVALUATED PRICE = $15.81M against a $17.3M envelope · $1.49M headroom · CY2027 is the only year over its ceiling: −$108,472 at a 10% margin, and it fits at roughly 7%
DECISION REQUESTED THIS QUARTER
Run the six gate tests — they decide $2,205,000 of CY2027 scope and none costs more than a day · settle the teaming structure on HITRUST and SOC 2, which changes Submittal Form A · approve the bid at a thin CY2027 margin recovered in the later years · submit the two written questions to Comagine by 9 October.
IBM Consulting · Health & Human Services · The Executive Ask · ties to the Cost by Scope tab ($15,809,306) · US-only delivery per RFP Sec. 3.6.4 · rates are assumptions pending the rate card · estimate class 4