## Slide 1
06
Delivery Timeline — Overview
IBM builds and releases the asset · Washington funds its deployment
CY2027–2031 · joint Connect360 + WPCO response
26 wks
MVP GO-LIVE
30 June 2027 · 103 MVP requirements
4
ASSET RELEASES
R1 wk8 · R2 wk14 · R3 wk20 · GA wk24
44%
OF CY2027 IS ASSET
31.35 of 71.5 FTE-months — absorbed as base asset
6–8
PARTNERS IN PRODUCTION
cannot connect before R2
Jan 2027
Jan 2028
Jan 2029
Jan 2030
Jan 2031
Dec 2031
IBM PLATFORM ASSET
Connect360 + WPCO
IBM-funded
One record per person · consent that actually withholds data · referrals you can follow · a live service directory · the worker screen · one way in for other systems · a complete history · HITRUST + SOC 2
Eight things, built once and reused. Every engine Washington receives in Phase 2 and Phase 3 is more of the same product — not bespoke development billed to the state.
R1
R2
R3
GA
R1 wk8 · R2 wk14 · R3 wk20 · GA wk24 released to delivery ↓
WASHINGTON FUNDS
CY2027
MVP
Deployment · configuration · 6–8 partner integrations · WaTech SDR · contract overhead
$2.23M
CY2028
Phase 2
◆ GATE 1 — shared care plan · granular consent · population & equity analytics
$2.25M
CY2029–31
Phase 3
◆ GATE 2 — event notification · knowledge graph · journey engine · WPC ranking · real-time dispatch · governed agents
$5.15M
Operations &
recertification
↻ tier-2/3 support · annual recertification · governance — continuous from go-live
DOES NOT FIT ANY FUNDING ROUTE
Client-facing portal · agentic marketplace · household thread · agent ROI — needs a second deal
$1.87M
Base position: asset development is absorbed into the base asset and carried on the IBM product P&L — all five years, $5.56M. Washington funds only its own deployment: five-year price $9.63M against a $17.3M envelope, $7.67M of headroom, every year clear of its ceiling. Partial-absorption fallbacks are on 06h.
Detail follows — 06a: what the asset is · 06b: which asset each release enhances · 06c: release and handover ladder · 06d: CY2027 MVP roadmap · 06e: the five-year asset plan · 06f–06g: Phase 1 and Phase 2/3 line by line · 06h: what Washington funds and what IBM funds · 06i: funding positions year by year · 06j: re-derivation against evidence · 07 / 07a: solution models A vs B

## Slide 2
06a
What the Asset Actually Is
eight finished pieces of product, in plain English
built once by IBM · configured and deployed for Washington
Washington is not buying eight project outcomes. It is buying eight pieces of finished product — the same eight every later deployment receives. Washington pays to configure them, connect its partners, load its own data and pass its own security review.
1
R1
One record per person
Each person exists once, even when agencies spell the name differently. A wrong match can be undone without losing anything.
FOR EXAMPLE
Maria is “Maria Lopez” at the food bank, “M. Lopez-Ruiz” at the clinic and a case number at housing. The asset shows one record — and if that match was wrong, a steward un-merges it and nothing is lost.
2
R1
Consent that actually withholds data
The person decides who sees what, and the rule is enforced when data is read — not written into a policy and hoped for.
FOR EXAMPLE
Maria shares her housing need with the CBO but not her behavioural-health history. The CBO worker searches and those records are simply not returned. She withdraws consent later: the record stays, the access stops.
3
R2 → R3
Referrals you can follow
A referral is a tracked thing with a fixed set of actions and one statewide list of reasons — so every organisation means the same thing.
FOR EXAMPLE
A clinic refers Maria to a housing provider. The clinic sees it was received Tuesday and declined Thursday for “no capacity” — instead of “we sent an email and never heard back”.
4
R3
A live service directory
A searchable list of real services with real hours, eligibility and capacity, fed by the organisations themselves and by the statewide directory.
FOR EXAMPLE
The worker searches “food assistance, open Saturday, near Yakima” and gets three places that are actually open — and refers straight from the result, instead of working from a PDF printed in March.
5
R3
The worker screen
The one place a caseworker works: find the person, confirm the match, see the record, capture consent, screen for need, send and track referrals, manage their own users.
FOR EXAMPLE
A CBO worker opens one screen, confirms Maria is the person in front of her, records her consent, screens her for food and housing need and sends two referrals — without re-typing anything.
6
R2
One way in for other systems
One versioned connection point. Partners build against it once; nobody builds a separate link per partner, in either direction.
FOR EXAMPLE
The regional HIE connects once. When the twelfth organisation joins it uses the same connection point as the first, so onboarding is a repeatable checklist rather than a new project each time.
7
R1
A complete history
Every write stamped with who did it and where it came from, every cross-organisation read logged, and an event stream that can be replayed.
FOR EXAMPLE
The state asks who viewed Maria’s record in March and where her address came from. That is a report you run, not an investigation you commission.
8
GA
Security credentials the product holds
Certification held by the product itself — HITRUST r2, SOC 2 Type II, an annual penetration test and WCAG 2.1 AA accessibility.
FOR EXAMPLE
Washington’s security review is submitted against a build that is already certified. The next state inherits the same certificate on day one — it is not re-earned and re-billed.
31.35 of CY2027’s 71.5 FTE-months build these eight things — absorbed into the base asset and carried by IBM, not billed to Washington. The other 40.15 are Washington’s own deployment: configuration, 6–8 partner integrations, its service-directory content, its security review and programme overhead.

## Slide 3
06b
Which Asset Each Release Enhances
what exists in the product today · what each release adds
evidence from the instance we inspected · unverified claims carry a gate test
CAPABILITY | ASSET | WHAT EXISTS TODAY — ● verified in the instance ○ not verified | R1 · wk 8 | R2 · wk 14 | R3 · wk 20 | GA · wk 24
1 One record per person | Connect360 core data | ○ 553 FHIR R4 types and a working Patient store, but no $match and no PIX / PDQ. Identity matching does not exist today. gate G6 | CIE identifier · non-destructive merge and un-merge · link history · stewardship queue | Identity resolved through the façade, so every partner resolves a person the same way | Match adjudication in the worker screen | —
2 Consent that withholds data | Connect360 consent | ● Full R4 ConsentProvision shape including securityLabel is present in the API. ○ Whether it is enforced at read time is unproven. gate G1 | Enforced at the data layer · revoke-not-delete · securityLabel written from the first record | Honoured on every partner read through the façade | Consent capture in the worker screen | In HITRUST / SOC 2 scope
3 Referrals you can follow | Connect360 service requests | ● serviceRequestsForOrganization exists — a queue, not a tracked lifecycle. No statewide reason vocabulary. | — | Send · accept · decline · close, with the statewide reason-code list | Create, track and close in the screen; status returns to the sender | —
4 A live service directory | Connect360 HSDS directory | ● HSDS directory model present. ○ No federation to the statewide directory; hours, eligibility and capacity are not kept current. gate G5 | — | — | Federation adapter · search by hours, eligibility and geography · refer straight from the result | —
5 The worker screen | WPCO experience + C360 portal | Connect360: ● participant portal only; ○ no worker UI, and no role or permission type among the 553. WPCO: ● ~7,600 lines of worker screens exist at demo grade; ○ their production seams are declared fail-closed. gates G3 · G4 | Roles and permissions behind the screen | — | The screen itself — search, match, consent, HRSN screening, referral, org admin | WCAG 2.1 AA · VPAT / ACR
6 One way in for other systems | New — IBM-owned façade | ○ A vendor API surface that can change underneath us. There is no owned, versioned façade today. | — | Owned façade profiled to US Core + SDOHCC — frozen at week 14 | — | —
7 A complete history | Connect360 events + audit | ○ 22 ChangePayload types but a single subscription, and the proxy blocks accurate totals. The stream is partial. | Provenance per write · cross-organisation read audit · durable event log with stable types, idempotency and ordering | — | Read-side projection restores operational counts and extracts | —
8 Security credentials | Platform certification | ○ No HITRUST r2 or SOC 2 Type II is held at product level today. gate G2 | — | — | — | HITRUST r2 · SOC 2 Type II · annual penetration test · SDR against a frozen build
WHERE WPCO ACTUALLY LANDS
In CY2027 WPCO contributes the worker experience and the screening / referral orchestration on top of Connect360 — nothing more. The intelligence engines are Phase 2 and Phase 3: shared care plan and granular consent (CY2028), then knowledge graph, journey engine, WPC ranking, real-time dispatch and governed agents (CY2029–31). Claiming them in MVP would not survive the demonstration.
READ THE TABLE THIS WAY
● seen working in the Connect360 instance. ○ not seen, or seen only as a data shape — each carries a gate test to run before the demonstration. The R-columns are what IBM builds into the asset, not what Washington configures; Washington’s own work sits on slide 06h.
IBM Consulting · Health & Human Services · WA CIE · gate tests G1–G6 must be run against the live instance before the 16–20 November demonstration

## Slide 4
06c
Asset Release → Client Handover
the asset story told inside the delivery story
client work cannot start on a stream until its asset release exists
R1
wk 8
Write path complete
ASSET RELEASE
One record per person, safely merged and safely un-merged. Consent that actually withholds data. A permanent record of who did what. Who is allowed to see what. A complete, replayable history.
cumulative asset 13.05 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
Washington writes its own sharing rules, sets up its organisations, and decides how long records are kept.
R2
wk 14
Contract surfaces frozen
ASSET RELEASE
One way in for other systems — connect once, not one link per partner. A fixed set of referral actions and standard reasons, so every organisation means the same thing by “declined”.
cumulative asset 17.55 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
Partner onboarding may begin. Nothing connects before this — and once it has, the surface cannot change.
R3
wk 20
MVP product complete
ASSET RELEASE
The screen staff actually use. Reports that answer in seconds instead of scanning everything. One call that returns a whole person. A plug for the statewide service directory.
cumulative asset 33.05 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
Washington finishes its setup, loads its service listings, defines its referral routes, and tests it with real staff.
GA
wk 24
Certified build
ASSET RELEASE
Security credentials the product holds, so every deployment inherits them. A break-in test. Proof it works for people using a screen reader or a keyboard only.
cumulative asset 37.75 FTE-mo
hands to delivery
UNBLOCKS CLIENT DELIVERY
Washington’s security review can be submitted. Nothing touches real state data until it passes.
GO
wk 26
MVP GO-LIVE
ASSET RELEASE
—
cumulative asset —
hands to delivery
UNBLOCKS CLIENT DELIVERY
Production cutover · 6–8 partners live · tier-2/3 support begins
WHY THE WEEK NUMBERS ARE WHAT THEY ARE
R2 at week 14 is the binding release. The moment 6–8 independent organisations hold production integrations against the façade and the verb set, neither can change — so onboarding cannot start before week 14 and must finish by week 26. GA at week 24 is the certification release: the Security Design Review cannot be submitted against a build that is still moving, and two weeks of float to go-live is thin. Peak concurrency is about thirteen people in weeks 6–13; roughly $1.4M of CY2027 is out the door by week 14, against acceptance milestones worth far less.
IBM Consulting · Health & Human Services · WA CIE · release ladder ties to the Release handover tab

## Slide 5
06d
CY2027 MVP Roadmap (wk 1–34)
Sequenced by irreversibility, not by value · contract start 4 Jan 2027
Tiers 1 and 2 complete before any partner integrates
wk1
wk8
wk14
wk20
wk26
wk34
Tier 1 · write path
identity · consent · provenance & audit · RBAC · event log
9.5
Tier 2 · contract surfaces
integration façade · domain verbs + reason codes
6.0
Tier 3 · MVP product
participant portal · read-side projection · conform & write · citizenEverything · directory adapter · referral · HRSN
24.5
Tier 4 · compliance
508 / WCAG 2.1 AA + VPAT · Tribal & IHS data sovereignty
4.5
Certification lane
HITRUST / SOC 2 evidence · penetration test · WaTech SDR + Privacy Threshold Analysis
4.0
Partner onboarding
6–8 interoperability partners — a factory, not eight bespoke projects
10.0
Programme management
23 deliverables · bi-weekly plan · monthly reports · RAID · governance
8.0
Operations · tier 2/3
Comagine owns tier 1
5.0
DELETED
claims / X12 / NCPDP spine · HCC/CDPS & DRG groupers · HEDIS · total cost of care · CMS-0057-F · prior authorisation · Epic/Cerner SMART · ADF/Databricks · asset packaging — no WA CIE buyer at any phase
Milestones
surfaces frozen wk14
SDR passed wk24
MVP GO-LIVE wk26
impl. ends wk34
WORKSTREAM | WKS | FTE-mo | WHAT LANDS, AND WHEN
Tier 1 · irreversible write path | 1–14 | 9.5 | ◆ Stable CIE identifier, permanent source-ID retention, non-destructive merge/unmerge with link history and a stewardship queue. ◆ Full R4 consent provision shape, enforcement at the data layer, revoke-not-delete, securityLabel from the first record. ◆ Provenance per write and cross-org read audit. ◆ Durable event log — stable types, idempotency, ordering.
Tier 2 · contract surfaces | 4–14 | 6.0 | ◆ Owned, versioned integration façade profiled to US Core + SDOHCC. ◆ Domain-verb mutations with the statewide reason-code vocabulary. — Both land BEFORE the first partner integrates; once 6–8 organisations hold production integrations the surface cannot be taken away.
Tier 3 · MVP product | 6–26 | 24.5 | ◆ Participant portal extended to worker roles — match adjudication, record view, consent capture, HRSN screening, referral create/receive/track/close, directory search, org admin. ◆ Read-side projection with operational counts and a participant extract. ◆ citizenEverything resolver. ◆ Directory federation adapter.
Tier 4 + certification | 1–25 | 8.5 | ◆ 508 / WCAG 2.1 AA, VPAT / ACR and remediation. ◆ Tribal and IHS data sovereignty — 29 federally recognised tribes. ◆ HITRUST r2 and SOC 2 evidence, penetration test, WaTech SDR and Privacy Threshold Analysis — a pre-condition of launch with an immediate-termination trigger.
Onboarding · PM · operations | 1–34 | 23.0 | ◆ 6–8 partners in production at go-live, run as a repeatable factory with a per-partner acceptance milestone. ◆ 23 deliverables, bi-weekly plan updates, monthly reports, RAID. ◆ Tier-2/3 support from go-live; Comagine owns tier 1.
IBM Consulting · Health & Human Services · WA CIE CY2027 MVP · 71.5 FTE-months · $3,157,625 delivered cost · ties to the Gantt and Staffing tabs · US-only delivery per RFP Sec. 3.6.4 · illustrative rates

## Slide 6
06e
The Asset Plan, End to End
nine asset releases · the engines and the agents are asset, not bespoke build
CY2027–2031 · every year still clears its funding ceiling
151.35
ASSET FTE-MONTHS
$5.56M of product across five years
9
ASSET RELEASES
v1.0 GA 2027 → v5.1 late 2031
47%
OF FIVE-YEAR EFFORT
151.35 asset · 169.15 Washington delivery
63.0
FTE-MO OF WPCO ENGINES
42% of the asset — plus 27.0 agentic
CY2027
Phase 1 · MVP
v1.0
GA wk 24
identity · consent · referrals · directory · worker screen · façade · complete history · HITRUST + SOC 2
31.35
40.15
asset FTE-mo · Washington delivery FTE-mo
CY2028
Phase 2 · Care coordination
v2.0
mid 2028
shared care plan · granular consent · care team and household
v2.1
late 2028
population and equity analytics · outcome measures · release engineering
◆ GATE 1 — MVP live and adopted
23.00
42.00
asset FTE-mo · Washington delivery FTE-mo
CY2029
Phase 3a · Intelligence
v3.0
mid 2029
knowledge graph · journey engine · event notification
v3.1
late 2029
signal dispositioning · whole-person ranking · agent runtime and governance
◆ GATE 2 — first renewal exercised
40.00
26.00
asset FTE-mo · Washington delivery FTE-mo
CY2030
Phase 3b · Agentic
v4.0
mid 2030
real-time dispatch · governed agents: intake triage, referral follow-up, benefit navigation
v4.1
late 2030
care plan intelligence · evaluation harness · drift and red-team
◆ human-in-the-loop by default
27.00
33.00
asset FTE-mo · Washington delivery FTE-mo
CY2031
Phase 3c · Orchestration
v5.0
mid 2031
multi-agent orchestration across journeys · impact measurement
v5.1
late 2031
configuration studio · TEFCA / QHIN · multi-deployment hardening
◆ second renewal exercised
30.00
28.00
asset FTE-mo · Washington delivery FTE-mo
WHERE THE ASSET EFFORT GOES
WPCO intelligence engines
63.00
42%
Connect360 platform extensions
29.15
19%
Agentic runtime, agents and assurance
27.00
18%
Platform — release, studio, hardening
16.70
11%
Worker experience (Connect360 + WPCO)
15.50
10%
THE RULE THAT MAKES THIS AN ASSET PLAN AND NOT A ROADMAP
Every engine and every agent above is built once into the product and configured per deployment — Washington never pays for construction it cannot reuse, and IBM never rebuilds it for the next state. The dividing line is the same in every year: if the next deployment would need it built again, it is client work; if it would not, it is asset. That is why Washington’s share falls from 56% of CY2027 to 39% of CY2029 even as the capability grows. Phase 2 and Phase 3 are gated: nothing is promised that a renewal has not paid for, and nothing is built ahead of the gate that clears it.
IBM Consulting · Health & Human Services · WA CIE · 151.35 asset / 169.15 client FTE-months · $36,750 blended US rate · figures tie to the Asset plan tab

## Slide 7
06f
Phase 1 — The MVP, Line by Line
what IBM builds into the asset · what Washington configures and runs
CY2027 · 31.35 asset · 40.15 Washington delivery FTE-months · go-live 30 June 2027
THE WRITE PATH, THE SURFACES AND THE CERTIFICATION
ASSET
CLIENT
R1 · WRITE PATH · week 8 — irreversible if wrong
R1
Identity — stable CIE ID, non-destructive merge and un-merge, stewardship queue
C360
2.10
0.90
R1
Consent — full R4 provision model, enforced at the data layer, revoke-not-delete
C360
1.75
0.75
R1
Provenance per write, cross-org read audit, retention and legal hold
C360
0.70
0.30
R1
RBAC, roles, permissions and delegated organisation administration
C360
1.05
0.45
R1
Event log — stable type vocabulary, idempotency, ordering, subscriptions
C360
1.05
0.45
R2 · CONTRACT SURFACES · week 14 — frozen once partners hold them
R2
Owned, versioned integration façade profiled to US Core + SDOHCC
C360
2.25
0.75
R2
Domain-verb mutations and the statewide reason-code vocabulary
C360
2.25
0.75
GA · CERTIFIED BUILD · week 24 — pre-condition of launch
GA
Accessibility — 508 / WCAG 2.1 AA, VPAT / ACR and remediation
PLATFORM
2.10
0.90
GA
Tribal and IHS data sovereignty handling — 29 federally recognised tribes
PLATFORM
0.60
0.90
GA
HITRUST r2 and SOC 2 Type II evidence and penetration test
PLATFORM
2.00
—
Write path, surfaces and certification
15.85
6.15
THE MVP PRODUCT AND THE WASHINGTON PROGRAMME
ASSET
CLIENT
R3 · MVP PRODUCT · week 20 — what a caseworker touches
R3
Participant portal extended to worker roles — match, record view, consent, org admin
C360 + WPCO
6.00
2.00
R3
Read-side reporting projection and operational counts
C360 + WPCO
3.75
1.25
R3
Conform and write — source-system adapters
C360
1.50
2.50
R3
citizenEverything composite resolver — one call returns a whole person
C360
2.00
0.50
R3
Directory federation adapter
C360
1.50
0.50
R3
Referral management workflow — create, receive, track, close
C360 + WPCO
0.50
1.50
R3
HRSN screening
C360 + WPCO
0.25
0.75
WASHINGTON DELIVERY ONLY — no asset content, none of it reusable
—
WaTech Security Design Review and Privacy Threshold Analysis
CLIENT
—
2.00
—
Partner integration and onboarding factory — 6–8 partners in production
CLIENT
—
10.00
—
Programme management — 23 deliverables, bi-weekly plan, RAID, governance
CLIENT
—
8.00
—
Operations and tier-2/3 support from go-live — Comagine owns tier 1
CLIENT
—
5.00
MVP product and Washington programme
15.50
34.00
CY2027 TOTAL
31.35
asset · 44%
40.15
Washington · 56%
HOW THE LINE IS DRAWN, AND WHY PHASE 1 IS THE MOST CLIENT-HEAVY YEAR
Asset is what the next deployment would not need built again; client is what it would. That is why 23.00 of Washington’s 40.15 — onboarding, programme management, operations and the WaTech review — carry no asset content at all: none of it travels. Conform-and-write and referral workflow are deliberately client-heavy because the mapping and the routing are Washington’s, not the product’s. Phase 1 is 44% asset; by CY2029 it is 61%, because the engines are built once and configured thereafter.
C360 Connect360 platform · C360 + WPCO worker experience on the platform · PLATFORM accessibility, sovereignty and certification. Ties to the Asset plan CY27-31 tab, rows 5–25.

## Slide 8
06g
Phase 2 & 3 — Engines and Agents
line by line: what IBM builds into the asset · what Washington configures and runs
CY2028–2031 · 120.00 asset FTE-months · 129.00 Washington delivery FTE-months
CY2028 · PHASE 2 — CARE COORDINATION
v2.0
Shared care plan — cross-org plan, goals, tasks, ownership, consent-aware sharing
WPCO
6.00
v2.0
Granular consent — element level, purpose-of-use, proxy and guardian delegation
C360
4.00
v2.0
Care team and household relationship model
C360
3.00
v2.1
Population and equity analytics — cohorts, disparity measures, governed marts
WPCO
5.00
v2.1
Outcome measures and closed-loop reporting
WPCO
3.00
v2.1
Release engineering — upgrade, regression, multi-tenant deployment
PLAT
2.00
CY2028 asset
23.00
WHAT WASHINGTON DOES IN CY2028 — 42.00 FTE-MONTHS
Deployment and configuration of Phase 2
4.00
Partner onboarding wave 2
6.00
Corpus and data expansion
2.00
Annual recertification — HITRUST, SOC 2, pen test
2.00
Operations and tier-2/3 support
6.00
Programme management and governance
5.00
Training and change management
2.00
Configuration of the Phase 2 engines above
15.00
CY2029–2031 · PHASE 3 — INTELLIGENCE, AGENTS, ORCHESTRATION
CY2029 · asset 40.00 · Washington 26.00
v3.0
Knowledge graph — person, organisation, service and event entities, graph query
WPCO
10.00
v3.0
Journey engine — stages, milestones, timers, per-person state machine
WPCO
8.00
v3.0
Event notification — subscriptions, routing, delivery guarantees
C360
6.00
v3.1
Signal dispositioning — ingest, triage rules, routing to an accountable owner
WPCO
5.00
v3.1
Whole-person ranking — need scoring with an explainable rationale
WPCO
6.00
v3.1
Agent runtime and governance — tool registry, guardrails, human-in-the-loop, action audit
AGENT
5.00
CY2030 · asset 27.00 · Washington 33.00
v4.0
Real-time dispatch and capacity matching — availability, hold, confirm, fallback
WPCO
8.00
v4.0
Governed agents — intake triage, referral follow-up, benefit navigation
AGENT
9.00
v4.1
Care plan intelligence — explainable next-best-action against the plan
WPCO
6.00
v4.1
Agent evaluation harness, drift monitoring and red-team suite
AGENT
4.00
CY2031 · asset 30.00 · Washington 28.00
v5.0
Agent orchestration across journeys — supervisor, escalation, hand-off
AGENT
9.00
v5.0
Impact measurement — attribution, cohort outcomes, programme effectiveness
WPCO
6.00
v5.1
Configuration studio — rules, forms and journeys changed without code
PLAT
7.00
v5.1
Interoperability expansion — TEFCA / QHIN, bulk FHIR, further profiles
C360
5.00
v5.1
Multi-deployment hardening and upgrade automation
PLAT
3.00
C360 Connect360 platform · WPCO whole-person intelligence engine · AGENT agentic runtime, agents and assurance · PLAT platform engineering. Washington’s 87.00 FTE-months in CY2029–31 are configuration of these engines, notification and dispatch onboarding, operations, recertification and governance — not construction.

## Slide 9
06h
What Washington Funds · What IBM Funds
the position is set — the asset is developed and absorbed as base asset
the fallbacks below exist only if the product investment board declines
CY2027 — WHERE EVERY FTE-MONTH SITS
Line
ASSET
CLIENT
Identity · consent · provenance · RBAC · event log
6.65
2.85
Integration façade · domain verbs
4.50
1.50
Worker portal · projection · resolver · directory adapter
15.50
9.00
Accessibility · Tribal sovereignty
2.70
1.80
HITRUST / SOC 2 · WaTech SDR + PTA
2.00
2.00
Partner onboarding (6–8)
—
10.00
Programme management · 23 deliverables
—
8.00
Operations · tier-2/3 support
—
5.00
CY2027 total
31.35
40.15
44% ASSET
56% CLIENT
THE BASE POSITION AND TWO FALLBACKS
A
BASE POSITION — absorbed into the base asset
IBM product investment
$5.56M
WA five-year price
$9.63M
Price advantage
$6.18M
All 151.35 asset FTE-months carried on the IBM product P&L across all five years. Washington is charged for its deployment only. Strongest cost score and the cleanest product story.
B
Fallback — half absorbed from CY2029
IBM product investment
$3.78M
WA five-year price
$11.61M
Price advantage
$4.20M
If the product investment board will not carry the renewal years, IBM absorbs the committed years in full and splits CY2029–31. Still clears every ceiling.
C
Floor — committed years only
IBM product investment
$2.00M
WA five-year price
$13.59M
Price advantage
$2.22M
The minimum that works. Asset work in the renewal years is charged to Washington. Weakest cost score of the three and the hardest to defend as a product.
The asset is developed and absorbed as base asset. Washington funds its deployment; IBM funds the product. Say it in the proposal rather than leaving it implicit.
A bid that charges all asset development to Washington does NOT clear the CY2027 ceiling — it is $108,472 over, and prices at $15.81M. Absorption is not only the strongest position, it is what makes the bid responsive at all. Price advantage is measured against that fully-loaded bid. Cost is 300 of 1000 points, scored as (lowest evaluated cost ÷ ours) × 300 across the full five-year period.
IBM Consulting · Health & Human Services · ties to the Asset vs Client and Funding scenarios tabs

## Slide 10
06i
Funding Positions, Year by Year
the adopted position, its two fallbacks, and the boundary case that proves it
all figures $M · every year tested against its own ceiling
$9.63M
WASHINGTON FIVE-YEAR PRICE
position A · against a $17.3M envelope
$5.56M
IBM PRODUCT INVESTMENT
absorbed as base asset, all five years
$6.18M
PRICE ADVANTAGE
vs a bid that charges the product build to the state
$7.67M
HEADROOM
every year clear of its ceiling at a 10% margin
POSITION | CY2027 | CY2028 | CY2029 | CY2030 | CY2031 | FIVE-YEAR
A — base · Washington price | 2.23 | 2.25 | 1.60 | 1.88 | 1.68 | 9.63
A — base · IBM investment | 1.15 | 0.85 | 1.47 | 0.99 | 1.10 | 5.56
B — fallback · Washington price | 2.23 | 2.25 | 2.41 | 2.43 | 2.29 | 11.61
B — fallback · IBM investment | 1.15 | 0.85 | 0.74 | 0.50 | 0.55 | 3.78
C — floor · Washington price | 2.23 | 2.25 | 3.23 | 2.98 | 2.90 | 13.59
C — floor · IBM investment | 1.15 | 0.85 | — | — | — | 2.00
Boundary — no absorption | 3.51 | 3.19 | 3.23 | 2.98 | 2.90 | 15.81
Annual ceiling | 3.40 | 3.40 | 3.50 | 3.50 | 3.50 | 17.30
▲ The boundary case is the only row that breaches a ceiling — CY2027 at $3.51M against $3.40M, over by $108,472. That is what makes absorption a matter of responsiveness rather than generosity.
A — BASE POSITION
absorbed, all years
· Asset work charged to Washington: none
· Procurement-integrity exposure: none
· Recovered from future deployments of the product
· Strongest cost score of the four
B — FALLBACK
half absorbed CY2029–31
· Asset work charged to Washington: half of CY2029–31
· Exposure: low
· Recovered part from renewals, part from the product
· Clears every ceiling
C — FLOOR
committed years only
· Asset work charged to Washington: all of CY2029–31
· Exposure: live in CY2029–31
· Recovered from renewals, or a second deal
· The minimum that still works
BOUNDARY
no absorption
· Asset work charged to Washington: all, every year
· Bid may be deemed nonresponsive
· Not an option — retained as proof
· CY2027 over by $108,472
Position A is adopted (assumption A25). B and C exist only if the product investment board will not carry the renewal years. If no renewal is ever exercised, IBM has spent $1,997,362 under any of the three — the committed-year asset work — and nothing further. Cost is 300 of 1000 points, scored as (lowest evaluated cost ÷ ours) × 300 across the full five-year period; the price advantage above is measured against the $15,809,306 fully-loaded bid.
IBM Consulting · Health & Human Services · WA CIE · ties to the Funding scenarios tab · US-only delivery per RFP Sec. 3.6.4 · rates are assumptions pending the rate card

## Slide 11
06j
Re-derivation Against Evidence
Connect360 corrected by its product owner · the WPCO codebase read
conditional on proofs P1–P8 · the deck body keeps the verified baseline
−32.00
ASSET FTE-MONTHS
151.35 → 119.35 across five years
−$1.18M
IBM INVESTMENT
$5.56M → $4.39M · a 21% reduction
$9.63M
WASHINGTON PRICE
unchanged — no client line moved
8
PROOFS OUTSTANDING
P1–P8 · none costs more than an hour
CONNECT360 — CORRECTED BY THE PRODUCT OWNER, 17 SEP
P1
Consent enforcement
◐ covered at the platform
withhold a Part-2 record from a CBO search, live
P2
Certification
◐ HITRUST certified
certificate, scope boundary, what the joint solution inherits
P3
Worker UI
◐ exists, needs extension
show the screen; agree the extension list
P4
RBAC
◐ controls present
role assignment and a denied cross-org read
P5
Directory
◐ own directory provided
content, currency and the statewide federation path
P6
Identity matching
◐ PIX / PDQ supported
a live PIX query; agree the WPCO integration contract
P7
Referral
◐ supported, incl. non-clinical
a tracked non-clinical referral through to close
P8
Events
◐ handling based on NAS
subscription fan-out, ordering and replay
◐ stated by the product owner, not yet demonstrated to us. Product-owner knowledge of their own platform outranks an outsider’s API probe — it does not outrank a demonstration, and the demonstration scores 350 points.
WHERE THE 32.00 FTE-MONTHS CAME OFF
CY | WAS | NOW | DELTA | WHAT EARNED THE CREDIT
2027 | 31.35 | 23.85 | −7.50 | C360 consent, RBAC, directory, PIX/PDQ, referral, NAS, worker UI, HITRUST
2028 | 23.00 | 18.00 | −5.00 | carePlan + careTeam 4,104 LOC · cohort and region routes · CI ratchets
2029 | 40.00 | 28.50 | −11.50 | graph 7,844 LOC / 101 tests · sde 1,775 · agentRuntime real-impl
2030 | 27.00 | 22.00 | −5.00 | 2 HITL agent manifests with allowlists · carePlan 2,188 LOC
2031 | 30.00 | 27.00 | −3.00 | policy 26,639 LOC is already policy-as-data · measures thin
TOT | 151.35 | 119.35 | −32.00 | 41% of five-year effort is asset, down from 47%
WHAT THE CODEBASE DID NOT EARN
Multi-agent orchestration (9.00), the agent evaluation harness (4.00), TEFCA / QHIN (5.00), granular consent (4.00 — the register’s own F2 says Part-2 segmentation is a blunt drop on a wrong basis) and the integration façade and verb set (4.50) are unchanged. Dispatch is a 378-line skeleton and earned almost nothing.
Evidence cut IBM’s investment, not Washington’s price. Under position A the client column sets the bid, and not one client line moved — the state still pays $9,629,181 over five years.
The rule applied: evidence moves a line from BUILD to INTEGRATE or EXTEND. It never moves a line to zero — integration, extension and hardening are real work — and it never touches the client column. All 24 changed lines carry a stated reason in the Re-derivation v2 tab. The deck body still carries the verified 151.35 / 31.35 baseline, because a ◐ must not be shown to Washington as fact; it is re-numbered when P1–P8 land.
IBM Consulting · Health & Human Services · WA CIE · class-4 estimate, conditional on P1–P8 · ties to the Re-derivation v2 tab · revision R9

## Slide 12
07
Two Solution Models
A: Connect360 + WPCO · B: TogetherNow + Databricks base, WPCO the decision plane
an analytical plane and a presentation plane — the plane between them is the question
PRESENTATION PLANE
TogetherNow · MyWayfinder
participant and CBO portal · resource directory · consent capture (“Journey of Trust”) · navigation · HRSN screening
DECISION PLANE
WPCO — the gap
signal → disposition → accountable owner → governed action → signed evidence
· governed agent runtime with a human-in-the-loop gate, tool allowlists and a fairness interlock
· signal dispositioning with a consent gate — who is accountable for this, now
· policy-as-data: eligibility, routing and escalation changed without code
· an exactly-once operational spine — outbox, idempotency, dead-letter, replay
· decision provenance, signed — why this person got this action
· terminology conformance, fail-closed
Neither partner has any of it. A lakehouse analyses; a portal presents; this decides and acts.
ANALYTICAL PLANE
Databricks
ingestion · Delta Lake longitudinal store · Unity Catalog governance and lineage · entity resolution · analytics and ML
THE UNPRICED LAYER
Every operational decision would read through a lakehouse. Lakehouse latency is not operational latency — a referral state machine or a crisis pathway cannot run off a batch medallion. An operational store between Delta and the app is required, and nobody has priced one. WPCO already has it.
WPCO KEEPS — code-evidenced, unique in the stack
✓
Governed agent runtime
agentRuntime real-impl 1,354 + governance 517
✓
Signal dispositioning
sde 1,775 with a consent gate
✓
Policy-as-data
policy 26,639 LOC, 117 tests
✓
Operational spine
outbox · idempotency · dead-letter · evidence ledger
✓
Decision provenance
signed — not data lineage
✓
Terminology gate
3,914 LOC, fail-closed
✓
FHIR façade + verbs
Delta Sharing is not a FHIR API
✓
Assurance architecture
29 seams, 22 fail-closed, 83 findings
WPCO CEDES
→ Resource directory · consent capture UI · HRSN screening
MyWayfinder
→ Analytics · data quality · mapping · dedup · batch matching
Databricks
→ The longitudinal store itself
Delta Lake
→ The general worker portal — keep CHW, crisis, panel, inbox
MyWayfinder
WHAT IS LEFT FOR CONNECT360
Six of its eight strengths are taken — directory and consent capture by MyWayfinder, identity resolution, governance, analytics and the record store by Databricks, and both certifications by Databricks. Three things neither partner covers: the FHIR API surface that utilisation models #3 and #4 require; PIX / PDQ, which is the protocol a partner queries and is not the same thing as Databricks’ analytical entity resolution; and real-time operational event handling. Connect360 narrows to an identity-protocol and clinical-interop layer — or it has no role, and that gap becomes WPCO’s.
The asset argument changes from “we build the CIE platform” — which invites “why not just buy Databricks?” — to “we build the governed layer that makes the CIE act, on whatever data platform you already own.” That is platform-agnostic, which neutralises HCA’s existing Snowflake estate rather than defending against it.
IBM Consulting · Health & Human Services · WA CIE · stack B teaming is UNCONFIRMED (A27) · ties to the Solution models A vs B tab

## Slide 13
07a
The Two Models, Costed
ceding build effort does not cede integration effort — across four organisations it adds it
all figures against the annual ceilings · class-4 · platform licence is the swing factor
−13.55
ASSET FTE-MONTHS
119.35 → 105.80 · IBM saves $497,962
+12.70
CLIENT FTE-MONTHS
169.15 → 181.85 · three seams, not one
+$1.19M
WASHINGTON PAYS MORE
$9.63M → $10.81M over five years
$237K
THE CROSSOVER
platform licence per year at which B breaks even
CY | A ASSET | B ASSET | A CLIENT | B CLIENT | A PRICE | B PRICE | DELTA | CEILING
2027 | 23.85 | 20.80 | 40.15 | 43.85 | $2.23M | $2.51M | +$284K | $3.40M
2028 | 18.00 | 12.00 | 42.00 | 45.00 | $2.25M | $2.50M | +$256K | $3.40M
2029 | 28.50 | 27.00 | 26.00 | 28.00 | $1.60M | $1.81M | +$215K | $3.50M
2030 | 22.00 | 22.00 | 33.00 | 35.00 | $1.88M | $2.10M | +$215K | $3.50M
2031 | 27.00 | 24.00 | 28.00 | 30.00 | $1.68M | $1.89M | +$215K | $3.50M
TOT | 119.35 | 105.80 | 169.15 | 181.85 | $9.63M | $10.81M | +$1.19M | $17.30M
Both models clear every annual ceiling. The difference is the cost score — 300 of 1000 points, scored as (lowest evaluated cost ÷ ours) × 300.
PLATFORM-LICENCE SENSITIVITY — THE DOMINANT VARIABLE
$0/yr
$8.31M
−$1.31M
$150K/yr
$9.15M
−$0.48M
$237K/yr
$9.63M
break-even
the line nobody has measured
$300K/yr
$9.98M
+$0.35M
$450K/yr
$10.81M
+$1.19M
$600K/yr
$11.65M
+$2.02M
Nobody has sized the licence (A26), so nobody knows which side of $237,000 this bid sits on. It is the cheapest number in the analysis to establish and the one that decides the model.
WHAT THE NUMBERS SAY
Stack B is a poor trade on price.
IBM saves $498K of investment; Washington pays $1.19M more. On a 300-point cost score that is the wrong direction.
The saving is real but small.
Ceding the directory, capture UI, analytics and batch matching removes 13.55 asset FTE-months. The decision plane is most of what was left.
Integration eats the saving.
Four organisations, three seams, three release cadences: +12.70 client FTE-months, and the November demonstration has no single party able to show the whole flow.
B wins on other grounds, if at all.
Certification inherited, platform credibility, co-sell, risk transfer — and platform-agnosticism that neutralises HCA’s Snowflake estate. Those are strategic arguments, not price arguments.
Ceding scope to partners cuts what IBM invests and raises what Washington pays. Choose stack B for certification, credibility or risk transfer — not to win on cost.
IBM Consulting · Health & Human Services · WA CIE · stack B teaming UNCONFIRMED (A27) · platform licence unsized (A26) · revision R10

## Slide 14
ASK
The Executive Ask
commit two years → renewal options → decide this quarter
WA CIE · proposal due 23 October 2026
PROVEN Connect360 is live, deployed on Azure and Marketplace-listed, with a real HIE integration in production · WPCO supplies the governed intelligence layer. US-ONLY DELIVERY per RFP Sec. 3.6.4 — the prior 54.3% offshore blend is void for this bid and every figure below is repriced.
1
COMMIT THE TWO-YEAR TERM — CY2027–28 · the only years Washington commits to
Committed term — MVP + Phase 2 $4.48M
CY2027 MVP $2.23M — Washington’s 40.15 deployment FTE-months: configuration, 6–8 partner integrations, directory content, WaTech review, programme and operations. The 31.35 FTE-months that build the product are absorbed by IBM. CY2028 Phase 2 $2.25M — deployment of shared care plan, granular consent and population analytics; the engines themselves are asset.
2
THEN THE RENEWAL OPTIONS — CY2029–31 (at Comagine’s sole discretion · no right or expectation of renewal)
CY2029 · Phase 3 begins
$1.60M
Event notification ingest and exchange, the knowledge graph rebuilt by replaying the MVP event log, journey engine, WPC context ranking behind the existing seam.
CY2030 · Real-time & inference
$1.88M
Real-time dispatch, signal dispositioning engine, graph inference and household linkage, enrollment verification, remaining change subscriptions.
CY2031 · Agents & maturation
$1.68M
Governed agents over the MVP domain verbs and actor model, care-plan intelligence, forecasting and equity monitoring, advanced consent interoperability.
Operations, support & recertification
CONTINUOUS
Tier-2/3 application support, defect resolution and root-cause analysis; annual HITRUST and SOC 2 recertification and penetration testing; governance participation. Comagine owns tier 1. Runs from MVP go-live to the end of the programme — inside each year, not a separate ask.
wk 26 → end
FIVE-YEAR EVALUATED PRICE = $9.63M against a $17.3M envelope · $7.67M headroom · every year clears its ceiling at a 10% margin · $6.18M below a bid that charges the product build to the state
DECISION REQUESTED THIS QUARTER
Approve $5.56M of base-asset investment across five years — $2.00M of it inside the committed term — carried on the product P&L, not the deal · run the six gate tests, which decide $2,205,000 of CY2027 scope and none costs more than a day · settle the teaming structure on HITRUST and SOC 2, which changes Submittal Form A · submit the two written questions to Comagine by 9 October.
IBM Consulting · Health & Human Services · The Executive Ask · ties to the Funding scenarios tab ($9,629,181 base position) · US-only delivery per RFP Sec. 3.6.4 · rates are assumptions pending the rate card · estimate class 4