## Slide 1
Washington Community
Information Exchange
Optimized delivery plan — joint Connect360 + WPCO response
CIE-scoped, US-only priced, and sequenced to the annual funding ceilings
Revision of the ACE / WHPC delivery plan · proposal due 23 October 2026

## Slide 2
Executive verdict
The re-scoped plan fits the five-year envelope. One year is tight, and one condition decides whether it is deliverable at all.
$15.81M
five-year price
against a $17.3M envelope — $1.49M of headroom
−$108,472
CY2027 at 10% margin
the only year over its ceiling; it fits at about 7%
$4.7M
construction-case gap
if the platform gaps must be built, no pricing structure recovers CY2027
Recommendation. Bid it on the configuration case, at a thin year-one margin recovered in CY2028–31 where there is headroom — and run six tests before Submittal Form F is priced. Those six tests, none costing more than a day, decide $2,205,000 of CY2027 scope.
What this plan is | What it is not
A CIE-scoped delivery plan for a joint Connect360 + WPCO response: configuration, integration, implementation and operations of a platform that exists before contract signature. | It is not the payer asset build. Roughly $2.35M of named scope in the prior plan has no WA CIE buyer at any phase and has been deleted rather than deferred.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
02

## Slide 3
Two decisions reshaped the plan
Both are read directly from the RFP. Together they move the estimate more than any sequencing choice.
01
No offshore content is permitted
RFP Sec. 3.6.4 — "All services under the resulting contract, by the Contractor and any Subcontractors at any tier, must be performed within the United States or its territories."
The prior estimate’s 54.3% offshore blend is void for this bid. Repriced at onshore premium, the prior committed figure moves from $5,093,845 to $8,023,500, and Position B from $6,316,265 to $10,573,650. This plan is priced at a blended $36,750 per FTE-month.
02
The plan was built for a payer; the buyer is a CIE
Zero occurrences of claims adjudication, 837/835, HCC/CDPS, DRG grouping, HEDIS, prior authorisation, CMS-0057-F or payer-to-payer exchange appear anywhere in the RFP, the Concept of Operations or the 212 requirements.
X12 appears once, as one of several payload formats an adapter must transform, with "or equivalent" in the acceptance criterion. That is an adapter, not a claims spine.
Consequence: deletion, not deferral. Deferral moves cost; deletion removes it — and only deletion makes $3.4M a year work.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
03

## Slide 4
The RFP inverts the plan
The payer plan schedules population analytics early and referrals late. The procurement does the opposite, in writing.
Capability family | MVP reqs | RFP phase | Prior plan | Revised
Referral management | 15 | MVP — 30 Jun 2027 | Wave 4, wk 34–42 | CY2027
Client record | 14 | MVP | Wave 1 | CY2027
Consent management | 13 | MVP | Wave 1 | CY2027
Resource directory | 12 | MVP | Wave 4, wk 46–54 | CY2027
Care coordination | 11 | MVP | Wave 3 | CY2027
Identity & access management | 10 | MVP | Wave 1 (no role model exists) | CY2027 — grows
Reporting & analytics — operational | 9 | MVP | Wave 2 | CY2027
Population & equity analytics | — | Phase 2, named in writing | Wave 2, wk 18 — first | CY2028
Event notification | — | Phase 3 | Wave 1 | CY2029
Client-facing portal | — | Phase 3 | Wave 5 | Does not fit
103 of 146 functional requirements carry a Phase 1 / MVP tag and are due 30 June 2027. All 66 non-functional requirements are MVP — security, consent segmentation, access control, audit, accessibility and 99.5% API availability apply from day one with no ramp.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
04

## Slide 5
What moved out — deletion, not deferral
Named deletions total $2,354,350. The unnamed payer scope inside Wave 1 is larger again.
Deleted from the plan | Value | Why it has no WA CIE buyer
Prior-Auth / Coverage / Financial Clearance bucket | $1,004,750 | Payer utilisation management
CMS-0057-F bucket | $545,050 | A CIE is not an impacted payer under the rule
Epic / Cerner SMART launch + CDS Hooks write-back | $506,250 | MVP partners are CBO and HMIS systems more than EHRs
ADF / Databricks secondary path | $298,300 | A reusable-asset hedge for Databricks-native payer clients
Claims / X12 / NCPDP spine, SNIP, corrections and voids, coding verification | ~58 Gantt wks | No claims adjudication anywhere in scope
HCC/CDPS+Rx, DRG/APR-DRG, episode groupers; RAF stratification and coding gaps | — | Payer risk adjustment
HEDIS / Stars / MIPS load to Measure / MeasureReport | — | Quality measurement is a payer function
Total cost of care, gain-share, braided funding, executive finance dashboard | — | Payer financial analytics
Dual-backend abstraction, tenant-onboarding automation, asset packaging | — | Product investment, not bid scope. One hosted deployment
Every line of the original plan carries a disposition and a reason in the workbook’s Revision log: KEEP · MOVE · REDUCE · SPLIT · RESHAPE · DEFER · DELETE · ADD.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
05

## Slide 6
What moved in — twelve workstreams the plan did not contain
Each one is either contractually required, architecturally irreversible, or was withdrawn in error from the prior estimate.
Participant portal, worker-facing
No worker UI exists in Connect360 — only API surface — and the prior staffing model had no front-end engineering role at all
RBAC & delegated org administration
No role or permission type appears in the 553 introspected types. IAM is a named MVP capability
Event publication contract
The keystone: stable type vocabulary, idempotency, ordering, 3–5 subscriptions exposed
Owned, versioned integration façade
Do not make another vendor’s internal schema the State’s public integration contract
Domain verbs + reason codes
Generic CRUD on Task guarantees drift across a federation of independent organisations
Read-side reporting projection
The proxy blocks cheap aggregates, so no count is answerable from the FHIR path
citizenEverything resolver
Nine resolvers fan out N+1 on the most-loaded screen
Certification lane
HITRUST r2, SOC 2 Type II, pen test, WaTech SDR and PTA — a pre-condition of launch
Accessibility — 508 / WCAG 2.1 AA, VPAT
Absent from the entire prior pack
Section 1557 language access
Absent from the entire prior pack
Tribal & IHS data sovereignty
RESTORED — withdrawn as "geography-specific". Washington has 29 federally recognised tribes
Directory federation adapter
RESTORED — withdrawn as "per-deployment content". The directory is a named MVP capability
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
06

## Slide 7
How the engines survive being deferred
The knowledge graph, the longitudinal record, the four engines and the agents all remain in the plan — and all arrive later.
A capability is safely deferrable if, and only if, it can be reconstructed from what MVP wrote down.
WRITE PATH — irreversible. A fact not captured cannot be recovered. This is what CY2027 buys.
READ PATH — deferrable. A function of history, computable at any future date. This is every engine you named.
Recorded at MVP — CY2027 | Arrives later, behind that seam
The edge set — relationships as dated, provenance-bearing facts | The knowledge graph as a running projection · CY2029, hydrated by replaying the MVP event log
The event log — stable types, idempotency, ordering | Every engine that consumes it · CY2029–31
The temporal spine, recorded on every state change | The journey engine over it · CY2029
The citizenEverything seam | WPC context ranking behind it · CY2029, with no partner-facing change
A stable event-type vocabulary | Signal dispositioning · CY2030
Domain verbs with recorded actor and reason; a non-human actor in the audit model | Governed agents · CY2031
The sharper version of the position: the graph is foundational in Phase 2, and the only way to have it in Phase 2 is to record its edges and publish its events at MVP. That is three to four weeks of architect and FHIR-engineer time against 45 duration weeks in the original plan.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
07

## Slide 8
CY2027 — the MVP to 30 June 2027
71.5 FTE-months, $3,157,625 delivered cost. Configuration case. Tiers 1 and 2 start week 1 and complete before partner onboarding begins.
TIER 1
Irreversible — the write path
Identity with non-destructive merge · consent provision model and enforcement · provenance and cross-org audit · RBAC · event log
9.5
FTE-mo
$349,125
TIER 2
Contract surfaces
Owned versioned integration façade · domain-verb mutations and the statewide reason-code vocabulary
6.0
FTE-mo
$220,500
TIER 3
The MVP product
Participant portal · read-side projection · conform and write · citizenEverything · directory adapter · referral workflow · HRSN screening
24.5
FTE-mo
$900,375
TIER 4
Compliance engineering
Accessibility 508 / WCAG 2.1 AA and VPAT · Tribal and IHS data sovereignty
4.5
FTE-mo
$165,375
NON-BUILD
What the contract actually pays for
Certification evidence and WaTech SDR · partner onboarding factory (6–8) · programme management and 23 deliverables · operations and tier-2/3
27.0
FTE-mo
$992,250
CY2027 total · 71.5 FTE-months · $2,627,625 labour + $530,000 non-labour = $3,157,625 delivered cost
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
08

## Slide 9
Five-year plan, right-sized to the annual ceilings
Each year is scoped to what that year’s ceiling can fund at the target margin — not to the wish list.
CY | What it delivers | FTE-mo | Cost | Price @10% GM | Ceiling | Headroom
2027 | MVP — identity, consent, referral, directory, record, operational reporting, portal | 71.5 | $3,157,625 | $3,508,472 | $3,400,000 | −$108,472
2028 | Shared care plan · granular consent · population & equity analytics · next partner cohort | 65.0 | $2,868,750 | $3,187,500 | $3,400,000 | $212,500
2029 | Event notification · knowledge graph by replay · journey engine · WPC ranking | 66.0 | $2,905,500 | $3,228,333 | $3,500,000 | $271,667
2030 | Real-time dispatch · signal dispositioning · graph inference · enrollment verification | 60.0 | $2,685,000 | $2,983,333 | $3,500,000 | $516,667
2031 | Governed agents · care-plan intelligence · forecasting · advanced consent interoperability | 58.0 | $2,611,500 | $2,901,667 | $3,500,000 | $598,333
Total |  | 320.5 | $14,228,375 | $15,809,306 | $17,300,000 | $1,490,694
Does not fit the five-year envelope at all — 51 FTE-months, $1,874,250
Client-facing portal · agentic marketplace and orchestration at scale · household and family thread · agent impact and ROI reporting
Stated plainly: the full WPCO vision does not fit inside the WA CIE envelope. The engines and the graph arrive; the marketplace and the client portal do not. If they matter they need a second funding source — which is an argument for a pipeline, not for loading them into this bid.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
09

## Slide 10
What $3,400,000 actually buys in CY2027
Gross margin is the lever that decides whether the configuration case fits. The construction case does not fit at any margin.
Chart: CY2027 price by gross margin, against the $3.4M ceiling
| 5% | 7.5% | 10% | 15% | 20% | 25%
Configuration case | 3323816 | 3413649 | 3508472 | 3714853 | 3947031 | 4210167
Construction case | 7695132 | 7903108 | 8122639 | 8600441 | 9137969 | 9747167
Configuration case
Fits at roughly 7% gross margin; about $108,000 over at 10%. A closeable gap — three FTE-months of scope, or a thinner year-one margin recovered in CY2028–31 where there is headroom.
Construction case
184.5 FTE-months. $4.3M to $6.3M over the ceiling at every margin tested. Exceeding an annual ceiling may be deemed nonresponsive and may not be scored — there is no pricing structure that recovers it.
Ask Comagine in writing
Evaluated Cost is defined twice in Sec. 5.7 — three components in one version, four in the other, with Year-1 recurring counted both on its own and inside the five-year total.
Priced US-only at a blended $36,750 per FTE-month — 55% from a US delivery centre or territory at $30,000, 45% onshore premium at $45,000. Both rates are assumptions; no rate card has been supplied.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
10

## Slide 11
Six tests decide $2,205,000 of CY2027 scope
None costs more than a day. Run them before Submittal Form F is priced — they decide which case this bid is in.
Gate | The question | Cost to answer | Swing | If it fails
G3 | Can the existing Connect360 portal be extended to worker roles, or is a new worker application required? | Repo review + staff-scoped demo | 27.0 FTE-mo $992,250 | A new build is 26 FTE-months of front-end at one concurrent engineer — the floor, not the estimate
G5 | Is the resource directory carved out to the statewide directory partner? | Written question to Comagine by 9 Oct | 10.0 FTE-mo $367,500 | We own corpus sourcing and curation — an operation, not code
G2 | Does Connect360 hold current HITRUST r2 and SOC 2 Type II? | One call | 8.0 FTE-mo $294,000 | Decides deliverability. HITRUST r2 from a standing start is 9–18 months against a 25-week runway — this bid then needs a certified partner
G4 | Does a role / permission model with delegated organisation administration exist? | Schema review | 5.5 FTE-mo $202,125 | No role or permission type appears in the 553 introspected types
G6 | Does matchPerson / resolveIdentity exist, and can it be fronted? | One call | 5.0 FTE-mo $183,750 | No $match, no PIX, no PDQ at the gateway; the EMPI rests on a verbal statement
G1 | Is provision.securityLabel enforced at QUERY time, not just stored? | One hour | 4.5 FTE-mo $165,375 | The pipeline writes labels nothing enforces — worse than no labelling, and the claim is carried into the WaTech Security Design Review
G2 decides whether this bid is deliverable at all — and it changes the teaming structure, which changes Submittal Form A. That cannot wait.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
11

## Slide 12
What this plan rests on
Twenty numbered assumptions sit in the workbook. These are the ones carrying the most weight.
ASSUMPTIONS
A3 / A4 — both labour rates are assumptions
$30,000 US delivery centre and $45,000 onshore premium. No rate card has been supplied; the prior plan’s rates were marked ILLUSTRATIVE. That caveat is now three document versions old and sits on a $15.8M number.
A5 — 55% from a US delivery centre or territory
Puerto Rico and Guam are US territories and are the only legitimate low-cost lever under Sec. 3.6.4. Key personnel, SMEs, architects and client-facing roles are onshore premium.
A11 — Connect360 is pre-existing at signature
Both the commercial position and the only posture under which an offshore-built platform is lawful alongside the US-only services clause.
A12 — the configuration case
The entire plan assumes the six gate tests pass.
OPEN RISKS
Two-year term, five-year plan
CY2029–31 are renewals at Comagine’s sole discretion, with no right or expectation of renewal. Build the investment case on CY2027–28 alone — $6.8M gross.
Section 701 gates the cash
Milestone gates and budget approvals before funds release, and no advance or mobilisation payment exists in the RFP. Decompose CY2027 into 8–12 acceptance milestones.
Three MVP capabilities sit in another IBM org’s backlog
The composite resolver, 21 unexposed subscriptions, and matchPerson. Get dates in writing or price them as owned.
Non-labour is only partly modelled
Chargeback, Azure, assessor fees and travel are in. Terminology licensing, HISP fees and AIRS membership are not.
Estimate class 4 on class 4 inputs — expected accuracy roughly −20% / +30%. Read headline figures to the nearest $100,000 and treat the precision in the workbook as internal consistency, not accuracy.
WA CIE optimized delivery plan | joint Connect360 + WPCO response | 17 Sep 2026
12

## Slide 13
What happens next
Thirty-six days to the proposal. The sequence below is ordered by what blocks what.
01
Run the six gate tests
Start with G2 (certification) and G3 (portal). Together they decide $1.29M and whether the bid is deliverable.
02
Settle the teaming structure
If Connect360 does not hold HITRUST and SOC 2, this bid needs a partner who does — and that changes Submittal Form A.
03
Submit two questions by 9 October
Is the resource directory in scope, and which of the two conflicting Evaluated Cost definitions governs.
04
Get the real US rate card
With a vintage and a named delivery-centre location. Every figure here is directional until then.
05
Build the demonstration
350 of 1000 points, 16–20 November, on scenarios Comagine supplies. Identity, consent, referral, closed loop.
Washington is not funding the construction of a CIE platform. It is funding the configuration of one that is already running.
13