## Slide 1
06
Delivery Timeline — Overview
MVP → phase gates → renewal options · CY2027–2031
WA CIE · joint Connect360 + WPCO response
26 wks
MVP GO-LIVE
30 June 2027 · 103 MVP requirements
wk 14
SURFACES FROZEN
before the first partner integrates
wk 24
WaTech SDR PASSED
gates every byte of HCA data
6–8
PARTNERS IN PRODUCTION
integrated at MVP
Jan 2027
Jan 2028
Jan 2029
Jan 2030
Jan 2031
Dec 2031
surfaces frozen wk14
MVP GO-LIVE wk26
CY2027
MVP
Write path · contract surfaces · MVP product · compliance · certification · WaTech SDR wk24 · 6–8 partners
$3.16M
CY2028
Phase 2
◆ GATE 1 — shared care plan · granular consent · population & equity analytics · next cohort
$2.87M
CY2029–31
Phase 3
◆ GATE 2 — event notification · knowledge graph by replay · journey engine · WPC ranking · real-time dispatch · governed agents · care-plan intelligence
$8.20M
Operations &
recertification
↻ tier-2/3 support · annual HITRUST / SOC 2 recertification · governance participation — continuous from go-live
DOES NOT FIT THE ENVELOPE
Client-facing portal · agentic marketplace · household thread · agent ROI — needs a second funding source
$1.87M
MVP go-live 30 June 2027 with 6–8 interoperability partners in production. Each phase is scoped to what that year’s funding ceiling can fund, not to the wish list. Five-year evaluated price $15.81M against a $17.3M envelope — $1.49M of headroom. CY2027 is the only year over its ceiling: $108,472 at a 10% margin, and it fits at roughly 7%. Renewal options CY2029–31 are exercised at Comagine’s sole discretion; only CY2027–28 is committed.
Detail follows — 06b: CY2027 MVP roadmap and release table

## Slide 2
06b
CY2027 MVP Roadmap (wk 1–34)
Sequenced by irreversibility, not by value · contract start 4 Jan 2027
Tiers 1 and 2 complete before any partner integrates
wk1
wk8
wk14
wk20
wk26
wk34
Tier 1 · write path
identity · consent · provenance & audit · RBAC · event log
9.5
Tier 2 · contract surfaces
integration façade · domain verbs + reason codes
6.0
Tier 3 · MVP product
participant portal · read-side projection · conform & write · citizenEverything · directory adapter · referral · HRSN
24.5
Tier 4 · compliance
508 / WCAG 2.1 AA + VPAT · Tribal & IHS data sovereignty
4.5
Certification lane
HITRUST / SOC 2 evidence · penetration test · WaTech SDR + Privacy Threshold Analysis
4.0
Partner onboarding
6–8 interoperability partners — a factory, not eight bespoke projects
10.0
Programme management
23 deliverables · bi-weekly plan · monthly reports · RAID · governance
8.0
Operations · tier 2/3
Comagine owns tier 1
5.0
DELETED
claims / X12 / NCPDP spine · HCC/CDPS & DRG groupers · HEDIS · total cost of care · CMS-0057-F · prior authorisation · Epic/Cerner SMART · ADF/Databricks · asset packaging — no WA CIE buyer at any phase
Milestones
surfaces frozen wk14
SDR passed wk24
MVP GO-LIVE wk26
impl. ends wk34
WORKSTREAM | WKS | FTE-mo | WHAT LANDS, AND WHEN
Tier 1 · irreversible write path | 1–14 | 9.5 | ◆ Stable CIE identifier, permanent source-ID retention, non-destructive merge/unmerge with link history and a stewardship queue. ◆ Full R4 consent provision shape, enforcement at the data layer, revoke-not-delete, securityLabel from the first record. ◆ Provenance per write and cross-org read audit. ◆ Durable event log — stable types, idempotency, ordering.
Tier 2 · contract surfaces | 4–14 | 6.0 | ◆ Owned, versioned integration façade profiled to US Core + SDOHCC. ◆ Domain-verb mutations with the statewide reason-code vocabulary. — Both land BEFORE the first partner integrates; once 6–8 organisations hold production integrations the surface cannot be taken away.
Tier 3 · MVP product | 6–26 | 24.5 | ◆ Participant portal extended to worker roles — match adjudication, record view, consent capture, HRSN screening, referral create/receive/track/close, directory search, org admin. ◆ Read-side projection with operational counts and a participant extract. ◆ citizenEverything resolver. ◆ Directory federation adapter.
Tier 4 + certification | 1–25 | 8.5 | ◆ 508 / WCAG 2.1 AA, VPAT / ACR and remediation. ◆ Tribal and IHS data sovereignty — 29 federally recognised tribes. ◆ HITRUST r2 and SOC 2 evidence, penetration test, WaTech SDR and Privacy Threshold Analysis — a pre-condition of launch with an immediate-termination trigger.
Onboarding · PM · operations | 1–34 | 23.0 | ◆ 6–8 partners in production at go-live, run as a repeatable factory with a per-partner acceptance milestone. ◆ 23 deliverables, bi-weekly plan updates, monthly reports, RAID. ◆ Tier-2/3 support from go-live; Comagine owns tier 1.
IBM Consulting · Health & Human Services · WA CIE CY2027 MVP · 71.5 FTE-months · $3,157,625 delivered cost · ties to the Gantt and Staffing tabs · US-only delivery per RFP Sec. 3.6.4 · illustrative rates

## Slide 3
ASK
The Executive Ask
commit two years → renewal options → decide this quarter
WA CIE · proposal due 23 October 2026
PROVEN Connect360 is live, deployed on Azure and Marketplace-listed, with a real HIE integration in production · WPCO supplies the governed intelligence layer. US-ONLY DELIVERY per RFP Sec. 3.6.4 — the prior 54.3% offshore blend is void for this bid and every figure below is repriced.
1
COMMIT THE TWO-YEAR TERM — CY2027–28 · the only years Washington commits to
Committed term — MVP + Phase 2 $6.70m
CY2027 MVP $3.51M (71.5 FTE-mo) — identity, consent, client record, referral, directory, operational reporting, participant portal, 6–8 partners. CY2028 Phase 2 $3.19M (65.0 FTE-mo) — shared care plan, granular consent, population & equity analytics.
2
THEN THE RENEWAL OPTIONS — CY2029–31 (at Comagine’s sole discretion · no right or expectation of renewal)
CY2029 · Phase 3 begins
$3.23M
Event notification ingest and exchange, the knowledge graph rebuilt by replaying the MVP event log, journey engine, WPC context ranking behind the existing seam.
CY2030 · Real-time & inference
$2.98M
Real-time dispatch, signal dispositioning engine, graph inference and household linkage, enrollment verification, remaining change subscriptions.
CY2031 · Agents & maturation
$2.90M
Governed agents over the MVP domain verbs and actor model, care-plan intelligence, forecasting and equity monitoring, advanced consent interoperability.
Operations, support & recertification
CONTINUOUS
Tier-2/3 application support, defect resolution and root-cause analysis; annual HITRUST and SOC 2 recertification and penetration testing; governance participation. Comagine owns tier 1. Runs from MVP go-live to the end of the programme — inside each year, not a separate ask.
wk 26 → end
FIVE-YEAR EVALUATED PRICE = $15.81M against a $17.3M envelope · $1.49M headroom · CY2027 is the only year over its ceiling: −$108,472 at a 10% margin, and it fits at roughly 7%
DECISION REQUESTED THIS QUARTER
Run the six gate tests — they decide $2,205,000 of CY2027 scope and none costs more than a day · settle the teaming structure on HITRUST and SOC 2, which changes Submittal Form A · approve the bid at a thin CY2027 margin recovered in the later years · submit the two written questions to Comagine by 9 October.
IBM Consulting · Health & Human Services · The Executive Ask · ties to the Cost by Scope tab ($15,809,306) · US-only delivery per RFP Sec. 3.6.4 · rates are assumptions pending the rate card · estimate class 4