## Prompt Chain
seq | step_id | trace_id | ts | iteration | wave | phase | depends_on | builds_on | agent_role | agent_label | workstream_domain | prompt_summary | key_inputs | output_summary | gate_result | findings | fidelity | review_note
1 | 0001 | TRC-P-0-0001 | 2026-01-05T09:07:00Z | P | 0 | probe |  | genesis: grounds the whole plan in real repo evidence | evidence | P1-repo-gate-evidence | planning/evidence | Phase-0 probe of the sibling repos; assemble the evidence pack + use-case steps that ground the plan. | sibling repos; owner intent | phase0_repo_gate.md, evidence.md, use_case_steps.md | grounded |  | recon | P-phase agents were not captured verbatim (pre-E10); metadata exact, prompt condensed. This roster row makes them visible in the log.
2 | 0002 | TRC-P-spine-0002 | 2026-01-05T09:14:00Z | P | spine | plan | 1 | the architectural spine every specialist inherits | spine | P2-spine | planning/architecture | Author ADR-001..006, contracts C1..C10, the golden path, the 16-step trace matrix, and a per-specialist context manifest. | P1 evidence; owner constraints | load-model, adrs, contracts, golden-path, trace-matrix, manifests | authored |  | recon | The spine is the shared context the 5 specialists branch from - the planning analogue of an iteration probe.
3 | 0003 | TRC-P-spec-0003 | 2026-01-05T09:21:00Z | P | spec | plan | 2 | feeds the iter2 graph build | specialist | P3-graph-context-G1 | planning/graph | Design the graph projector, mapping specs, and lens queries (G1). | P2 spine | g1-graph.md | authored |  | recon | One of 5 parallel design specialists on disjoint concerns.
4 | 0004 | TRC-P-spec-0004 | 2026-01-05T09:28:00Z | P | spec | plan | 2 | feeds the iter1 pipeline+outbox build | specialist | P4-pipeline-fhir-G3X2 | planning/pipeline | Design the 5-stage pipeline, adapters, outbox, and validation (G3/X2). | P2 spine | g3-pipelines.md | authored |  | recon | Parallel design specialist.
5 | 0005 | TRC-P-spec-0005 | 2026-01-05T09:35:00Z | P | spec | plan | 2 | feeds the iter2 SDE + iter3 runtime builds | specialist | P5-agentic-G2G4 | planning/agentic | Design the SDE and the agent runtime (G2/G4). | P2 spine | g2g4-agentic.md | authored |  | recon | Parallel design specialist.
6 | 0006 | TRC-P-spec-0006 | 2026-01-05T09:42:00Z | P | spec | plan | 2 | feeds the iter0 care-plan hardening | specialist | P6-careplan-G5 | planning/care-plan | Design care-plan hardening + the DP-4 acceptance oracle (G5). | P2 spine | g5-careplan.md | authored |  | recon | Parallel design specialist.
7 | 0007 | TRC-P-spec-0007 | 2026-01-05T09:49:00Z | P | spec | plan | 2 | feeds the D7 doc pack | specialist | P7-documentation-X4 | planning/docs | Design the D7 doc pack + the honesty ledger (X4). | P2 spine | x4-documentation.md | authored |  | recon | Parallel design specialist.
8 | 0008 | TRC-P-use-case-0008 | 2026-01-05T09:56:00Z | P | use-case | plan | 2 | the corpus later becomes executable scenario tests at I0 wave 3B | use-case-expert | P8-TCOC-70-use-case-expert | planning/verification-corpus | ACT AS TCOC SME PANEL (10 specialty lenses): devise the 70-use-case verification corpus that the platform must satisfy - families A-O, each with actor, trigger, expected orchestration, and TCOC lever. THIS IS THE 70-USE-CASE AGENT. | P1 evidence; P2 golden path; 10 SME lenses | use_case_corpus.md - 70 cases, families A-O | authored |  | recon | << The 70-use-case agent you asked about. Its OUTPUT (use_case_corpus.md) is committed; its prompt lives in the transcript. Downstream: seq for I0/3B corpus-scenario turns it into runnable tests.
9 | 0009 | TRC-P-adversarial-0009 | 2026-01-05T10:03:00Z | P | adversarial | red-team | 3,4,5,6,7,8 | the FIRST adversarial pass - the ancestor of the R1-R4 red-team personas | red-team | P9-adversarial-rubric-panel | planning/review | Adversarially score all 5 design specialists against a rubric; surface cross-cutting findings the specialists missed on their own. | P3-P7 specialist designs; P8 corpus | adversarial-verdict.md - 3 cross-cutting findings (C1 orphan, ADR-006 atomicity, compliance orphans) | findings |  | recon | The planning-phase red team. Its 3 findings triggered a DYNAMIC RE-PROMPT of the spine (next row).
10 | 0010 | TRC-P-amend-0010 | 2026-01-05T10:10:00Z | P | amend | fix | 9 | << DYNAMIC RE-PROMPT LINEAGE: P2 spine -> P9 adversarial findings -> P10 same-agent re-prompt -> amendment. The clearest multi-turn lineage in the whole build. | spine | P10-spine-amendment-REPROMPT | planning/architecture | RECONVENE the spine agent WITH CONTEXT INTACT (SendMessage): resolve the 3 adversarial findings - C1 orphan, ADR-006 atomicity, compliance orphans. | P9 findings; P2 spine (same agent, context retained) | amendment-001.md | resolved |  | recon | THIS is the lineage you asked about: an agent re-prompted with updated context (its own prior output + the red-team findings), not a one-shot. Chain: seq2 -> seq10.
11 | 0011 | TRC-P-data-0011 | 2026-01-05T10:17:00Z | P | data | plan | 8,10 | materializes the 70-case corpus as the D1 trace sheet | data | P11-data-extractor-D1 | planning/datasets | Build the D1 workbook datasets (5 sheets incl. the 70-case trace matrix) from the resolved plan. | P8 corpus; P10 amended spine | sheet1-5.json -> D1_Gap_Matrix.xlsx | authored |  | recon
12 | 0012 | TRC-P-data-0012 | 2026-01-05T10:24:00Z | P | data | plan | 10 | the specs iterations 9-10 will execute | spec-author | P12-spec-author-D4D5 | planning/specs | Author the D4 load-test spec + the D5 deployment-config spec. | P10 amended spine | D4_load_test_spec.md, D5_deployment_config_spec.md | authored |  | recon
13 | 0013 | TRC-P-final-0013 | 2026-01-05T10:31:00Z | P | final | fix | 10,11,12 | the plan package that the build phase (I0) inherits | orchestrator | P13-finalizer | planning/assembly | Assemble + QA the D1-D7 plan package; commit. Hand the plan to the build phase. | all P outputs | docs/production-plan/D1-D7 committed | committed |  | recon | Bridge from planning to build: I0's probe depends on this row.
14 | 0014 | TRC-0-probe-0014 | 2026-01-05T10:38:00Z | 0 | probe | probe | 13 |  | probe | cycle1-probe | harness | Harness health probe: echo, write, edit a file; confirm tool access before fan-out. | baseline tree | tools working | clean->fanout |  | live | E6 probe standard; cheap insurance before parallel build.
15 | 0015 | TRC-0-1A-0015 | 2026-01-05T10:45:00Z | 0 | 1A | build | 14 |  | specialist | mechanical-sweeper | persona/determinism/logging | Four sweeps: purge persona-in-logic, inject clock/rng in engines, structured PHI-safe logger over console.log, silent-catch audit. | conventions v2; evidence.md | 2 logic fixes; 31 files determinism seam; logger; 0 console.log | tsc0; ratchet ok |  | recon | Grep-driven cleanup framed as defect classes worked; classify data-vs-logic to avoid touching legit demo data.
16 | 0016 | TRC-0-1B-0016 | 2026-01-05T10:52:00Z | 0 | 1B | build | 14 |  | specialist | route-test-author | bff-routes | TESTING AGENT: cover all 21 API routes: 401/403/400/422/200 + PHI-safe body; skip infra-bound with reason. | route handlers; _helpers pattern | 107 route tests, 9 named skips | green |  | recon | << Testing agent (route). Test-file-only (no src edits) kept it disjoint from the sweeper.
17 | 0017 | TRC-0-1-conv-0017 | 2026-01-05T10:59:00Z | 0 | 1-conv | convergence | 15,16,18,19,20,23,24 |  | convergence | cycle1-convergence-x2 | cross-cutting | Re-sweep determinism/console/persona; review mode-registry; converge to DRY (2 passes). | cycle1 reports | determinism stragglers + demoDefaults; DRY on 2nd pass | DRY |  | recon | Two passes needed; convergence found what build waves missed.
18 | 0018 | TRC-0-1-2-0018 | 2026-01-05T11:06:00Z | 0 | 1-2 | build | 14 |  | specialist | mode-registry | config/dataMode | Consolidate scattered mock toggles into one config-driven dataMode registry (mock¦seeded¦production per seam). | runtimeConfig; consent seam | dataMode.ts + session override; consent+fhir wired | green |  | recon | This became the mock->production switch mechanism the owner later relied on.
19 | 0019 | TRC-0-2A-0019 | 2026-01-05T11:13:00Z | 0 | 2A | build | 14 |  | specialist | property-test-author | engines | TESTING AGENT: property tests for match/policy/adequacy/goldenThread/consent engines; ~3000 generated cases via seeded PRNG. | engine source | found REAL match bug: blank/whitespace fields -> false matches | green (2 it.fails) |  | recon | << Testing agent (property). Earned its place immediately; caught a patient-safety defect.
20 | 0020 | TRC-0-2B-0020 | 2026-01-05T11:20:00Z | 0 | 2B | build | 14 |  | specialist | careplan-hardening | care-plan | Extract 1262-line frozen generator into carePlan/ modules; DP-4 acceptance oracle (fixtures+invariants). | carePlanGenerator*; g5 design | 14 modules; frozen files 1269->66 lines; 47 tests; 9 findings | green |  | recon | Ratchet moved forward: legacy files shrank via extraction, not edits.
21 | 0021 | TRC-0-2-conv-0021 | 2026-01-05T11:27:00Z | 0 | 2-conv | convergence | 15,16,18,19,20,23,24 |  | convergence | cycle2-convergence | identity | Fix the blank-field match bug family across deterministic + probabilistic tiers; flip it.fails. | cycle2a findings | guard non-empty both sides; regression tests | DRY |  | recon | Fixed a real correctness bug found by property tests, not weakened the test.
22 | 0022 | TRC-0-3A-0022 | 2026-01-05T11:34:00Z | 0 | 3A | red-team | 15,16,18,19,20,23,24 |  | red-team | security-lens | api-security | Attack all routes: authz bypass, consent scoping, PHI in errors, IDOR, input validation, AI-guardrail. | api routes; authz | 2 HIGH (consent-read bypass, IDOR); fixed match consent gate | green |  | recon | First real adversarial security pass; found the IDOR class later fully closed in I3.
23 | 0023 | TRC-0-3B-0023 | 2026-01-05T11:41:00Z | 0 | 3B | build | 14 | consumes P8's 70-use-case corpus - the planning->build link for the use cases | specialist | corpus-scenario | verification | TESTING AGENT: turn the 70-case corpus (P8 output) into executable scenario tests where code exists; register the rest as pending. | use_case_corpus.md (P8) | 15 runnable, 55 pending, all 70 accounted | green |  | recon | << Testing agent (corpus). This is where P8's 70 use cases become a living regression asset.
24 | 0024 | TRC-0-3C-0024 | 2026-01-05T11:48:00Z | 0 | 3C | build | 14 |  | specialist | e2e-a11y-specs | e2e | TESTING AGENT: author C5 demo walkthrough + dual-mode + axe specs (CI-runnable; live run sandbox-blocked). | playwright config; routes | 20 specs; found + fixed a Next illegal-export bug | tsc0 |  | recon | << Testing agent (e2e/a11y). Honest CI-pending labeling; build compiled but dev server would not boot in sandbox.
25 | 0025 | TRC-1-probe-0025 | 2026-01-05T11:55:00Z | 1 | probe | probe | 22 |  | probe | iter1-probe | harness/pg-mem | Probe pg-mem + confirm dataMode/clock/log seams exist. | baseline | pg-mem ok | clean |  | live | Added infra probe (pg-mem) to the harness check since this iteration needs SQL.
26 | 0026 | TRC-1-A-0026 | 2026-01-05T12:02:00Z | 1 | A | build | 25 |  | specialist | pipeline+outbox | pipeline/outbox | Five-stage pipeline + 3 adapters (834/ADT/CBO); lane-agnostic transforms; ADR-006 outbox-intent propagation. | plan 4A; C2/C10; ADR-006 | 17 modules; outbox intent->confirm->event; 36 tests | green |  | live | Adapters generic over records; identity via injected resolver seam (later found to be a stub).
27 | 0027 | TRC-1-B-0027 | 2026-01-05T12:09:00Z | 1 | B | build | 25 |  | specialist | persistence+adapters | evidence/dataSources | O-1 append-only pg evidence ledger behind seam; O-2 gold-card/denial/provider loaders. | ADR-005; evidence interface | ledger + immutability trigger; 3 adapters; 31 tests | green |  | live | Reused the existing EvidenceStore interface verbatim; no caller changed.
28 | 0028 | TRC-1-C-0028 | 2026-01-05T12:16:00Z | 1 | C | convergence | 26,27 |  | convergence | security+convergence | security/outbox | Fix 2 HIGH IDOR/consent; adversarial review of A+B; DRY. | cycle3 security report | consent-read fixed; flagged multi-writer outbox gaps for I2 | DRY |  | live | Documented the real-Postgres outbox concurrency gap rather than hiding it (L1 in action).
29 | 0029 | TRC-2-A-0029 | 2026-01-05T12:23:00Z | 2 | A | build | 28 | builds on iter1 outbox (event source) | specialist | graph-projector+backends | graph | Harden outbox (UNIQUE+CAS); store-agnostic projector; Postgres + Neo4j adapters on one interface; shared contract test. | ADR-001 v12.3; C10; iter1 outbox | projector + both backends; parity proven; 30 tests | green |  | live | Step-0 outbox hardening carried the I1 concurrency gap forward (L4 lesson: should have been in I1 DoD).
30 | 0030 | TRC-2-B1-0030 | 2026-01-05T12:30:00Z | 2 | B1 | build | 28 |  | specialist | lens-suite+replay | graph/lens | 5 lens queries passing on BOTH backends; Part 2 restriction; rebuild-from-replay; merge/unmerge rekey. | wave A graph; DP-1 | dual-backend parity on all 5 lenses + replay + merge | green |  | live | Co-equal backend guarantee proven in code, not asserted.
31 | 0031 | TRC-2-B2-0031 | 2026-01-05T12:37:00Z | 2 | B2 | build | 28 | consumes graph/pipeline signals | specialist | sde-disposition | sde | Disposition service: signal taxonomy, act/suppress/delay/bundle, policy-as-data, consent-gated, explainable. | DP-2; demo SDE shape | 5/3/1 shape EMERGES from policy; 26 tests; flagged seam-id collision | green |  | live | Agent flagged the sde seam-id collision itself (good), fixed in convergence.
32 | 0032 | TRC-2-C-0032 | 2026-01-05T12:44:00Z | 2 | C | convergence | 29,30,31 |  | convergence | iter2-convergence | graph/sde | Fix seam-id collision; verify projector purity (no SQL/Cypher in core); Part 2 both backends; DRY. | B1/B2 reports | signalDisposition seam; purity confirmed; DRY | DRY |  | live | Seam-id collision is the L3 lesson origin.
33 | 0033 | TRC-3-probe-0033 | 2026-01-05T12:51:00Z | 3 | probe | probe | 32 |  | probe | iter3-probe | harness | Probe; locate the work-queue store to reuse (no second inbox). | baseline | workQueueView found | clean |  | live | Probe located the HITL surface to reuse.
34 | 0034 | TRC-3-A-0034 | 2026-01-05T12:58:00Z | 3 | A | build | 33 |  | specialist | agent-runtime+registry | agentRuntime/agents | Journey-lane WorkflowEngine + in-memory fake + Temporal seam; manifest registry (data); escalation-as-data; HITL proposeAndWait via work queue. | g2g4 design; conventions s10 | runtime + manifests; FAKE_FIDELITY.md; 26 tests | green |  | live | L1 fake-fidelity ledger shipped as a required deliverable for the workflow fake.
35 | 0035 | TRC-3-A2-0035 | 2026-01-05T13:05:00Z | 3 | A2 | build | 33 |  | specialist | idor-role-model | authz/principal | Session-principal role model; close evidence + financial-clearance IDOR; remove hardcoded pa-reviewer. | cycle3 security; match-route pattern | principal model; 2 IDOR it.fails flipped; 24 tests | green |  | live | Ran parallel to A on a disjoint tree (authz vs runtime).
36 | 0036 | TRC-3-B-0036 | 2026-01-05T13:12:00Z | 3 | B | build | 33 | consumes SDE dispositions via iter3 runtime | specialist | three-agents | agents | Outreach/referral/PA-doc agent behaviors on the runtime; HITL; PA-doc never sets authoritative state. | wave A runtime; sde output | decide->act->HITL->execute loop reproduced; PA guardrail asserted; 18 tests | green |  | live | The AI-guardrail (agent never sets PA state) is tested, not just claimed.
37 | 0037 | TRC-3-C-0037 | 2026-01-05T13:19:00Z | 3 | C | convergence | 34,35,36 |  | convergence | iter3-convergence | agents | Cross-agent namespace integrity; confirm 1 expected-fail is legit; determinism; HITL genuinely suspends. | A/A2/B reports | found F-C1 namespace drift across 3 surfaces; pinned by test; DRY | DRY |  | live | L3 refinement origin: pre-allocate AND pin names across all surfaces.
38 | 0038 | TRC-4-A-0038 | 2026-01-05T13:26:00Z | 4 | A | build | 37 | establishes template reused by all later domains | specialist | template+medications | pipeline/medications | Author the L7 domain template + checklist; build medications (prescribed+dispensed) through it. | existing adapters; medication FHIR | _TEMPLATE.md + medications T1; pinning test; 14 tests | green |  | live | Templatize-before-mass-produce (L7); medications stress-tested the two-node shape.
39 | 0039 | TRC-4-EMPI-0039 | 2026-01-05T13:33:00Z | 4 | EMPI | build | 37 | replaces the iter1 identity stub | specialist | empi-resolver | identity | OWNER LITMUS: wire the REAL match engine as identity resolver; possible-match 60-90 HELD not auto-linked; demographics-carrying seam. | matchEngine; owner directive | EMPI resolver; HELD path; 14 tests | green |  | live | Owner caught the hash-stub. Prompt folded the fix in-iteration rather than deferring.
40 | 0040 | TRC-4-B-0040 | 2026-01-05T13:40:00Z | 4 | B | build | 37 | fills the iter4 template | specialist | labs+allergies | pipeline/labs/allergies | Build labs-vitals + allergies through the template. | _TEMPLATE.md | 2 domains T1; 26 tests | green |  | live | First proof the template makes domains a fill-in.
41 | 0041 | TRC-4-EXT-0041 | 2026-01-05T13:47:00Z | 4 | EXT | build | 37 |  | specialist | external-seams | identity/terminology | OWNER DIRECTIVE: stub external EMPI (PIX/PDQ, PIXm/PDQm) + terminology/semantic-validation seam (RxNorm/LOINC/HCC) fail-closed. | owner directive; NotConfigured pattern | external identity + terminology seams; stage-4 semantic gate; 28 tests | green |  | live | Stubs now, real later; honest fail-closed stubs, roadmap I8A created. << external EMPI stubs here become REAL at I8A-i wave B.
42 | 0042 | TRC-4-C-0042 | 2026-01-05T13:54:00Z | 4 | C | build | 37 | fills the iter4 template | specialist | procedures | pipeline/procedures | Build procedures through the template. | _TEMPLATE.md | procedures T1; 14 tests; record 7/20 | green |  | live
43 | 0043 | TRC-4-VSM-0043 | 2026-01-05T14:01:00Z | 4 | VSM | build | 37 |  | specialist | value-set-registry | terminology/registry | OWNER DIRECTIVE: value-set/ontology lifecycle registry across 6 classification families (HCC is one of several). | owner directive; terminology seam | registry facility; 26 assets/6 families; 16 tests | green |  | live | Owner: HCC is only one; behavioral+social families added. Governance-console scoped to I8A.
44 | 0044 | TRC-4-C-conv-0044 | 2026-01-05T14:08:00Z | 4 | C-conv | convergence | 38,39,40,41,42,43 |  | convergence | iter4-convergence | pipeline/identity/terminology | Cross-agent: namespace pin all 4 domains; double gate order; seed covers all demo codes; DRY. | 6 wave reports | 1 doc-only finding; DRY; record 7/20 | DRY |  | live | Six parallel agents; convergence reconciled cleanly.
45 | 0045 | TRC-V-panel-0045 | 2026-01-05T14:15:00Z | V | panel | red-team | 44 |  | red-team | domain-fidelity-adversary | healthcare-standards | [verbatim: verbatim/red-team-and-adversarial-prompts.md R1] Audit I0-4 for naive/stubbed/missing healthcare-standard mechanisms (X12, EMPI survivorship, terminology, Part2, FHIR conformance). | summaries + code | 26 findings (4 Critical incl 834-term, Part2, EMPI survivorship, $validate stub) | registered |  | live | R1 persona. Found what conformance review missed; validates L9. Prompt now captured verbatim.
46 | 0046 | TRC-V-panel-0046 | 2026-01-05T14:22:00Z | V | panel | red-team | 44 |  | red-team | negative-space-adversary | operability | [verbatim: red-team-and-adversarial-prompts.md R2] Find what is ABSENT that production needs; must produce a missing-list not a pass. | summaries + code | 31 findings (dead-letter drop, right-to-delete, observability, idempotency) | registered |  | live | R2 persona. NS-01 (records vanish) drove Iteration 5. Prompt now captured verbatim.
47 | 0047 | TRC-V-panel-0047 | 2026-01-05T14:29:00Z | V | panel | red-team | 44 |  | red-team | stub-legitimacy-adversary | stubs | [verbatim: red-team-and-adversarial-prompts.md R3] Grade every seam/stub Acceptable/Risky/Unacceptable; find fail-open/masquerade/dead-wiring. | seam code | 26 graded; 4 Unacceptable (dev-auth fail-open, validator fail-open, EMPI mock-in-prod, evidence dead-wiring) | registered |  | live | R3 persona. The 4 Unacceptable were worse than what the owner caught (they mislead). Prompt now captured verbatim.
48 | 0048 | TRC-V-fix-0048 | 2026-01-05T14:36:00Z | V | fix | fix | 44 |  | specialist | unacceptable-fixes | seams | Fix the 4 Unacceptable: make each fail CLOSED in production, demo green. | stub findings; NotConfigured pattern | U1-U4 fixed fail-closed; 22 tests | green |  | live | High-integrity: spotted AND fixed the worst, not just logged.
49 | 0049 | TRC-V-gate-0049 | 2026-01-05T14:43:00Z | V | gate | fix | 44 |  | specialist | governance-seam-gate | config/governance | Build mechanical fail-closed gate: seam-disposition manifest + test forcing every seam to declare + prove fail-closed. | seam registry | 17 seams declared; 29 governance tests; new seam with no disposition fails CI | green |  | live | E1 enforcement: the durable prevention (gate over prose).
50 | 0050 | TRC-5-probe-0050 | 2026-01-05T14:50:00Z | 5 | probe | probe | 49 |  | probe | iter5-probe | harness | Probe pg-mem; locate quarantine/held-identity producers. | baseline | heldIdentity.ts found | clean |  | live
51 | 0051 | TRC-5-A-0051 | 2026-01-05T14:57:00Z | 5 | A | build | 50 | persists records the pipeline/EMPI/outbox previously dropped | specialist | dead-letter-subsystem | deadLetter | Durable dead-letter/held-review store (quarantine¦held-identity¦failed-outbox); wire at call sites so nothing vanishes; ops reviewer surface. | NS-01; producers | store + ops routes; producers persist; 44 tests; seam declared | green |  | live | Closed the Critical operability gap; ops surface distinct from clinical work queue.
52 | 0052 | TRC-5-B-0052 | 2026-01-05T15:04:00Z | 5 | B | build | 50 | guards iter2 SDE + iter3 agents against outbox republish | specialist | idempotency+session-secret | idempotency/authz | Durable idempotency store (per-consumer CAS); wire SDE+agents; R5 session-secret fail-closed. | NS-04; R5 | idempotency store; SDE+agents dedupe on republish; secret fails closed; 29 tests | green |  | live
53 | 0053 | TRC-5-C-0053 | 2026-01-05T15:11:00Z | 5 | C | red-team | 51,52 |  | convergence+red-team | iter5-convergence+panel | deadLetter/idempotency | [RECONSTRUCTED in red-team-and-adversarial-prompts.md] Converge; then mandatory red-team panel (R1 reliability/data-integrity, R2 negative-space, R3 stub-legitimacy). | A/B reports; register | found+fixed a re-introduced fail-open drop-path; R1 5/R2 10/R3 3 findings; DRY | DRY | R1:5 R2:10 R3:3 | live | Panel caught a re-introduced NS-01 fail-open the build missed. I5 lens=reliability. Prompt reconstructed (pre-E10).
54 | 0054 | TRC-6-probe-0054 | 2026-01-05T15:18:00Z | 6 | probe | probe | 53 |  | probe | iter6-probe | harness | Probe; enumerate current C9 domains; find 834 adapter. | baseline | 8 domains found (care-team already a graph node) | clean |  | live | Probe+scope-enum prevented a duplicate-domain assumption.
55 | 0055 | TRC-6-A-0055 | 2026-01-05T15:25:00Z | 6 | A | build | 54 | fills the template; extends iter2 careteam lens | specialist | careteam+goalstasks | pipeline/care-team/goals-tasks | Build care-team + goals-tasks through template; EXTEND existing careteam mapping without breaking the I2 lens. | _TEMPLATE.md; careteam.ts | 2 domains T1; lens preserved; 28 tests; namespace split to companion file | green |  | live | Shared-file (namespace test) split improvised mid-run; future briefs should pre-declare the partition (L3 refinement).
56 | 0056 | TRC-6-B-0056 | 2026-01-05T15:32:00Z | 6 | B | build | 54 | fills the template | specialist | referrals+immunizations | pipeline/referrals/immunizations | Build referrals + immunizations through template; keep provider refs RAW + flag deferred-I8A (no invented NPI). | _TEMPLATE.md | 2 domains T1; provider deferred-I8A; 27 tests | green |  | live | Keep-unresolved-entity-raw-and-flagged is the durable anti-masquerade clause. << the deferred-I8A provider refs get resolved at I8A-i wave C.
57 | 0057 | TRC-6-C-0057 | 2026-01-05T15:39:00Z | 6 | C | red-team | 55,56 | reuses iter5 idempotency; fixes iter1 834 adapter | convergence+red-team | iter6-foldins+panel | pipeline/deadLetter/834 | [RECONSTRUCTED] Fold-ins: idempotency reuse in dead-letter; 834 INS-3 termination fix. Then converge + mandatory red-team panel. | register F1+HIGH; wave reports | both fold-ins fixed; found+fixed latent 834 fail-open; R1 5/R2 7/R3 3; DRY; record 11/20 | DRY | R1:5 R2:7 R3:3 | live | Red-team caught a fail-open AGAIN (834 default-to-active). Fail-open is the recurring top class -> candidate mechanical lint E9. I6 lens=care-coordination.
58 | 0058 | TRC-7-probe-0058 | 2026-01-05T15:46:00Z | 7 | probe | probe | 57 |  | probe | iter7-probe | harness | [verbatim: verbatim/iteration-7-verbatim.md] probe; locate Part2 handling + PA state machine. | baseline | Part2 thin; paMachine found | clean |  | live | Probe confirmed Part 2 handling thin (F2).
59 | 0059 | TRC-7-A-0059 | 2026-01-05T15:53:00Z | 7 | A | build | 58 | closes F2 (Part 2 segmentation) | specialist | behavioralHealth+part2 | pipeline/behavioral-health | [verbatim: iteration-7-verbatim.md waveA] BH+SUD domain + real Part2 segmentation (basis, consent-directed, re-disclosure, break-glass). | iteration7_context F2 spec | BH T1; SUD restricted; break-glass audited; 21 tests | green |  | live | HIGH CARE wave; two-factor Part2 basis + over-restriction guard.
60 | 0060 | TRC-7-B-0060 | 2026-01-05T16:00:00Z | 7 | B | build | 58 |  | specialist | claims+paLifecycle | pipeline/claims/pa-lifecycle | [verbatim: iteration-7-verbatim.md waveB] claims-financial (Claim/ClaimResponse/EOB chain, CARC/RARC) + pa-lifecycle (status lifecycle, non-authoritative). | paMachine | 2 domains T1; PA capture non-authoritative asserted; 34 tests | green |  | live | pa-lifecycle references but never drives paMachine (guardrail).
61 | 0061 | TRC-7-C-0061 | 2026-01-05T16:07:00Z | 7 | C | build | 58 |  | specialist | assessments+caregiver+documents | pipeline/assessments/caregiver/documents | [verbatim: iteration-7-verbatim.md waveC] assessments (QuestionnaireResponse T1) + caregiver (RelatedPerson T1) + documents (DocumentReference T2, honest). | _TEMPLATE.md | 3 domains; documents honestly T2; 39 tests | green |  | live | documents T2 not a hidden T1 claim.
62 | 0062 | TRC-7-D-0062 | 2026-01-05T16:14:00Z | 7 | D | red-team | 59,60,61 | advances F2; first composed prompt; E9 standing sweep | convergence+red-team | iter7-convergence+panel | pipeline/part2/claims | [verbatim: iteration-7-verbatim.md waveD - FIRST COMPOSED v1.1 PROMPT] convergence + E9 fail-open sweep + red-team (R1=Part2/privacy+financial, R2 negative-space, R3 stub-legitimacy). | wave reports; register; framework v1.1 | E9 found+fixed 2 Unacceptable Part2 fail-opens; R1 8/R2 9/R3 findings; F2 advanced; DRY; record 17/20 | DRY | R1:8 R2:9 R3:fixed2 | live | First composed-prompt agent (v1.1). E9 standing sweep caught top-severity class on top-stakes surface.
63 | 0063 | TRC-8A-i-probe-0063 | 2026-01-05T16:21:00Z | 8A-i | probe | probe | 62 |  | probe | iter8ai-probe | harness/identity | [verbatim: verbatim/iteration-8ai-verbatim.md] probe pg-mem; locate I4 external-EMPI stubs + deferred-I8A provider refs. | baseline | pgmem ok; external stubs found; deferred-I8A refs present | clean |  | live | Probe confirmed the I4 stubs to make real + the deferred provider refs to resolve.
64 | 0064 | TRC-8A-i-A-0064 | 2026-01-05T16:28:00Z | 8A-i | A | build | 63 | closes F3; uses DP-7 replay-rekey from iter2 graph | specialist | survivorship+crossReference | identity/survivorship/crossReference | [verbatim: iteration-8ai-verbatim.md waveA - COMPOSED v1.1] F3: member<->source xref (link/unlink/merge/unmerge, replay-rekey) + source-ranked survivorship rules-as-data, golden record as PROJECTION. Fix fragmentation. | iteration8ai_context F3; DP-7 | xref+survivorship built; two feeds->one member; golden-record projection; seam declared; tests green | green |  | live | F3 core fix: id-only second-feed record LINKS to existing member, not a new mint.
65 | 0065 | TRC-8A-i-B-0065 | 2026-01-05T16:35:00Z | 8A-i | B | build | 63 | makes the iter4 external-EMPI stubs real | specialist | external-empi-real | identity/external | [verbatim: iteration-8ai-verbatim.md waveB - COMPOSED v1.1] Make PIX/PDQ (HL7v2 QBP^Q23/Q22) + PIXm/PDQm (FHIR $ihe-pix / Patient search) REAL query+parse vs a fake MPI; fail-closed without live endpoint; external results respect HELD. | iteration8ai_context; I4 external stubs | PIX/PDQ + PIXm/PDQm real logic; fail-closed w/o MPI; HELD on low-confidence; tests green | green |  | live | Advances the I4 labeled-stubs to real adapter logic; live endpoint CI-pending.
66 | 0066 | TRC-8A-i-C-0066 | 2026-01-05T16:42:00Z | 8A-i | C | build | 63 | closes F5; resolves the iter6 deferred-I8A provider refs | specialist | provider-identity-npi | identity/provider | [verbatim: iteration-8ai-verbatim.md waveC - COMPOSED v1.1] F5: NPI Luhn validation + provider resolver (seeded dir for tests, NPPES fail-closed in prod); ProviderIdentity graph node; deferred-I8A refs now resolve; no invented NPI. | iteration8ai_context F5; deferred-I8A refs | NPI validation; provider resolves to node; fail-closed w/o NPPES; deferred refs resolved; tests green | green |  | live | F5 fix. Anti-masquerade: unresolvable provider stays raw+flagged, never a fabricated NPI.
67 | 0067 | TRC-8A-i-D-0067 | 2026-08-22T21:19:00Z | 8A-i | D | red-team | 64,65,66 | closes/advances F3+F5; identity/interoperability red-team lens | convergence+red-team | iter8ai-convergence+panel | identity/interoperability | [verbatim: verbatim/iteration-8ai-verbatim.md waveD - COMPOSED v1.2] convergence to DRY + E9 fail-open sweep (identity: ambiguous match -> HELD not wrong link) + red-team panel (R1=IHE PIX/PDQ+EMPI survivorship+NPPES lens, R2 negative-space, R3 stub-legitimacy on new external seams) + register update (close F3/F5). | wave A/B/C reports; register F3/F5; framework v1.2 | convergence DRY (dataMode/seamDispositions reconciled, identity/index barrel completed); E9 fixed-1 Unacceptable (PDQ/PDQm fabricated enterprise anchor via ?? ids[0] -> empty-anchor HELD, +2 regression tests); R1 4 (1 Unacceptable-fixed, 2 MED, 1 LOW); R2 7-item missing-list; R3 3 Acceptable/0 open; F3 CLOSED; F5 CLOSED; orchestrator gate: tsc0, 1198 pass +1 expected-fail, size+E1(33) PASS | DRY | R1:4 R2:7 R3:0open E9:fixed1 | live | E9 standing sweep caught the wrong-person-link class AGAIN (fabricated enterprise anchor from a peer id) on the highest-stakes surface - identity - exactly as it caught the Part 2 fail-opens in I7. F3 residual: live-pg cutover -> NS-05. F5 residual: F5-b HIGH (claims/care-team/medication provider refs still to resolve) -> backlog. Orchestrator re-ran the authoritative gate independently (E5).
68 | 0068 | TRC-8A-ii-probe-0068 | 2026-08-23T01:30:00Z | 8A-ii | probe | probe | 67 |  | probe | iter8aii-probe | harness/terminology | Orchestrator inline probe of the I4 terminology surface: semanticValidator, seed/production services, valueSetRegistry + 6 families, the declared terminology seam. | baseline src/lib/terminology | seed allowlist + fail-closed prod stub confirmed; scoped 3 disjoint waves | clean |  | live | Probe done by the orchestrator (not a subagent); logged for E11 completeness.
69 | 0069 | TRC-8A-ii-A-0069 | 2026-08-23T01:45:00Z | 8A-ii | A | build | 68 | makes the I4 terminology stub real (validate/expand/version/UCUM) | specialist | terminology-validate+expand | terminology/validateCode/expand | [verbatim: verbatim/iteration-8aii-verbatim.md waveA - COMPOSED v1.2] make validateCode real (member-of-bound-value-set-version) + $expand + version/retired awareness + UCUM on LOINC quantities; production fail-closed. | iteration8aii_context WaveA; terminology seed+registry | validateCode real; $expand; retired-code rejected with version; UCUM; 29 tests; prod fail-closed | green |  | live | Member-of-version validity replaces the flat allowlist; retired-code path wired into the stage-4 gate.
70 | 0070 | TRC-8A-ii-B-0070 | 2026-08-23T01:46:00Z | 8A-ii | B | build | 68 | adds $translate crosswalks + HCC/risk classification on the I4 seam | specialist | terminology-translate+classify | terminology/translate/classify | [verbatim: iteration-8aii-verbatim.md waveB - COMPOSED v1.2] $translate over seeded crosswalks (ICD-10<->CMS-HCC, SNOMED<->ICD-10) + HCC classification data-driven; risk families (CMS-HCC/RxHCC/HHS-HCC/CDPS) as data; untranslatable->no-map. | iteration8aii_context WaveB | translate real w/ asset+version; no fabricated maps; HCC classify data-driven; risk families enumerated; 16 tests; live crosswalk fail-closed | green |  | live | HCC is one family of several (owner directive honored). Seed labeled synthetic, not the full licensed map.
71 | 0071 | TRC-8A-ii-C-0071 | 2026-08-23T01:47:00Z | 8A-ii | C | build | 68 | binds the stage-4 semantic gate; reuses the dead-letter quarantine | specialist | terminology-pipeline-binding+currency | terminology/registry/pipeline | [verbatim: iteration-8aii-verbatim.md waveC - COMPOSED v1.2] bind the stage-4 semantic gate for code-carrying domains (quarantine bad/retired codes via existing dead-letter path, no new store) + value-set currency enforcement (stale/expired binding quarantines). | iteration8aii_context WaveC; semanticValidator; deadLetter | pipeline binding quarantines bad code; currency enforced on stale versions; reuse-not-duplicate; 24 tests | green |  | live | Reused the semanticValidator + dead-letter quarantine; no duplicated validation logic and no new store.
72 | 0072 | TRC-8A-ii-D-0072 | 2026-08-23T02:05:00Z | 8A-ii | D | red-team | 69,70,71 | advances the terminology stub to real logic; terminology/semantic red-team lens | convergence+red-team | iter8aii-convergence+panel | terminology/semantic | [verbatim: iteration-8aii-verbatim.md waveD - COMPOSED v1.2] convergence to DRY + E9 fail-open sweep (terminology: unverifiable/retired->quarantine, untranslatable->no-map, stale version not silently valid) + red-team panel (R1 terminology/semantic-interoperability lens, R2 negative-space, R3 stub-legitimacy on seed/crosswalk data) + register. | wave A/B/C reports; register; framework v1.2 | convergence DRY (consolidated a drifted duplicate ICD-10->HCC map); E9 clean (8 shapes justified); R1 7/R2 8/R3 6 all Acceptable (1 Risky fixed); register 8A-ii section; orchestrator gate tsc0, 1267 pass +1 expected-fail, size+E1(33) PASS | DRY | R1:7 R2:8 R3:6 E9:clean | live | Convergence caught a drifted DUPLICATE crosswalk map (DRY defect the build waves missed) and consolidated it - the convergence pass earning its place. Residuals: live terminology server + full licensed maps -> backlog.
73 | 0073 | TRC-8A-iii-probe-0073 | 2026-08-23T02:30:00Z | 8A-iii | probe | probe | 72 |  | probe | iter8aiii-probe | harness/governance | Orchestrator inline probe: admin-console sibling pages, valueSetRegistry API, authz principal/role model, append-only evidence ledger to reuse; scoped 3 disjoint waves + shared-file partitions. | baseline src/app/admin-console, terminology/registry, authz, evidence | reuse surfaces confirmed; namespace pre-allocated | clean |  | live | Probe by orchestrator; logged for E11 completeness.
74 | 0074 | TRC-8A-iii-A-0074 | 2026-08-23T02:47:00Z | 8A-iii | A | build | 73 | governs the terminology value-set versions (lifecycle+approval+audit+replay) | specialist | governance-backend-lifecycle | terminology/governance | [verbatim: verbatim/iteration-8aiii-verbatim.md waveA - COMPOSED v1.2] value-set version lifecycle state machine + ENFORCED maker-checker (config single-approver) + immutable evidence-ledger audit + chosen-version replay; valueSetGovernanceStore seam fail-closed. | iteration8aiii_context WaveA; registry; evidence ledger; validateCode | lifecycle guarded; maker-checker enforced (MakerCheckerViolationError); single-approver configurable; immutable audit + history; chosen-version replay (no fallback); one-active invariant; 19 tests; seam-gate 27 | green |  | live | Separation-of-duties enforced in code, not advice. Reused the evidence ledger as the immutable audit trail (no new store).
75 | 0075 | TRC-8A-iii-B-0075 | 2026-08-23T02:48:00Z | 8A-iii | B | build | 73 | admin/UI over the governance backend; reuses admin-console patterns | specialist | governance-console-ui | admin-console/value-set-governance | [verbatim: iteration-8aiii-verbatim.md waveB - COMPOSED v1.2] dual-mode admin/UI governance console: version list+states, diff, approval gates (maker-checker disable), audit timeline, replay panel; nav entry; no browser storage. | iteration8aiii_context WaveB; admin-console patterns | console renders; gates by role/mode; maker-checker approve disabled for maker; replay panel; dual-mode; 5 render tests (new React test infra scoped in-partition) | green |  | live | Bound to a local read-model adapter mid-flight (waves parallel); Wave D collapsed it to real delegation.
76 | 0076 | TRC-8A-iii-C-0076 | 2026-08-23T02:49:00Z | 8A-iii | C | build | 73 | role-gated BFF over the governance backend; maker-checker at the boundary | specialist | governance-bff-routes | api/value-set-governance | [verbatim: iteration-8aiii-verbatim.md waveC - COMPOSED v1.2] BFF routes submit/approve/reject/retire/replay/history, role-gated (steward vs reviewer), maker-checker enforced at the route boundary (defense in depth), PHI-safe, CALL the backend not duplicate. | iteration8aiii_context WaveC; authz guard; _helpers | routes role-gated; maker-checker at boundary (403 self-approve); call-not-duplicate; PHI-safe; 20 route tests | green |  | live | Defense-in-depth: maker-checker enforced at both backend and route boundary.
77 | 0077 | TRC-8A-iii-D-0077 | 2026-08-23T03:10:00Z | 8A-iii | D | red-team | 74,75,76 | collapses the console adapter to real delegation; closes the I8A block | convergence+red-team | iter8aiii-convergence+panel | governance/workflow-integrity | [verbatim: iteration-8aiii-verbatim.md waveD - COMPOSED v1.2] convergence (extract single maker-checker predicate; collapse console adapter to real delegation) + E9 fail-open sweep (unapproved->not active; no self-approve; replay binds chosen version; unauth fails closed) + red-team (governance/workflow-integrity + auditability lens) + register; CLOSES the I8A block. | wave A/B/C reports; register; framework v1.2 | convergence DRY (single makerChecker.ts predicate; adapter collapsed to real delegation); E9 fixed-1 Unacceptable (resolveGovernanceBackend bound ?? integrationDouble served in-memory as production - now fails closed); R1 4/R2 7/R3 3; register 8A-iii section; I8A CLOSED; orchestrator gate tsc0, 1314 pass +1 expected-fail, size+E1(34) PASS | DRY | R1:4 R2:7 R3:3 E9:fixed1 | live | E9 caught a MASQUERADE fail-open (an in-memory double served as durable production governance) - the stub-legitimacy class the owner's original identity-stub concern was about, now caught by the standing sweep. I8A block (identity+terminology+governance) closed.
78 | 0078 | TRC-9-probe-0078 | 2026-08-23T03:15:00Z | 9 | probe | probe | 77 |  | probe | iter9-probe | harness/substrate | Orchestrator inline probe: per-store pg adapters + SQL migrations already exist (evidence/idempotency/outbox/graph); memory-only crossReference+governance; env.ts fail-closed pattern; 23 seams. Scoped substrate/deploy/lifecycle waves. | baseline persistence + config surface | pg adapters exist; no unified migration runner/preflight; scoped 3 waves | clean |  | live | Probe by orchestrator; live infra CI-pending in sandbox - deliver real logic verified vs pg-mem, fail-closed live.
79 | 0079 | TRC-9-A-0079 | 2026-08-23T03:32:00Z | 9 | A | build | 78 | unifies the per-store pg adapters under one migration runner + bootstrap | specialist | substrate-migration+bootstrap | substrate | [verbatim: verbatim/iteration-9-verbatim.md waveA - COMPOSED v1.2] unified migration runner (idempotent, schema_migrations ledger, checksum-guard) + substrate bootstrap (one DATABASE_URL, fail-closed unconfigured); pg adapter/disposition for crossReference+governance. | iteration9_context WaveA; pg adapters; pg-mem | migration runner idempotent + checksum-guarded; bootstrap fail-closed (SubstrateNotConfiguredError); 11 tests; live pg CI-pending | green |  | live | Consolidated per-store pg adapters under one runner+bootstrap; verified vs pg-mem.
80 | 0080 | TRC-9-B-0080 | 2026-08-23T03:33:00Z | 9 | B | build | 78 | makes the E1 seam postures enforceable at startup; readiness/liveness | specialist | deploy-preflight+health | deploy/health | [verbatim: iteration-9-verbatim.md waveB - COMPOSED v1.2] deployment config schema + fail-closed startup preflight (names the unmet required prod seam/env) + readiness (503 not-ready) / liveness routes. | iteration9_context WaveB; seamDispositions; env.ts | preflight fails closed naming unmet seam/key; readiness reflects it; liveness; 22 tests | green |  | live | Startup preflight makes the E1 seam postures enforceable at boot, not just per-call.
81 | 0081 | TRC-9-C-0081 | 2026-08-23T03:34:00Z | 9 | C | build | 78 | adds retention/purge/right-to-delete preserving evidence-ledger immutability | specialist | data-lifecycle+runbook | lifecycle | [verbatim: iteration-9-verbatim.md waveC - COMPOSED v1.2] policy-driven retention/purge over mutable stores + immutability-preserving right-to-delete on the evidence ledger (governed tombstone, never silent row delete) + legal-hold + deployment runbook. | iteration9_context WaveC; evidence ledger; consent/Part2 | retention by policy; right-to-delete preserves ledger immutability; legal-hold blocks purge; runbook; 25 tests | green |  | live | Right-to-delete done correctly: audited tombstone, not a row delete that would break the immutable ledger.
82 | 0082 | TRC-9-D-0082 | 2026-08-23T03:55:00Z | 9 | D | red-team | 79,80,81 | deployment fail-closed-at-startup; deployment/operability red-team lens | convergence+red-team | iter9-convergence+panel | deployment/operability | [verbatim: iteration-9-verbatim.md waveD - COMPOSED v1.2] convergence to DRY + E9 fail-open sweep (deployment: missing prod config fails closed at startup; migrations idempotent+non-destructive; readiness not default-ready; purge preserves immutability + legal hold) + red-team (deployment/operability/data-integrity lens) + register. | wave A/B/C reports; register; framework v1.2 | convergence DRY (preflight consults substrate disposition; single config schema); E9 fixed-2 Unacceptable (preflight phantom-key fail-open; blank-DATABASE_URL fail-open); R1 7/R2 8/R3 6; register Iteration 9 section; orchestrator gate tsc0, 1371 pass +1 expected-fail, size+E1(34) PASS | DRY | R1:7 R2:8 R3:6 E9:fixed2 | live | E9 caught TWO deployment fail-opens (a phantom-key that read as satisfied; a blank DATABASE_URL that would boot serving a mock) - the fail-closed-at-startup class, exactly where a prod misconfig is most dangerous. Live pg/neo4j/external remain CI-pending residuals -> Iteration 10 certification.
83 | 0083 | TRC-10-probe-0083 | 2026-08-23T03:58:00Z | 10 | probe | probe | 82 |  | probe | iter10-probe | harness/certification | Orchestrator inline probe: enumerated the claimed standards + their code/test evidence surface (routes, validators, adapters, seams) to scope the conformance matrix / capability statement / readiness waves. | baseline standards surface + register | standards + evidence surface mapped; scoped 3 waves | clean |  | live | Probe by orchestrator. Capstone iteration: honesty rule (no standard supported on a stub); red-team = overclaim detection.
84 | 0084 | TRC-10-A-0084 | 2026-08-23T04:12:00Z | 10 | A | build | 83 | binds every claimed standard to real evidence or an honest residual | specialist | conformance-matrix | certification/matrix | [verbatim: verbatim/iteration-10-verbatim.md waveA - COMPOSED v1.2] conformance MATRIX as data: standard -> capability -> evidence {codePath, testId, status}; every supported row points to a real test; a stub is ci-pending/partial, never supported. | iteration10_context WaveA; routes/validators/adapters/tests | matrix covers all claimed standards; supported rows point to real tests; counts 17 supported/20 partial/3 ci-pending/2 absent; 17 tests | green |  | live | Honest distribution - only 17 of the claimed capabilities are fully supported+evidenced; the rest are truthfully partial/pending/absent.
85 | 0085 | TRC-10-B-0085 | 2026-08-23T04:13:00Z | 10 | B | build | 83 | derives a FHIR CapabilityStatement from the real implemented surface | specialist | capability-statement | certification/capabilityStatement | [verbatim: iteration-10-verbatim.md waveB - COMPOSED v1.2] FHIR R4 CapabilityStatement generated from the ACTUAL implemented surface (routes, operations, validator profiles, SMART security); must not list an unimplemented resource/operation. | iteration10_context WaveB; api routes; profileValidator | CapabilityStatement from real surface; only-implemented ops; profiles reflect validator; 17 tests | green |  | live | The statement is derived from code, not hand-asserted, so it cannot claim an operation the platform does not serve.
86 | 0086 | TRC-10-C-0086 | 2026-08-23T04:14:00Z | 10 | C | build | 83 | per-standard readiness + residuals; no drift vs the matrix | specialist | certification-readiness | certification/readiness | [verbatim: iteration-10-verbatim.md waveC - COMPOSED v1.2] CERTIFICATION_READINESS.md per-standard status + residuals + path-to-certification + machine-readable summary; a test asserts the summary matches the matrix (no doc-vs-evidence drift). | iteration10_context WaveC; register; seams | readiness doc all 13 standards; nothing marked ready; NS-05 ceiling + per-standard residuals named; summary matches matrix; 22 tests | green |  | live | Certification-READINESS, not an assertion of certification. Doc-vs-evidence drift gated by test.
87 | 0087 | TRC-10-D-0087 | 2026-08-23T04:35:00Z | 10 | D | red-team | 84,85,86 | capstone overclaim detection; final register rollup | convergence+red-team | iter10-convergence+overclaim-panel | certification/overclaim | [verbatim: iteration-10-verbatim.md waveD - COMPOSED v1.2] convergence (matrix single source; readiness comparator wired to real matrix; capability statement subset of matrix) + E9 (no default-supported; readiness not ready for ci-pending) + CAPSTONE red-team OVERCLAIM detection (audit each supported row's test depth) + register FINAL rollup. | wave A/B/C reports; register; framework v1.2 | convergence DRY (matrix single source); E9 clean; R1 demoted 3 OVERCLAIMS (shallow tests behind supported rows); R2 1; R3 11 seams graded 0 faked-green; 4 Unacceptable fixed; register final rollup; orchestrator gate tsc0, 1435 pass +1 expected-fail, size+E1(34) PASS | DRY | R1:3-demoted R2:1 R3:0-faked E9:clean | live | CAPSTONE. The overclaim red-team demoted 3 conformance overclaims (a supported row whose test did not actually exercise the standard's requirement) - the exact 'stub dressed as conformance' failure the whole framework exists to catch, applied to the platform's own certification claims. Build plan I0->I10 reaches an honest, evidenced certification-readiness state.
88 | 0088 | TRC-11-probe-0088 | 2026-08-23T04:40:00Z | 11 | probe | probe | 87 |  | probe | iter11-probe | harness/closeout | Orchestrator inline probe: WpcDomain=17 (3 USCDI gaps: conditions/diagnostic-reports/family-history); open buildable register HIGHs (F5-b, R1-I7-5/6, R1-I6-1/2, R1-8Ai-2). Scoped 4 disjoint waves + framework wave. | baseline domains + register open findings | 3 missing domains + 5 buildable findings + framework enhancement scoped | clean |  | live | Probe by orchestrator. Final buildable closeout; the rest is live-infra/licensing/accreditation, not code.
89 | 0089 | TRC-11-A-0089 | 2026-08-23T05:00:00Z | 11 | A | build | 88 | closes F5-b + claims integrity + CARC member-liability | specialist | f5b-claims-integrity-carc | pipeline/claims/provider | [verbatim: verbatim/iteration-11-verbatim.md waveA - COMPOSED] F5-b resolve claims/care-team/medication provider refs to ProviderIdentity (no invented NPI) + claims golden-thread integrity (orphan ClaimResponse HOLDs, no dangling edge) + CARC X12 group code (CO/PR/OA/PI) via terminology gate. | iteration11_context WaveA; provider resolver; terminology gate | F5-b resolved (raw+flagged when no NPI); orphan claim holds not dangles; CARC group captured; 22 tests | green |  | live | Closes F5-b (HIGH) + R1-I7-5 (HIGH claims integrity) + R1-I7-6 (HIGH CARC member-liability).
90 | 0090 | TRC-11-B-0090 | 2026-08-23T05:01:00Z | 11 | B | build | 88 | completes C9 record model to 20/20 (USCDI problems/diagnostics/family) | specialist | three-new-domains-20of20 | pipeline/conditions/diagnostic/family | [verbatim: iteration-11-verbatim.md waveB - COMPOSED] conditions (Condition problem list, HCC-relevant) + diagnostic-reports (DiagnosticReport incl imaging) + family-history (FamilyMemberHistory) through the template; WpcDomain 17->20; semantic-gated. | iteration11_context WaveB; _TEMPLATE.md | 3 domains registered; record 20/20 (typed union + runtime spec); conditions semantic-gated; 29 tests | green |  | live | Completes the C9 record model to 20/20 with real USCDI data classes (problems, diagnostics, family history), not padding.
91 | 0091 | TRC-11-C-0091 | 2026-08-23T05:02:00Z | 11 | C | build | 88 | closes referral loop-closure + goal status + survivorship tiebreak | specialist | referral-goal-lifecycle-tiebreak | graph/referral/goal/survivorship | [verbatim: iteration-11-verbatim.md waveC - COMPOSED] referral loop-closure (ServiceRequest.status lifecycle + closed-loop signal) + Goal lifecycleStatus/achievementStatus/target + survivorship source-order tiebreak honored. | iteration11_context WaveC; referral/goalTask mappings; survivorship rules | referral loop-closure; goal can be MET; source-order tiebreak honored; 23 tests | green |  | live | Closes R1-I6-1 (referral loop-closure), R1-I6-2 (goal status), R1-8Ai-2 (tiebreak). Care-coordination closed-loop rate now computable.
92 | 0092 | TRC-11-F-0092 | 2026-08-23T05:03:00Z | 11 | F | build | 88 | adds the R5 cross-examiner + E12 claim-vs-evidence gate to the framework | spine | framework-R5-E12-v1.3 | framework | [verbatim: iteration-11-verbatim.md waveF - COMPOSED] add R5 Verification/Cross-Examiner persona + E12 claim-vs-evidence gate to the framework; SKILL.md v1.3; five-persona panel + E12 in the DoD. (Orchestrator finalized into the canonical framework copy.) | iteration11_context WaveF; docs/framework | R5 persona + E12 gate + v1.3; DoD updated; canonical framework repackaged | green |  | live | The framework self-improvement the whole build fed: R5 institutionalizes the owner's instinct that catching load-bearing gaps needs a reviewer whose job is to distrust the green; E12 mechanizes claim-vs-evidence.
93 | 0093 | TRC-11-D-0093 | 2026-08-23T05:25:00Z | 11 | D | red-team | 89,90,91,92 | five-persona closeout incl R5; final buildable completion | convergence+red-team | iter11-convergence+5persona-panel | closeout/cross-examination | [verbatim: iteration-11-verbatim.md waveD - COMPOSED v1.3] convergence + E9 sweep + FIVE-persona red-team incl the NEW R5 cross-examiner on this iteration's own claims + E12 claim-vs-evidence + register FINAL closeout. | wave A/B/C/F reports; register; framework v1.3 | convergence DRY; E9 clean; R1 4/R2 7/R3 6/R4 2; R5 10 upheld / 0 demoted; E12 satisfied; 6 findings CLOSED (F5-b, R1-I7-5, R1-I7-6, R1-I6-1, R1-I6-2, R1-8Ai-2); record 20/20; orchestrator gate tsc0, 1509 pass +1 expected-fail, size+E1(34) PASS | DRY | R1:4 R2:7 R3:6 R4:2 R5:10up/0dem E9:clean E12:ok | live | FINAL BUILDABLE CLOSEOUT. The new R5 cross-examiner re-read all 10 of this iteration's claims against their E12 evidence and upheld each - the standing verification agent doing exactly what it was designed for. All in-sandbox-buildable register findings closed; remaining residuals are live-infra/licensing/accreditation only. Build plan I0->I11 at buildable-completion.
94 | 0094 | TRC-FW1-4-reflect-0094 | 2026-08-23T15:00:00Z | FW1.4 | reflect | fix | 93 | the framework self-improvement the whole build fed - the ToT injection the owner flagged | spine | framework-v1.4-reflection | framework | Owner-requested pause+reflect (chain AND tree of thought) on efficiency/quality/rework/testing/adversarial/personas after the 11-iteration build. Orchestrator-authored v1.4: reasoning-mode doctrine (CoT default, ToT at forks), E13 test-effectiveness gate, E9 shift-left, spine interface-freeze, tighter adversarial loop + N-skeptic, on-demand Performance persona, L10-L12. | whole build's cost centers (fail-open recurrence, cross-wave transients, coordination-gap rework, presence-not-effectiveness testing) | framework docs v1.4 (SKILL/personas/enforcement-kit/operating-model); E13 tooling BUILT + DOGFOODED (check-mutation.mjs killed 6/6 on npi.ts + 8/8 on goldenRecord.ts; check-testlink.mjs passed on the 3 new domains); repackaged skill + agentic-build-framework-v1.4.zip | green |  | live | Tree-of-thought used in the reflection itself (the new-persona decision was branch-evaluate-prune: resist proliferation - net add one on-demand persona, the rest are mandates/gates/doctrines). E13 is dependency-free (no Stryker) and proven against real modules, not prose.

## Roster Index
step_id | trace_id | phase-group | agent_label | what it is / where its output lives
0001 | TRC-P-0-0001 | PLANNING | P1-repo-gate-evidence | phase0_repo_gate.md, evidence.md, use_case_steps.md
0002 | TRC-P-spine-0002 | PLANNING | P2-spine | load-model, adrs, contracts, golden-path, trace-matrix, manifests
0003 | TRC-P-spec-0003 | PLANNING | P3-graph-context-G1 | g1-graph.md
0004 | TRC-P-spec-0004 | PLANNING | P4-pipeline-fhir-G3X2 | g3-pipelines.md
0005 | TRC-P-spec-0005 | PLANNING | P5-agentic-G2G4 | g2g4-agentic.md
0006 | TRC-P-spec-0006 | PLANNING | P6-careplan-G5 | g5-careplan.md
0007 | TRC-P-spec-0007 | PLANNING | P7-documentation-X4 | x4-documentation.md
0008 | TRC-P-use-case-0008 | PLANNING | P8-TCOC-70-use-case-expert | use_case_corpus.md - 70 cases, families A-O
0009 | TRC-P-adversarial-0009 | PLANNING | P9-adversarial-rubric-panel | adversarial-verdict.md - 3 cross-cutting findings (C1 orphan, ADR-006 atomicity, compliance orphans)
0010 | TRC-P-amend-0010 | PLANNING | P10-spine-amendment-REPROMPT | amendment-001.md
0011 | TRC-P-data-0011 | PLANNING | P11-data-extractor-D1 | sheet1-5.json -> D1_Gap_Matrix.xlsx
0012 | TRC-P-data-0012 | PLANNING | P12-spec-author-D4D5 | D4_load_test_spec.md, D5_deployment_config_spec.md
0013 | TRC-P-final-0013 | PLANNING | P13-finalizer | docs/production-plan/D1-D7 committed
0014 | TRC-0-probe-0014 | BUILD I0 | cycle1-probe | tools working
0015 | TRC-0-1A-0015 | BUILD I0 | mechanical-sweeper | 2 logic fixes; 31 files determinism seam; logger; 0 console.log
0016 | TRC-0-1B-0016 | BUILD I0 | route-test-author | 107 route tests, 9 named skips
0017 | TRC-0-1-conv-0017 | BUILD I0 | cycle1-convergence-x2 | determinism stragglers + demoDefaults; DRY on 2nd pass
0018 | TRC-0-1-2-0018 | BUILD I0 | mode-registry | dataMode.ts + session override; consent+fhir wired
0019 | TRC-0-2A-0019 | BUILD I0 | property-test-author | found REAL match bug: blank/whitespace fields -> false matches
0020 | TRC-0-2B-0020 | BUILD I0 | careplan-hardening | 14 modules; frozen files 1269->66 lines; 47 tests; 9 findings
0021 | TRC-0-2-conv-0021 | BUILD I0 | cycle2-convergence | guard non-empty both sides; regression tests
0022 | TRC-0-3A-0022 | BUILD I0 | security-lens | 2 HIGH (consent-read bypass, IDOR); fixed match consent gate
0023 | TRC-0-3B-0023 | BUILD I0 | corpus-scenario | 15 runnable, 55 pending, all 70 accounted
0024 | TRC-0-3C-0024 | BUILD I0 | e2e-a11y-specs | 20 specs; found + fixed a Next illegal-export bug
0025 | TRC-1-probe-0025 | BUILD I1 | iter1-probe | pg-mem ok
0026 | TRC-1-A-0026 | BUILD I1 | pipeline+outbox | 17 modules; outbox intent->confirm->event; 36 tests
0027 | TRC-1-B-0027 | BUILD I1 | persistence+adapters | ledger + immutability trigger; 3 adapters; 31 tests
0028 | TRC-1-C-0028 | BUILD I1 | security+convergence | consent-read fixed; flagged multi-writer outbox gaps for I2
0029 | TRC-2-A-0029 | BUILD I2 | graph-projector+backends | projector + both backends; parity proven; 30 tests
0030 | TRC-2-B1-0030 | BUILD I2 | lens-suite+replay | dual-backend parity on all 5 lenses + replay + merge
0031 | TRC-2-B2-0031 | BUILD I2 | sde-disposition | 5/3/1 shape EMERGES from policy; 26 tests; flagged seam-id collision
0032 | TRC-2-C-0032 | BUILD I2 | iter2-convergence | signalDisposition seam; purity confirmed; DRY
0033 | TRC-3-probe-0033 | BUILD I3 | iter3-probe | workQueueView found
0034 | TRC-3-A-0034 | BUILD I3 | agent-runtime+registry | runtime + manifests; FAKE_FIDELITY.md; 26 tests
0035 | TRC-3-A2-0035 | BUILD I3 | idor-role-model | principal model; 2 IDOR it.fails flipped; 24 tests
0036 | TRC-3-B-0036 | BUILD I3 | three-agents | decide->act->HITL->execute loop reproduced; PA guardrail asserted; 18 tests
0037 | TRC-3-C-0037 | BUILD I3 | iter3-convergence | found F-C1 namespace drift across 3 surfaces; pinned by test; DRY
0038 | TRC-4-A-0038 | BUILD I4 | template+medications | _TEMPLATE.md + medications T1; pinning test; 14 tests
0039 | TRC-4-EMPI-0039 | BUILD I4 | empi-resolver | EMPI resolver; HELD path; 14 tests
0040 | TRC-4-B-0040 | BUILD I4 | labs+allergies | 2 domains T1; 26 tests
0041 | TRC-4-EXT-0041 | BUILD I4 | external-seams | external identity + terminology seams; stage-4 semantic gate; 28 tests
0042 | TRC-4-C-0042 | BUILD I4 | procedures | procedures T1; 14 tests; record 7/20
0043 | TRC-4-VSM-0043 | BUILD I4 | value-set-registry | registry facility; 26 assets/6 families; 16 tests
0044 | TRC-4-C-conv-0044 | BUILD I4 | iter4-convergence | 1 doc-only finding; DRY; record 7/20
0045 | TRC-V-panel-0045 | VERIFY | domain-fidelity-adversary | 26 findings (4 Critical incl 834-term, Part2, EMPI survivorship, $validate stub)
0046 | TRC-V-panel-0046 | VERIFY | negative-space-adversary | 31 findings (dead-letter drop, right-to-delete, observability, idempotency)
0047 | TRC-V-panel-0047 | VERIFY | stub-legitimacy-adversary | 26 graded; 4 Unacceptable (dev-auth fail-open, validator fail-open, EMPI mock-in-prod, evidence dead-wiring)
0048 | TRC-V-fix-0048 | VERIFY | unacceptable-fixes | U1-U4 fixed fail-closed; 22 tests
0049 | TRC-V-gate-0049 | VERIFY | governance-seam-gate | 17 seams declared; 29 governance tests; new seam with no disposition fails CI
0050 | TRC-5-probe-0050 | BUILD I5 | iter5-probe | heldIdentity.ts found
0051 | TRC-5-A-0051 | BUILD I5 | dead-letter-subsystem | store + ops routes; producers persist; 44 tests; seam declared
0052 | TRC-5-B-0052 | BUILD I5 | idempotency+session-secret | idempotency store; SDE+agents dedupe on republish; secret fails closed; 29 tests
0053 | TRC-5-C-0053 | BUILD I5 | iter5-convergence+panel | found+fixed a re-introduced fail-open drop-path; R1 5/R2 10/R3 3 findings; DRY
0054 | TRC-6-probe-0054 | BUILD I6 | iter6-probe | 8 domains found (care-team already a graph node)
0055 | TRC-6-A-0055 | BUILD I6 | careteam+goalstasks | 2 domains T1; lens preserved; 28 tests; namespace split to companion file
0056 | TRC-6-B-0056 | BUILD I6 | referrals+immunizations | 2 domains T1; provider deferred-I8A; 27 tests
0057 | TRC-6-C-0057 | BUILD I6 | iter6-foldins+panel | both fold-ins fixed; found+fixed latent 834 fail-open; R1 5/R2 7/R3 3; DRY; record 11/20
0058 | TRC-7-probe-0058 | BUILD I7 | iter7-probe | Part2 thin; paMachine found
0059 | TRC-7-A-0059 | BUILD I7 | behavioralHealth+part2 | BH T1; SUD restricted; break-glass audited; 21 tests
0060 | TRC-7-B-0060 | BUILD I7 | claims+paLifecycle | 2 domains T1; PA capture non-authoritative asserted; 34 tests
0061 | TRC-7-C-0061 | BUILD I7 | assessments+caregiver+documents | 3 domains; documents honestly T2; 39 tests
0062 | TRC-7-D-0062 | BUILD I7 | iter7-convergence+panel | E9 found+fixed 2 Unacceptable Part2 fail-opens; R1 8/R2 9/R3 findings; F2 advanced; DRY; record 17/20
0063 | TRC-8A-i-probe-0063 | BUILD I8A-i | iter8ai-probe | pgmem ok; external stubs found; deferred-I8A refs present
0064 | TRC-8A-i-A-0064 | BUILD I8A-i | survivorship+crossReference | xref+survivorship built; two feeds->one member; golden-record projection; seam declared; tests green
0065 | TRC-8A-i-B-0065 | BUILD I8A-i | external-empi-real | PIX/PDQ + PIXm/PDQm real logic; fail-closed w/o MPI; HELD on low-confidence; tests green
0066 | TRC-8A-i-C-0066 | BUILD I8A-i | provider-identity-npi | NPI validation; provider resolves to node; fail-closed w/o NPPES; deferred refs resolved; tests green
0067 | TRC-8A-i-D-0067 | BUILD I8A-i | iter8ai-convergence+panel | convergence DRY (dataMode/seamDispositions reconciled, identity/index barrel completed); E9 fixed-1 Unacceptable (PDQ/PDQm fabricated enterprise anchor via ?? ids[0] -> empty-anchor HELD, +2 regression tests); R1 4 (1 Unacceptable-fixed, 2 MED, 1 LOW); R2 7-item missing-list; R3 3 Acceptable/0 open; F3 CLOSED; F5 CLOSED; orchestrator gate: tsc0, 1198 pass +1 expected-fail, size+E1(33) PASS
0068 | TRC-8A-ii-probe-0068 | BUILD I8A-ii | iter8aii-probe | seed allowlist + fail-closed prod stub confirmed; scoped 3 disjoint waves
0069 | TRC-8A-ii-A-0069 | BUILD I8A-ii | terminology-validate+expand | validateCode real; $expand; retired-code rejected with version; UCUM; 29 tests; prod fail-closed
0070 | TRC-8A-ii-B-0070 | BUILD I8A-ii | terminology-translate+classify | translate real w/ asset+version; no fabricated maps; HCC classify data-driven; risk families enumerated; 16 tests; live crosswalk fail-closed
0071 | TRC-8A-ii-C-0071 | BUILD I8A-ii | terminology-pipeline-binding+currency | pipeline binding quarantines bad code; currency enforced on stale versions; reuse-not-duplicate; 24 tests
0072 | TRC-8A-ii-D-0072 | BUILD I8A-ii | iter8aii-convergence+panel | convergence DRY (consolidated a drifted duplicate ICD-10->HCC map); E9 clean (8 shapes justified); R1 7/R2 8/R3 6 all Acceptable (1 Risky fixed); register 8A-ii section; orchestrator gate tsc0, 1267 pass +1 expected-fail, size+E1(33) PASS
0073 | TRC-8A-iii-probe-0073 | BUILD I8A-iii | iter8aiii-probe | reuse surfaces confirmed; namespace pre-allocated
0074 | TRC-8A-iii-A-0074 | BUILD I8A-iii | governance-backend-lifecycle | lifecycle guarded; maker-checker enforced (MakerCheckerViolationError); single-approver configurable; immutable audit + history; chosen-version replay (no fallback); one-active invariant; 19 tests; seam-gate 27
0075 | TRC-8A-iii-B-0075 | BUILD I8A-iii | governance-console-ui | console renders; gates by role/mode; maker-checker approve disabled for maker; replay panel; dual-mode; 5 render tests (new React test infra scoped in-partition)
0076 | TRC-8A-iii-C-0076 | BUILD I8A-iii | governance-bff-routes | routes role-gated; maker-checker at boundary (403 self-approve); call-not-duplicate; PHI-safe; 20 route tests
0077 | TRC-8A-iii-D-0077 | BUILD I8A-iii | iter8aiii-convergence+panel | convergence DRY (single makerChecker.ts predicate; adapter collapsed to real delegation); E9 fixed-1 Unacceptable (resolveGovernanceBackend bound ?? integrationDouble served in-memory as production - now fails closed); R1 4/R2 7/R3 3; register 8A-iii section; I8A CLOSED; orchestrator gate tsc0, 1314 pass +1 expected-fail, size+E1(34) PASS
0078 | TRC-9-probe-0078 | BUILD I9 | iter9-probe | pg adapters exist; no unified migration runner/preflight; scoped 3 waves
0079 | TRC-9-A-0079 | BUILD I9 | substrate-migration+bootstrap | migration runner idempotent + checksum-guarded; bootstrap fail-closed (SubstrateNotConfiguredError); 11 tests; live pg CI-pending
0080 | TRC-9-B-0080 | BUILD I9 | deploy-preflight+health | preflight fails closed naming unmet seam/key; readiness reflects it; liveness; 22 tests
0081 | TRC-9-C-0081 | BUILD I9 | data-lifecycle+runbook | retention by policy; right-to-delete preserves ledger immutability; legal-hold blocks purge; runbook; 25 tests
0082 | TRC-9-D-0082 | BUILD I9 | iter9-convergence+panel | convergence DRY (preflight consults substrate disposition; single config schema); E9 fixed-2 Unacceptable (preflight phantom-key fail-open; blank-DATABASE_URL fail-open); R1 7/R2 8/R3 6; register Iteration 9 section; orchestrator gate tsc0, 1371 pass +1 expected-fail, size+E1(34) PASS
0083 | TRC-10-probe-0083 | BUILD I10 | iter10-probe | standards + evidence surface mapped; scoped 3 waves
0084 | TRC-10-A-0084 | BUILD I10 | conformance-matrix | matrix covers all claimed standards; supported rows point to real tests; counts 17 supported/20 partial/3 ci-pending/2 absent; 17 tests
0085 | TRC-10-B-0085 | BUILD I10 | capability-statement | CapabilityStatement from real surface; only-implemented ops; profiles reflect validator; 17 tests
0086 | TRC-10-C-0086 | BUILD I10 | certification-readiness | readiness doc all 13 standards; nothing marked ready; NS-05 ceiling + per-standard residuals named; summary matches matrix; 22 tests
0087 | TRC-10-D-0087 | BUILD I10 | iter10-convergence+overclaim-panel | convergence DRY (matrix single source); E9 clean; R1 demoted 3 OVERCLAIMS (shallow tests behind supported rows); R2 1; R3 11 seams graded 0 faked-green; 4 Unacceptable fixed; register final rollup; orchestrator gate tsc0, 1435 pass +1 expected-fail, size+E1(34) PASS
0088 | TRC-11-probe-0088 | BUILD I11 | iter11-probe | 3 missing domains + 5 buildable findings + framework enhancement scoped
0089 | TRC-11-A-0089 | BUILD I11 | f5b-claims-integrity-carc | F5-b resolved (raw+flagged when no NPI); orphan claim holds not dangles; CARC group captured; 22 tests
0090 | TRC-11-B-0090 | BUILD I11 | three-new-domains-20of20 | 3 domains registered; record 20/20 (typed union + runtime spec); conditions semantic-gated; 29 tests
0091 | TRC-11-C-0091 | BUILD I11 | referral-goal-lifecycle-tiebreak | referral loop-closure; goal can be MET; source-order tiebreak honored; 23 tests
0092 | TRC-11-F-0092 | BUILD I11 | framework-R5-E12-v1.3 | R5 persona + E12 gate + v1.3; DoD updated; canonical framework repackaged
0093 | TRC-11-D-0093 | BUILD I11 | iter11-convergence+5persona-panel | convergence DRY; E9 clean; R1 4/R2 7/R3 6/R4 2; R5 10 upheld / 0 demoted; E12 satisfied; 6 findings CLOSED (F5-b, R1-I7-5, R1-I7-6, R1-I6-1, R1-I6-2, R1-8Ai-2); record 20/20; orchestrator gate tsc0, 1509 pass +1 expected-fail, size+E1(34) PASS
0094 | TRC-FW1-4-reflect-0094 | BUILD IFW1.4 | framework-v1.4-reflection | framework docs v1.4 (SKILL/personas/enforcement-kit/operating-model); E13 tooling BUILT + DOGFOODED (check-mutation.mjs killed 6/6 on npi.ts + 8/8 on goldenRecord.ts; check-testlink.mjs passed on the 3 new domains); repackaged skill + agentic-build-framework-v1.4.zip