## Gap Matrix
D1 Gap Matrix: current state to target architecture per area (amendment-001 ownership applied)
ACE Production Gap Assessment. Governing plan v11, gates A-L approved 2026-08-21. Source: coalition run (spine, five specialists, adversarial verdict, amendment-001).
Area | Item | Current State | Code Evidence | Target Architecture | Build Approach Reuse | Contracts Touched | Scale Posture | Portability Posture | Dependencies | Effort Sml Assumptions | Risks | Acceptance Tests | Docs Done | Owner | Status
G1 | Knowledge graph, population, query layer | Tier B presentational. 804-line hardcoded dataset: 52 nodes, 67 edges, five Cypher lens filters rendered as UI labels; no graph store, no Cypher execution. Node data mixes semantics with presentation. File frozen in the quality baseline. | src/lib/wholePersonGraphData.ts:1-805 (nodes 85-446, edges 449-624, lensDefinitions 637-735, activeSignals 752-804); evidence.md Tier B list. | TARGET. Postgres property-graph projection per ADR-001: member-partitioned graph_nodes/graph_edges with dated validity, Part 2 restricted columns; projector consumes C10 events; typed lens queries (depth<=3 recursive CTE) behind SEAM: graph-store; rebuild and merge/unmerge rekey by replay. Per amendment-001 §1, G1 also owns the person-context projector and endpoint, O-6 provider-context endpoint, metrics projector. | Reuse consent-module seam shape (C3), authz guard, anchored memberIds from match engine, BackboneNotConfiguredError. Order: B1 mock extraction to data/graph JSON plus GraphStore seam; B2 Postgres store plus lens engine; B3 projector core; B4 mapping modules P1 then P2; B5 rebuild/rekey plus proof; B6 C1 endpoints; B7 view-model registry. | C1 (lens plus person-context serving), C2, C3 (SEAM: graph-store), C5 dual-mode, C6, C7, C8, C9.4 graph MVR, C10 mapping specs and rebuild. | Stream <300 ev/min state peak; batch windows ~28K/min with permitted lag, alarmed 1h catch-up. Partition key memberId; eventId dedupe; idempotent upserts. Lens query <=2s p95 and view-model read <=1s p95 CONFIRMED; 8 consumers state for partition parallelism. | Postgres wire plus Kafka API only (subset of C7 five). No graph database; Neo4j-class contingency stays an adapter behind SEAM: graph-store, rebuilt from replay. | ADR-002 backbone; ADR-006 outbox as per-member replay source (ratified amendment-001 §3); G3 stage-5 events; C9 P2 domains for graph MVR; DP-7 merge events (G3 stage 3); gap-derivation projector (G2, F1) for CareGap nodes. | E1 M, E2 M, E3 L (~19 mapping modules; C10 payload stability ASSUMPTION), E4 M, E5 M, E6 S, E7 M. Amendment adds: C1 implementation layer, keystone ranking, hypothesis-edge lifecycle, around-event and household query additions. | R1 upstream event starvation if G3 slips; R2 F1 ownership open (CareGap events); R3 merge-rekey correctness; R4 ontology drift toward the demo instance; R5 Part 2 presence-stub interpretation (SP-3, compliance); R6 view-model discipline erosion; R7 lens latency at outlier subgraphs. | lens.acceptance (five lenses plus declared additions, mock AND real), graphStore.contract, projector.idempotency, per-domain mapping tests, rebuild.proof checksum equality, rekey.merge, part2.restriction, route.lens BFF 401/403/400/422/200, viewmodels.contract screen-vs-report divergence, C5 dual-mode plus axe-core. | docs/graph/mapping-specs.md generated from mapping modules; graph and viewmodels READMEs; projector-rebuild runbook (T2); Part 2 handling section in compliance posture; operator-guide graph entry; traceability rows per capability. | Graph & Context Architect | ACTIVE; P1 code behind seam, real at P2
G2 | Signal Disposition Engine (first real agent) | Tier B presentational. 918-line page with hardcoded results (5 approved, 3 suppressed, 1 delayed, single coordinated touchpoint); no engine, no stream, no policy store. Page frozen in the baseline; retired by extraction only. | src/app/signal-disposition-engine/page.tsx (918 lines); evidence.md Tier B. | TARGET. Stream-lane disposition service: signal taxonomy as data; per-member fold deciding act/suppress/delay/bundle; policy packs as versioned data behind SEAM: sde-policy-store; every decision explainable (policy ids) and audited to the ADR-005 ledger; memberId ordering per C6. Canonical intake topology per amendment-001 adjudication (e): intake consumes domain-events, publishes signal.raised, folds from its own projection. Demo screen seamed with mock mode retained. | Reuse consent seam pattern for three new seams, authz guard, ADR-005 evidence store, ADR-006 internal-writer outbox. Order: engine plus taxonomy plus policy packs offline first (mock mode), then intake plus pending-signal projection on the backbone. | C2 envelope on all emitted events, C6 consumer groups and DLQ, C10 (signal.raised, disposition.decided, touchpoint.executed), C1 context reads, C3 seams (sde-policy-store, sde-signal-store), C5 dual-mode, C9.4 SDE MVR as honesty bound, ADR-005. | Signals topic 6/48 partitions pilot/state; <300 ev/min stream peak gives two orders margin; signal-to-disposition <=5s p95 CONFIRMED; idempotent intake (eventId plus taxonomy dedupe key); fold idempotencyKey per window; lag delays but never corrupts (per-member fold). | Kafka API, Postgres wire, OIDC, container runtime; subset of C7 five. No vendor SDK types in core. | ADR-002 backbone; C9.4 SDE MVR (1@T1, 3@T1 stream, 5-dispense@T1, 12@T1, 13@T1, 15@T1); gap-derivation projector (sub-row); O-1 evidence store; G3 feeds for signal sources. | E1 SDE engine plus screen M (backbone ASSUMPTION for intake); E4 intake plus projection S. Coordination-window default daily is ASSUMPTION (spike S2); workforce capacity as config until S4. | Policy-pack misconfiguration silently suppressing outreach (attributed publish, suppression-rate alarms, last-valid fallback); consent revocation racing in-flight touchpoints (immediate fold plus act-time recheck); second-inbox drift (DP-3 axis); escalation-hierarchy gap at P1 (amendment adjudication a). | dispositionEngine.fold (golden-path batch, exact policy ids), dispositionEngine.property (caps never exceeded, every suppress carries reason plus policyId, deterministic fold), taxonomy.schema refuse-loudly, policyStore and pendingSignalStore contract tests, projection.rebuild, BFF route matrix, C5 dual-mode acceptance-shape regions. | sde README (fold semantics, pack format); disposition-policy reference generated from policy data; DLQ replay and policy-publish runbooks; compliance explainability note (fold reconstructed from ledger); operator-guide Q2 update. | Agentic Systems Designer | ACTIVE; engine mock-mode first, real at P2
G3 | FHIR WPC ingestion pipelines | CURRENT: zero pipeline-fed coverage. Seed script (tools/seed/load-maria.mjs) is the only populator; seeded record is 20 resources / 15 types, PA-shaped. WPC screens render from hardcoded TS, not from FHIR. | evidence.md WPC baseline; mockData.data.patients.ts, patientRegistry.data1-3.ts, fhirCareTeamData.ts, patientContext.*; tools/seed/ (load-maria.mjs 43 lines, maria.bundle.json 416, parse_policies.py 302, gen_network_adequacy_seed.py 134). | TARGET. §4A five-stage pipeline (land, stage+validate, transform+enrich, conform+load, project+propagate) per source: 834, 837/835, pharmacy, provider directory, CCD/QE, ADT, screening, referral webhooks, CBO flat file/HMIS, Part 2 SUD lane. One transform codebase, batch and stream harnesses. Outbox relay per ADR-006 as amended (intent pattern, amendment-001 §2). Amendment adds: egress-scrubbing library, record-repair DAG (UC-03), UC-43 discrepancy gate, claim-identity dedupe, 834 dependent linkage. | Wrap matchEngine.ts unchanged in a matchService (blocking keys, thresholds, work items); consent module as C3 template for every store; goldenThread work queue for unmatched-identity and quarantine items; parse_policies.py normalization pattern; HAPI Docker plus Newman extended. Order: O-1 swap, outbox plus relay, pipeline core, P1 adapters, validation harness, P2 adapters, P3 adapters, rolling screen seam swaps. | C9 scope boundary and tier stamping; C2 envelope emission; C10 event catalog plus rebuild contract test; C6 partitioning, DLQ, traffic classes; C3 (SEAM: evidence-store, per-feed source seams); C4 $validate gate; C5 seams registry; C7; ADR-003 dag-orchestrator seam; ADR-006 cdc-relay seam. | 834 full 7M records in 4h = 486 rec/s across 16 loader workers; claims 234 rec/s; ADT 200/min peak, 60s end-to-end; batch-class ~470 ev/s exempt with 1h catch-up. Idempotency keys per step plus claim-identity dedupe; DLQ mirrored keying; halt thresholds stop DAGs. $validate throughput is the one named threat (SP-2, spine escalation). | Strict subset of C7 five: Postgres wire, Kafka API, S3-compatible object store, OIDC, OCI. Airflow via orchestrator-neutral step contract; SFTP, geocoding, terminology licensing at IaC layer; HAPI via FHIR REST only. | ADR-002 backbone (Redpanda compose), ADR-005 ledger (O-1, built here), ADR-006 outbox, C9, C2/C6/C10, DP-7, C4, X1 substrate, X3 IaC for SFTP/object-store provisioning. | O-1 S; outbox M; pipeline core L; 834 L; 837/835 L; pharmacy M (SP-3); provider directory O-2 M; validation harness M (SP-2); CCD/QE L; ADT M; screening plus webhook M; segmentation labeler M; match service M; flat-file P3 L; screen swaps M total. | External feed access timing gates dates (fixture-complete adapters, GB blockers named); $validate vs 4h window; terminology licensing; identity false merges (DP-7 exactly, SP-7); flat-file quality floods quarantine; batch-window projector lag; Part 2 rule-set gaps; 834 diff-load audit expectations (R8, owner decision per amendment adjudication b). | Reconciliation equality property (in = loaded + rejected), lane-equivalence property, idempotency property, envelope property vs C2 schema, survivorship property, evidenceStore.contract (first C3 proof), backbone.contract, rebuildFromReplay.contract, usCore $validate conformance suite, C5 dual-mode toggle-OFF renders per swapped screen, D4 k6 window gates. | Pipeline architecture doc; per-adapter READMEs and design notes with C9 yield and thresholds; batch DAG ops, DLQ replay, quarantine remediation runbooks; reconciliation threshold reference generated from thresholds.json; per-load audit evidence description; traceability rows. | Pipeline + FHIR Engineering & Validation pair | ACTIVE; foundation, goes first (O-1/O-2 order)
G4 | Agentic orchestration runtime + agent library foundation | Absent. Agent coalition is demo scenario data only; no runtime exists. | evidence.md Tier B (agent coalition / orchestration: no runtime, demo scenario data only). Reuse foundation verified Tier A: goldenThread orchestrator, paMachine.ts (96 lines, pure transitions, human-gated submit/close-gap), workQueue.ts (113 lines, five queues, CMS SLA clocks). | TARGET. Minimal runtime on self-hosted Temporal (ADR-002): manifest registry (versioned data, conventions §10), journey-engine seam, least-privilege tool broker, HITL gate reusing the goldenThread work queue (two additive queue names, no second inbox), escalation engine with DP-3 defaults as role-rank config data (amendment adjudication a). Three named agents HITL-first: outreach, referral coordination, PA/documentation (O-8). | Reuse paMachine.transition, slaHours, requiresHumanApproval verbatim; goldenThread public surface (runFinancialClearance, routeToQueue, workItemFromEvidence, DTR generators); evidence store (O-1). Order: runtime foundation, PA agent first (no external vendor), outreach agent (channel spike S3), referral agent (P2 referral events). | C1 (tool broker context reads, O-6 re-routing), C2/C6/C10 (agent events via outbox), C3 seams (journey-engine, comms-channel), C5 dual-mode inbox, C9.4 agents MVR (11, 12, 15, 17@T1), ADR-005 proposals as evidence. | Journey lane tracks open journeys, not events: ASSUMPTION 2% active = 1K pilot / 140K state open workflows, inside a small self-hosted Temporal cluster; two workers pilot, four state. Tool-broker mutations carry idempotency keys so Temporal retries are safe. | Kafka API, Postgres wire, OIDC, container runtime. Temporal self-hosted per ADR-002 (never Step Functions / Durable Functions); channel vendors behind comms-channel adapter at the IaC edge. | ADR-002 Temporal; SDE dispositions (G2); referral events 12@T1 (G3, P2); pa.* events via PA-lifecycle persistence (G3 outbox library precedes agentic E5 per amendment §2); care team 10@T1 for escalation chains (P2); consent 15@T1. | E3 runtime foundation M (additive QueueName accepted; Temporal dev-compose from X1); E5 PA agent M (pa.* events dependency); E6 outreach agent M (one channel adapter; narration flag OFF); E7 referral agent S. | Escalation chains need hierarchy no C9 tier carries; resolved as role-rank config over membership, degraded P1 posture ratified (amendment a). paMachine invariant erosion (property test: no path reaches Submitted/GapClosed without attributed human decision); Temporal ops burden (S1, runbook gated); LLM narration determinism/PHI (flagged OFF, evals). | paJourney.transitions (legal transitions only, gates blocked without approvedBy), toolBroker.property (no invocation outside allowlist, autonomy never exceeded), escalationEngine (SLA tiers, chain walk, park-with-audit), journeyFacade and commsChannel contract tests, journeyReplay determinism, outreach evals with injection and PHI fixtures. | agents README plus manifest schema doc generated from zod; T9 agent pages generated from manifests; journey-workflow-ops runbook; eval-suite documentation per prompt; operator-guide Q3 update. | Agentic Systems Designer | ACTIVE; P2 first agents, P3 coalition breadth
G5 | Intelligent care plan hardening + clinical rigor | CURRENT. Real 1,262-line generator across five modules; two entry points; ZERO tests; keyword-string clinical logic; nondeterministic (inline Date.now); side-effecting (mutates referralStore during generation); PHI in console logs; hardcoded member-name literal in referral ids; no FHIR output; no contraindication input; no BFF route; consent-blind sharing; all five files baseline-frozen. | src/lib/services/carePlanGenerator.ts:39-111, :66 (PHI log), :107-110 (silent fallback); helpers.ts:143 (ref-margaret- literal), :173 (referralStore mutation); goals.ts:98-169; holistic.ts:120-129 (demo-journey keywords); types.ts:1 (mockData import). Line counts: 255/327/347/272/61. | TARGET. New src/lib/carePlan/ split builder/validator/templates per the debt register; pure deterministic planEngine.evaluate(context, deps); context via C1 (tier-labeled, consent-scoped); FHIR CarePlan/Goal/Task/ServiceRequest output per C4; persistence via ADR-006 internal-writer outbox in the BFF route transaction (amendment adjudication f; §1 stage-4 wording superseded); clinician review in the goldenThread work queue; DP-4 oracle as regression floor; legacy files retire as delegates, baseline shrinks by five. | Reuse goldenThread work queue (routeToQueue, isSlaBreached), policy corpus and NormalizedPolicy (O-7 home), consent seam exemplar, authz guard, FHIR validation utilities, ADR-005 store, ADR-006 outbox library (G3 build step 2 precedes E3). Order: E1 core extraction, E2 oracle, E3 routes plus review, E4 progress projector, E5 contraindication gate, E6 O-7 content, E7 legacy retirement. | C1 (contextAdapter, purpose care-coordination), C2, C4 (fhir mappers plus $validate), C9.4 care-plan MVR incl 9@>=T2 allergy honesty flag, C10 (care-plan.*, goal.*, task.* events; progress projector), C3 (SEAM: care-plan-store), C5, C8. | Generation clinician-initiated, request-scoped: ASSUMPTION <=10/min state peak. Progress projector consumes stream-class events (<300/min); memberId partition; eventId dedupe; idempotencyKey on route mutations; rebuild from replay plus ledger; internal evaluate() target <=500ms p95 labeled ASSUMPTION, not a spine budget. | Kafka API plus Postgres wire only; FHIR record via doctrine-6 store seam; O-7 extraction tooling as OCI containers in the batch lane. | C1 person-context (mock mode until it lands), C9.4 MVR tiers, C10 gap events (G2, F1), ADR-002 backbone for projector, ADR-005 ledger, ADR-006 outbox library (sequenced first per amendment §2), goldenThread work-queue surface, C5 dual-mode. | E1 M (legacy semantics port as data rules); E2 M (seven fixture archetypes suffice); E3 M (C1 availability sequencing); E4 S; E5 M (SP1 bounds rule set); E6 M (documents stable, semi-automated extraction); E7 S (SP4 de-risks UI coupling). | Contraindication over-trust before 9@T1 (flag made structural); O-7 content escaping smeReviewed gate; clinical/financial re-entanglement; legacy UI coupling surprises (unstaged app tree); scope creep into measure evaluation (F1 boundary); fixture sign-off bottleneck; C1 sequencing. | invariants.property P1..P6 (goal has intervention; no contraindicated intervention or limitation flag; citations resolve; barriers addressed or deferred; determinism; schema/profile parse), goldenFixtures (journey-diverse, medical-lens signed), fhirMapping plus fhirConformance $validate, planStore.contract, carePlanRoutes BFF matrix, progressProjector rebuild and Part 2 envelope drop, criteriaContent smeReviewed gate, C5 dual-mode plus axe. | carePlan README; API reference from zod schemas; clinical rigor statement (scope boundary exactly as shipped); O-7 provenance catalog; progress-projector runbook section; honest-answer FAQ entries; traceability rows. | Care Plan pair (Medical Expert lens + engineering lens) | ACTIVE; P2
G7 | Network adequacy completion + cross-domain integration | Adequacy engine is Tier A (time/distance, ratios, wait-time, gaps, augmentation, analyst copilot) running on deterministic seed data. Dashboards compute per-screen inline numbers; providernet_analytics views live in a standalone Vite app; no integration with referrals or PA. | evidence.md Tier A adequacy line; Tier B dashboards line; tools/seed/gen_network_adequacy_seed.py; phase0 item 4 (providernet_analytics standalone app; port views, not the app). | TARGET. O-3 four dashboards, O-4 county choropleth, O-5 compliance report all read named versioned view-models materialized by the metrics projector (G1 build per amendment-001 §1); report generates from the same view-models as screens (DP-6). O-6 shared provider model NPI-anchored per DP-7; C1 provider-context endpoint (G1-served) joins gaps to referral candidates to PA posture. Thresholds are configurable data. Language-concordance ranking is G7 adequacy logic delivered as a shared view-model. | Reuse the Tier-A adequacy engine unchanged; provider-directory loader (G3 O-2) feeds it; port providernet_analytics view definitions onto shared view-models inside tcoc; copilot focusCounties drives parameterized reads of the same view-models. | C1 provider-context extension (O-6), C9.4 adequacy MVR (2@T1, 10@T1, 12@T1), DP-6 thresholds as data, C8 (O-5 feeds compliance audience). | Dashboard view-model read <=1s p95 CONFIRMED (precomputed keyed reads); provider-context read within the C1 300ms budget; no inline aggregation anywhere (G6 lesson). | Postgres wire plus Kafka API via the shared projector substrate; geocoding data licensed at the IaC layer, core sees coordinates as data. | O-2 provider-directory, gold-card, denial-rate loaders (G3); metrics projector plus serving (G1, amendment §1); coverage 2@T1 (P1) and referrals 12@T1 (P2); DP-7 provider identity. | G1 E7 view-model registry M (providernet aggregate definitions recoverable from adequacy outputs, ASSUMPTION); feed epics inside G3 O-2 M; O-5 report rides the view-model contract. | View-model discipline erosion recreating inline math (boundaries lint, divergence test); GB-6 live adequacy data blocked (seed spread regression guards until then); split ownership seams (amendment boundary rules: neither side reimplements the other). | viewmodels.contract; O-5 report vs O-3 screen consistency test (one source of truth); threshold config change alters results without deploy (UC-32 shape); language-concordance fixture (UC-36); drill-down from view-models only, axe-core per O-9; adequacy seed-spread regression guard (D4). | View-model registry README; O-5 report described in audit-evidence catalog (T7 pattern); operator-guide adequacy entries; traceability rows. | Graph & Context Architect (view-models, serving) + Pipeline pair (feeds); G7 adequacy logic per DP-6 | ACTIVE; P2 experience layer over Tier-A engine
G6 | Shared metric engine for dashboards (parked) | Parked, recorded, not worked. Dashboards today compute per-screen inline numbers (Tier B). | evidence.md: dashboards, per-screen inline numbers. | Not designed in this run. Its lesson is applied anyway: G7 dashboards consume shared view-models materialized by the metrics projector; no per-screen math. F1 gap derivation was assigned into G2 scope rather than unparking G6; F3 QARR-class reporting parked alongside with the O-5 generated-from-view-models pattern named as the eventual template. | None this run. The view-model registry (G1) plus metrics projector are the substrate any future G6 unparking would extend. | None directly; the G6 lesson is encoded in DP-6 and the view-model contract. | n/a (parked). | n/a (parked). | Owner decision on F1 escalation (G2 scope growth vs unparking a G6 slice) remains open per amendment-001 §5; F3/UC-46 parked adjacent. | None allocated. | Measure-evaluation scope creeping into SDE or care plan without an owner (role-separation boundaries stated in G2 and G5 designs); QARR exposure bounded by the binding interim egress-scrubbing rule (amendment §4). | None (parked). The gap-derivation not-certified boundary test lives in G2 scope. | Parked status recorded in the honesty ledger and roadmap; F1/F3 dispositions surfaced to owner in the deliverable package. | Unassigned (parked); owner escalation open | PARKED
X1 | Execution substrate (three lanes) | Absent by design. start runs next dev; in-process Map stores; no queue/cache/worker deps; file-based state (fhir-state.json); backend/ holds logs only. Engines are pure stateless functions, ideal for scale-out. | evidence.md substrate paragraph; phase0 item 5 (no queue, worker, cache, or IaC assets in any repo). | TARGET per ADR-002: Kafka-API backbone from day one (Redpanda self-hosted reference; MSK / Event Hubs Kafka mode as IaC swaps) behind SEAM: event-backbone; Temporal self-hosted, Postgres-persisted, for the journey lane behind a workflow facade; batch lane per ADR-003. Load model governs sizing: partitions 12/96 pilot/state on domain-events; loader worker floors; HAPI clustered posture with CQRS reads. | Greenfield behind seams; dev runs backbone via docker compose alongside the existing HAPI container; in-memory Map stores retire in the ADR-005 seam-swap order (evidence store first). | C6 (backbone contract), C7 (five protocols), C2 traffic classes, ADR-002/003/005. | Stream <300 ev/min state peak vs gates 1K/5K/10K per min (>3x margin); batch-class ~470 ev/s windows; 96 partitions x 2K msg/min = 192K/min mechanical headroom; 140K open journeys inside a small Temporal cluster; DP-5 budgets all CONFIRMED by the load model. | Doctrine 5: core depends only on Postgres wire, Kafka API, S3-compatible object storage, OIDC, OCI. Durable workflow engine self-hostable (Temporal-class); never Step Functions / Durable Functions in core. | ADR-004 IaC provisioning; D4 load-test spec (k6 gates); DLQ and replay runbooks (D7 build-gated). | Spine-decided; built incrementally under G3 (backbone, outbox) and G4 (Temporal) epics. Per-partition throughput 2K msg/min and utilization factors labeled ASSUMPTION, replaced with measured feed statistics at O-2. | One more platform component (Redpanda) to operate from phase 1, accepted for replayability; Temporal operational burden on a team that has never run it (S1 spike, gated runbooks). | backbone.contract (publish/subscribe/replay vs in-memory and Redpanda); D4 k6 gates (1K sustained / 5K burst / 10K headroom); UC-59 surge scenario; journey replay determinism tests. | Observability guide (SLOs from load-model budgets); backpressure-response and hapi-cluster-ops runbooks (build-gated); DLQ replay runbook. | Spine (Performance & Scalability + Platform & Portability Engineers); built via G3/G4 epics | ACTIVE; P1 foundation
X2 | Pipeline DAG layer (Airflow-compatible) | Absent. No queue, worker, cache, or orchestrator assets anywhere (phase0 item 5). | evidence.md substrate paragraph; phase0_repo_gate.md item 5. | TARGET per ADR-003: steps-as-containers; DAG definitions live in the repo as data (pipelines/dags/*.yaml) rendered to Airflow (MWAA / ADF-managed) by a thin generator; orchestrator-neutral step contract (image, declared I/O, idempotency key, timeout, retries) behind SEAM: dag-orchestrator. Streams never run in Airflow; boundary rule: any consumer latency budget under 15 min = stream lane. 12 named DAGs P1..P3 including dag-replay and dag-quarantine-sweep. | Built inside the G3 pipeline-core epic; reconciliation is a step whose output artifact is the batch evidence entry. | ADR-003 (dag-orchestrator seam), C6 (batch lane), C7, ADR-004 (IaC provisions Airflow, object storage, SFTP). | Batch windows sized by the load model (834 4h budget; claims 4h); halt thresholds stop DAGs rather than flooding quarantine; replays safe end to end via idempotency keys. | Orchestrator reached only through the neutral step contract; MWAA vs ADF-managed Airflow is IaC configuration; ADF-native or Step Functions adapters only on customer mandate. | ADR-003/004; G3 pipeline core; object storage and SFTP at IaC layer. | Inside G3 pipeline-core L (Airflow rendering kept to a minimal operator set, ASSUMPTION). | Native-operator lock-in creeping in (banned by ADR-003); stream work leaking into Airflow (boundary rule binding). | DAG generator renders repo definitions; step idempotency property tests; dag-replay reprocessing yields exact counts, zero duplicates (UC-57). | DAG documentation generated from DAG definitions (never hand-written); batch DAG ops runbook per DAG epic. | Pipeline + FHIR Engineering & Validation pair | ACTIVE; P1
X3 | Hyperscaler portability + deployment configurator | Absent. No Terraform or IaC anywhere in any repo; greenfield confirmed by Phase 0. | phase0_repo_gate.md items 2 and 5; evidence.md substrate paragraph. | TARGET per ADR-004: one Terraform repo, three layers (core: network, K8s, Postgres, object storage, Kafka broker; platform: HAPI cluster, Temporal, Airflow, observability; app: services, BFF, projectors); per-cloud modules implementing a fixed interface; AWS + Azure first, GCP fast-follow. deploy.config.yaml drives CI (v1); admin-console Deployment screen renders the same engine (v2). Managed-FHIR services are conformance-gated adapters. | Greenfield; module interface is the seam (adding GCP = fourth implementation directory, zero core change); conformance suite (G3 harness) gates any managed-FHIR swap. | C7 (everything hyperscaler-specific in IaC), ADR-004, D5 deployment config spec, doctrine 6/7. | Provisions the load-model postures (HAPI 2 nodes pilot / 4-8 state; partition counts at topic creation; worker fleets per sizing logic). Single-tenant per state deployment; isolation by deployment, never code branching. | The workstream IS the portability posture: core sees only the five C7 protocols; per-cloud specifics live in module implementations. | ADR-004; approval gate D (AWS + Azure first); D5 spec; per-cloud walkthrough docs gated on first clean deploy. | Spine-scoped; sized in D5. Geocoding/terminology licensing per deployment at this layer. | Proprietary control-plane leakage into core (C7 dependency allowlist lint, adversarial axis); walkthrough docs authored before a stack deploys clean (forbidden: they must be deploy transcripts). | deploy.config.yaml schema validation; CI applies per-cloud stacks; conformance suite green before any managed-FHIR swap; dependency allowlist check. | Deployment guide structure rendered from deploy.config.yaml; environment matrix; upgrade/rollback template; AWS and Azure walkthroughs build-gated on first clean deploy. | Platform & Portability Engineer | ACTIVE; P1 onward
X4 | Stakeholder documentation (docs-as-code, audience-mapped) | CURRENT: real engineering docs/ tree exists (ARCHITECTURE, traceability, conformance-plan, current-state, remaining-work-and-test-plan, demo-plan, feature READMEs); conventions v2 with live gates. Zero coverage beyond engineering: no runbooks, deployment guide, API reference, executive ledger, compliance posture, enablement material. Known drift: doc says 145 passing tests; measured 223/223. | evidence.md item 5 docs list; 223/223 measurement; /home/claude/AI-CODING-CONVENTIONS_v2.md. | C8 register at docs/REGISTER.md (audience x document x state label x class x owner x done-gate x generatedFrom); authored-now set committed this run (honesty ledger, compliance posture, demo operator guide, onboarding, skeletons); build-gated set as templates T1..T9 plus epic acceptance criteria; generated sources wired (API reference from zod, deployment guide from deploy.config.yaml, agent pages from manifests); docs-stay-current CI checks. | Absorbs the existing docs tree as owned register rows (updated in place, never forked); reuses conventions §13.2 README template as T1 and the Tier-A/B language as the ledger grading scale. Order: drift fix, register, authored-now set, CI checks, templates handed to specialists, generation wiring. | C8 owned in full; C5 (operator guide toggle contract), C9 (tier honesty scale restated), C1/C2 (posture statement), C6 (DLQ runbook row), C3 (seam-swap discipline described). | No runtime component. Register lint, label audit, generated-doc freshness run per PR alongside convention gates; seconds of CI cost. | Zero protocol dependencies; markdown in the repo, rendered by CI in the permitted container runtime. | Spine outputs for target-state content; the other four specialists' docs-done entries for register absorption; D5 schema for the deployment guide. | E-X4-1 register plus checks S; E-X4-2 authored-now set S; E-X4-3 drift fix S (145 appears <=3 times, ASSUMPTION); E-X4-4 templates S; T8 generator wiring M (zod-openapi compatibility, SP-X4-1); Phase-4 assembly duties M. | Fiction creep (build-gated docs drifting into authored-now prose); ledger misuse in sales; register rot; RECONSTRUCTED trace steps hardening into fact (label must survive every derivative, amendment-001 §5 item 11); count drift recurrence; toggle honesty gap on unseamed screens. | docs-register-lint, docs-label-audit, docs-freshness-generated, docs-stay-current PR check, docs-readme-cap, drift-fix zero-145 verification, per-release operator-guide vs C5 walkthrough reconciliation. | The register itself plus all Annex documents; per-specialist docs-done packages T1..T9 handed off; capability-brief row closes at D6 assembly (finalizer obligation, verdict item 11). | Documentation Specialist | ACTIVE; authored-now set this run; adversarial verdict PASS, zero rubric failures
X5 | Accessibility + app-wide quality pass | No systematic accessibility coverage; Playwright e2e exists but no axe-core checks, no app-wide keyboard/aria pass. | Plan §3.1 O-9 row; evidence.md (Playwright e2e present). | TARGET. axe-core in Playwright per surface, keyboard navigation, aria/roles extended app-wide (O-9). Delivered as acceptance criteria attached to every surface any specialist touches, plus the absorbed D4 test plan (route-level 401/403/400/422/200 with PHI-safe assertions per BFF route, corpus-accuracy and adequacy seed-spread regression guards). | Rides C5 Playwright machinery; attaches to each specialist's epics rather than a separate build. | C5 (walkthrough suites), D4 (absorbed test plan), O-9. | n/a; CI cost only. | n/a. | Each surface's owning epic; C5 dual-mode suites. | Distributed: S per surface, attached to owning epics. | Accessibility treated as a final sweep instead of per-epic acceptance criteria (mitigated: O-9 criteria attach to every specialist surface by plan mandate). | axe-core pass per touched screen (named in G1 test 10, G5 E3/E7, UC-55); keyboard-nav assertions; D4 route matrix suite. | Accessibility criteria recorded per epic; finalizer spec owns the consolidated statement. | Finalizer spec + all specialists (acceptance criteria) | ACTIVE; cross-cutting, proves at the end of the dependency order
G3 / O-1 | Durable evidence persistence | CURRENT: defaultEvidenceStore() and siblings are in-process Maps; file-based state; evidence does not survive a restart. | evidence.md substrate paragraph; ADR-005 context. | TARGET per ADR-005: append-only Postgres ledger as system of record (monotonic sequence, attributed actor, correlation id, PHI-safe payload); EvidenceStore interface in src/lib/evidence/ modeled on the consent exemplar; mock Map stays selectable; record-affecting entries projected to FHIR Provenance/AuditEvent as derived state, rebuilt from the ledger, never dual-mastered. SEAM: evidence-store. | Consent module is the direct template (id field, attributed appends, absence-as-value, typed errors). First build step in the entire order; the template for consent store, gold-card, denial-rate swaps. | ADR-005, C3 (the first production C3 proof), C8 (per-load audit description). | Append-only table gives cheap ordered scans at batch-window write rates; retention table-level, 7-year default configurable. | Postgres wire only. | Postgres in dev compose (ASSUMPTION); GB-7 security review is a consumer. | S. ASSUMPTION: table design per ADR-005 needs no schema debate. | Minimal; the swap is the smallest and unblocks audit for everything after. | evidence.store.spec (attribution required, append-only, sequence monotone); evidenceStore.contract (mock AND real, C3 rule 7); UC-44 immutability shape. | Per-load audit evidence description (build-gated on this epic); traceability row evidence-store-swap. | Pipeline + FHIR pair (spine decided store via ADR-005) | ACTIVE; P1, first build step
G3 / O-2 | Real data-source adapters | CURRENT: gold-card roster, denial rates, provider directory are mock/seed sources behind existing seams; adequacy seed generated by gen_network_adequacy_seed.py. | evidence.md Tier A (adequacy engine real); src/lib/consent/providerAccessOptOut.ts:11-13 seam family; tools/seed/gen_network_adequacy_seed.py. | TARGET: production loaders behind the same interfaces: provider-directory nightly DAG (NPI-anchored survivorship per DP-7, feeds G7 shared provider model), gold-card roster feed, denial-rate feed. Each swap ships the C3 contract test against mock AND real; seed data remains the selectable mock mode forever. | Rides the O-1 swap template and the generic small-feed DAG shape; NUCC specialty normalization; geocoding at IaC layer. | C3 (SEAM per feed), C9 domain 10, DP-7 provider identity, O-6 consumer. | Nightly/weekly small feeds; trivial rates; reconciliation gates per feed (NPI checksum validity, active-provider delta >10% warn). | Postgres wire, S3-compatible object storage, OCI; extracts as CSV/FHIR bulk. | O-1 first (swap template); DP-7; G7 view-models consume what these load; measured feed statistics replace load-model ASSUMPTIONs here. | M. ASSUMPTION: extracts obtainable in CSV/FHIR bulk; geocoding licensed at IaC layer. | Feed access timing (GB-6 adjacent); directory ghosts (UC-05 answered by NPI survivorship). | goldCardSource.contract, denialRates.contract, providerDirectory.contract; UC-05 one-NPI-one-node fixture; UC-39 gold-card threshold path change without deploy. | Per-adapter design notes with C9 yield; traceability rows per adapter. | Pipeline + FHIR pair | ACTIVE; P1
G7 / O-3 | NA dashboards (port four providernet_analytics views) | Four dashboards live in a standalone Vite/React app (providernet_analytics); tcoc dashboards compute inline numbers. | phase0_repo_gate.md item 4; evidence.md Tier B dashboards line. | TARGET: the four views port as translations onto shared view-models inside tcoc (never lifted wholesale); each is a registered, versioned view-model materialized by the metrics projector (G1 build per amendment §1); BFF read routes; no aggregate math in components. | View definitions recovered from the standalone app; registry and read routes from G1 E7; feed events from G3. | View-model contract (zod, versioned, additive); C8; DP-6. | Keyed reads <=1s p95 CONFIRMED. | Postgres wire via projector substrate. | Metrics projector (G1, amendment §1); O-2 feeds; adequacy engine outputs. | Inside G1 E7 M; ASSUMPTION aggregate definitions recoverable without new source data beyond O-2. | Inline-math regression (registry as only read path, boundaries lint). | viewmodels.contract; UC-53 dashboard equals projector count exactly; axe-core per surface. | View-model registry README; dashboard rows in the register. | Graph & Context Architect (view-model discipline + build) + Pipeline pair (feed events) | ACTIVE; P2
G7 / O-4 | NA geospatial heatmap (county choropleth, drill-down) | Not built in tcoc; copilot focusCounties already exists and will drive it. | Plan §3.1 O-4 row; evidence.md adequacy copilot. | TARGET: county choropleth with state-to-county-to-detail drill-down as parameterized reads of registered view-models (never ad-hoc queries); copilot focusCounties drives parameters into the same read path. | Rides the O-3 view-model registry; geocoded provider locations from the O-2 directory loader. | View-model contract; DP-6; O-9 accessibility. | Precomputed county aggregates; <=1s p95 reads. | Postgres wire; geocoding data at IaC layer. | O-2 loader (locations), O-3 registry, metrics projector. | Inside G1 E7 / G3 O-2 scope; S-M. | Drill-down bypassing view-models (rule 5 of the discipline forbids). | UC-55: drill-down renders from view-models with no inline aggregation and passes axe-core. | Register row under G7 dashboards; operator-guide entry. | Graph & Context Architect + Pipeline pair | ACTIVE; P2
G7 / O-5 | NA compliance-readiness report | Not built. One-click audit evidence does not exist. | Plan §3.1 O-5 row. | TARGET: the report generates from the same registered view-models the screens consume, rendered to report format, citing view-model id plus version, so screen and audit evidence can never disagree (DP-6). First consumer of the Part 2 egress-scrubbing library per amendment-001 §4 binding interim rule. | View-model registry (O-3); egress-scrubbing library (G3, amendment §4); T7 audit-evidence-catalog pattern. | DP-6; C8 compliance audience; amendment §4 scrubbing rule (binding: no population extract ships without consuming the library). | Report generation is batch, from precomputed view-models. | Postgres wire; OCI for the generator. | O-3 view-models; egress-scrubbing library (G3); GB-6 for live data. | S-M inside the G7 view-model scope. | Report computing independently of screens (divergence test fails it); Part 2 re-disclosure without scrubbing (UC-17; interim rule binds). | Screen-vs-report consistency test (G1 test 9); UC-17 automated label scan finds zero Part 2 elements in mixed-population extracts; UC-54 one-view-model proof. | Audit-evidence-catalog entries (T7); feeds the D7 compliance audience. | Graph & Context Architect + Pipeline pair (scrubbing library) | ACTIVE; P2
G7 / O-6 | Adequacy, referrals, prior-auth integration | Not built. Adequacy findings do not connect to referrals or PA; no shared provider model. | Plan §3.1 O-6 row; evidence.md (adequacy engine Tier A, standalone). | TARGET: C1 provider-context extension (GET /api/person-context/{memberId}/provider-context) joins open gaps to adequacy-ranked referral candidates to each candidate's PA posture (gold-card status included), NPI-anchored per DP-7. Endpoint served by G1 per amendment §1; adequacy and language-concordance ranking logic is G7 per DP-6, delivered as a shared view-model; neither side reimplements the other. | Adequacy engine outputs; O-2 provider identities; gold-card roster; C1 read model. | C1 extension (spine-set shared provider model), DP-7, DP-6. | Single-read join from precomputed models; UC-35 target p95 <=300ms. | Postgres wire. | C1 implementation layer (G1, amendment §1); O-2 loaders; coverage 2@T1, care team 10@T1, referrals 12@T1. | M; joint G1/G7 surface. | S1-class ownership blur (resolved by amendment §1 boundary rules). | UC-35 single-call join with adequacy standing and PA posture populated; UC-36 language-concordance fixture; UC-32 threshold config change without deploy. | Provider-context endpoint in the generated API reference; register rows. | Solution Integration Architect (model) + G1 (serving) + G7 (ranking logic) | ACTIVE; P2
G5 / O-7 | Richer CQL criteria content | CURRENT: policy corpus engine is Tier A (17 real policies, 19/19 accuracy anchors, NormalizedPolicy ingestion); corpus lacks payer PA criteria depth. Sources verified: Aetna cardiac Clinical Policy Bulletins plus UnitedHealthcare PA requirements (documents, not code). | evidence.md Tier A policy corpus; phase0_repo_gate.md item 3 (PA folder contents). | TARGET: extraction into NormalizedPolicy-pattern criteria records with full provenance (source filename, checksum, section anchor, extractor version); every record ships smeReviewed: false; auto-approval and gold-carding hard-refuse unreviewed criteria; GB-3 sign-off flips the flag per record per version, attributed and audited. Care plan citations and goldenThread necessity consume one corpus (single source of truth). | Existing Tier-A corpus is the home (no parallel store); tools/content/extract-criteria scripts; accuracy anchors extended per extracted policy in the 19/19 pattern. | C8 provenance catalog row; GB-3 gate; DP-4 (citations). | Content work; batch extraction as OCI containers. | n/a beyond tooling containers. | GB-3 SME sign-off (blocked gate, planned around; content lands decision-support-only until then); SP2 decides JSON vs CQL representation. | E6 M. ASSUMPTION: document set stable and re-suppliable; semi-automated extraction with manual verification. | Unreviewed criteria escaping the flag into auto-approval (hard code gate, named test, owner notified on any exception request). | criteriaContent.test (schema, provenance completeness, smeReviewed false on every unreviewed record, auto-approval refusal); corpus accuracy anchors per policy. | O-7 criteria provenance catalog (one row per record: source, checksum, version, smeReviewed state); FAQ honest-answer entries. | Care Plan pair (Medical Expert lens) | ACTIVE; content flagged not-SME-reviewed until GB-3
G4 / O-8 | Interactive stage-3 deepening (PA journey) | PA engine chain is Tier A and real (goldenThread orchestrator, paMachine, DTR, work queue); no journey-lane driver; machine advanced only by per-request calls. | evidence.md Tier A goldenThread; src/lib/workflow/paMachine.ts (96 lines, pure table-driven transitions, human-gated submit/close-gap). | TARGET: the PA/documentation agent drives the existing /prior-auth machine end to end from thread context (ThreadResult) as a Temporal journey: human-gated submit, await payer claim-response, more-info documentation loop via existing DTR generator, denial-to-appeal packet, human-gated gap closure. transition() remains the single authority; the agent never sets Approved/Denied. The journey lane's first real workload. | Wraps paMachine without replacing it; reuses runFinancialClearance, selectDtrGenerator, generateQuestionnaireFromPolicy, the denied-appeal queue, CMS SLA clocks (72h/7d) as the binding outer bound. | C10 pa.* events; ADR-005 evidence chain; C1 context reads; DP-3 reuse rule. | One workflow per PA journey; inside the Temporal sizing envelope; every mutation idempotency-keyed. | Temporal via the journey-engine seam; no external channel dependency. | pa.* events from PA-lifecycle persistence (G3 outbox library precedes agentic E5 per amendment §2); agent runtime foundation (E3). | E5 M. ASSUMPTION: until pa.* events land, the journey runs Tier-A offline against in-memory stores in tests. | paMachine invariant erosion by the wrapping journey (property test: no path to Submitted/GapClosed without an attributed human decision). | paJourney.transitions; UC-41 full flow with every mutation human-approved through the existing inbox; journeyReplay determinism. | T9 agent page generated from pa-documentation-agent.json manifest; journey ops runbook. | Agentic Systems Designer | ACTIVE; P1 persistence, P2 journey
X5 / O-9 | Accessibility pass (whole app) | No axe-core checks, no systematic keyboard/aria coverage. | Plan §3.1 O-9 row. | TARGET: axe-core in Playwright per surface, keyboard nav, aria/roles extended app-wide; delivered as acceptance criteria attached to every surface every specialist touches, not a separate sweep. | Rides C5 Playwright machinery and each owning epic. | C5; D4. | CI cost only. | n/a. | Owning epics per surface. | S per surface, distributed. | Deferred to a terminal sweep (plan forbids: criteria attach per epic). | axe-core pass named in G1 test 10, G5 E3/E7 criteria, UC-55; keyboard-nav assertions. | Criteria recorded per epic row. | Finalizer spec + all specialists | ACTIVE; proves the build at the end of the dependency order
GB-1 | Live AI-DTR | Not built; planned around. DTR flow runs deterministically from the policy corpus today; live AI-assisted DTR is gated. | Plan §3.1 gated track (repo doc G-1, renumbered GB-1). | Planned around, not built, until the blocker clears. Any AI layer lands under the six guardrails on top of the deterministic DTR path. | Deterministic DTR generator remains the product path meanwhile. | AI guardrails (conventions §9); feature flags. | n/a until unblocked. | n/a. | BLOCKER: LLM API keys and model infrastructure. | Not estimated; blocked. | Building around the gate rather than through it is the mandated posture. | Deferred to unblock; guardrail evals required then. | Recorded as a blocked row in the register and ledger. | Blocked; planned around by Care Plan pair / goldenThread owners | BLOCKED (LLM keys / infrastructure)
GB-2 | LLM narration | Not built. Narration prompts are designed as versioned templates with the flag OFF; deterministic template path is the product. | Plan §3.1 gated track (GB-2); g2g4-agentic.md outreach agent design (narration behind feature flag, degrades to template). | Server-side narration on top of deterministic engines only, schema-parsed, PHI-safe, labelled decision-support, feature-flagged with graceful degradation (BackboneNotConfiguredError when absent). | prompts/*.md versioned with eval fixtures including injection cases, ready to activate. | AI guardrails; conventions §10.1 prompts-as-code. | n/a until unblocked. | Model endpoint at IaC edge. | BLOCKER: LLM keys and guardrail-compliant model infrastructure. | Not estimated; blocked. Narration flag ships OFF. | PHI leak or determinism erosion if activated early (UC-50/UC-51 tests gate activation). | UC-50 PHI-safe model-call assertion; UC-51 graceful degradation; eval suites per prompt. | Blocked row in register; honest-answer scripts already forbid claiming it. | Blocked; planned around by Agentic Systems Designer | BLOCKED (LLM keys / infrastructure)
GB-3 | SME sign-off | No external SME time available. Coalition medical-lens review is explicitly not GB-3 sign-off and is never represented as such. | Plan §3.1 gated track (GB-3); g5-careplan.md §3.2 honesty note. | Per-record, per-version attributed flag flip (smeReviewed: true) recorded to the ADR-005 ledger; auto-approval paths unlock only then. | O-7 flag lifecycle is built and waiting; content operates decision-support-only meanwhile. | ADR-005 (attributed flips); DP-4. | n/a. | n/a. | BLOCKER: clinical SME time. | Not estimated; blocked. | Unreviewed content influencing auto-approval (hard code gate refuses; named test). | criteriaContent auto-approval refusal gate stays green until sign-off. | smeReviewed state visible in the provenance catalog and every consumer surface. | Blocked; planned around by Care Plan pair | BLOCKED (SME time)
GB-4 | Tier-B backbone | The CMS-0057-F reference implementation (WSO2/Ballerina stack: fhir-service, cds-service, rule-engine, bulk-export-client, demo apps) is the Tier-B backbone source; not wired. | phase0_repo_gate.md item 2; conventions Tier-A/Tier-B distinction. | Backbone-gated capabilities keep the BackboneNotConfiguredError fail-loud pattern; Tier-B rows marked in traceability; nothing backbone-dependent claimed as offline-verified. | Planned around; adapters are fixture-complete and contract-tested before connectivity exists. | Conventions §15 Tier language; C5. | n/a. | n/a. | BLOCKER: backbone infrastructure and connectivity. | Not estimated; blocked. | Tier-A behavior claimed as Tier-B conformance (adversarial convention axis watches). | Backbone-gated test rows marked and skipped honestly offline. | Blocked row in register; conformance-plan.md governs. | Blocked; planned around by all specialists | BLOCKED (backbone infrastructure)
GB-5 | Conformance runs | CMS-0057-F API shapes exercised by Newman contract tests only; formal conformance never claimed from offline behavior. | evidence.md (Newman CMS-0057-F contract tests); x4 posture statement §7. | Formal conformance is an Inferno / Da Vinci activity governed by docs/conformance-plan.md, gated on backbone infrastructure; the G3 $validate fixture suite doubles as the doctrine-6 conformance seed gating any managed-FHIR swap. | Newman suite plus the CI conformance harness stand ready. | C4; doctrine 6; conventions §11 (offline never cited as conformance). | n/a. | n/a. | BLOCKER: conformance infrastructure (Inferno / Da Vinci environment); GB-4. | Not estimated; blocked. | Conformance overclaim (forbidden by the repo's own docs; operator guide Q7). | usCore $validate conformance suite in CI meanwhile. | conformance-plan.md absorbed register row. | Blocked; planned around by Pipeline + FHIR pair | BLOCKED (conformance environment)
GB-6 | Live adequacy data | Adequacy engine runs on the deterministic two-state seed; no live provider-directory or network feeds connected. | evidence.md Tier A adequacy; tools/seed/gen_network_adequacy_seed.py. | O-2 provider-directory loader is the production path when feeds exist; seed remains the selectable mock mode; adequacy seed-spread regression guards hold meanwhile (D4). | O-2 adapters fixture-complete before connectivity. | C3 seams per feed; D4 regression guards. | n/a until feeds land. | n/a. | BLOCKER: live provider-directory / network data feeds and contracts. | Not estimated; blocked (O-2 build itself is scoped and active). | Screens implying live data (operator guide labels; dual-mode registry binds OFF-mode claims). | providerDirectory.contract ready; seed-spread guard green. | Blocked row; ledger adequacy row labels engine vs data honestly. | Blocked; planned around by Pipeline pair + G7 owners | BLOCKED (live data feeds)
GB-7 | Security review | Not performed. Consent/authz code is tested; no formal security review has run. | Plan §3.1 gated track (GB-7); ADR-005 names GB-7 as a consumer. | The ADR-005 append-only ledger, Part 2 labeler test evidence, BFF invariant suite, and audit-evidence catalog are built as the review's substrate; review consumes them when resourced. | Everything auditable-by-construction: attributed mutations, correlation ids, PHI-safe payloads. | ADR-005; C8 compliance rows; UC-62 access-trail shape. | n/a. | n/a. | BLOCKER: security review resourcing / scheduling. | Not estimated; blocked. | Review findings arriving late against a widened surface (mitigated by evidence substrate landing first, O-1). | UC-62 trail-completeness proof stands ready as review input. | Compliance posture statement and audit-evidence catalog are the review's entry documents. | Blocked; substrate built by Pipeline pair (O-1) and X4 | BLOCKED (security review resourcing)

## Backlog
Spike and epic backlog (finalizer estimates flagged where amendment-assigned)
ACE Production Gap Assessment. Governing plan v11, gates A-L approved 2026-08-21. Source: coalition run (spine, five specialists, adversarial verdict, amendment-001).
Id | Title | Area | Type | Rationale | Effort | Dependencies | Phase
G1-E1 | Mock extraction + GraphStore seam + D3 screen on BFF lens route | G1 | epic | Retires the 804-line frozen file by extraction; seam lands with mock mode; demo stays green; baseline shrinks. | M | C5 demo-green suite | P1
G1-E2 | Postgres graph store + lens engine + contract tests | G1 | epic | ADR-001 store made real; recursive CTE lens engine; C3 contract suite against mock AND real. | M | G1-E1; SP-1 verifies CTE performance | P1
G1-E3 | Projector core + P1/P2 mapping modules | G1 | epic | Consumer group, envelope parsing, dedupe, checkpointing, ~19 per-domain mapping modules. Largest G1 surface. | L | ADR-002 backbone in dev compose; C10 payload schemas stable; G1 edge taxonomy completed first (amendment adjudication e) | P1 domains first, P2 domains as feeds land
G1-E4 | C1 lens endpoints + consent scoping + Part 2 redaction | G1 | epic | Authz-guarded, purpose-scoped serving; asOf; presence-only stubs for restricted nodes (SP-3 sets default). | M | Authz guard reusable server-side call; SP-3 | P2
G1-E5 | Rebuild harness + merge/unmerge rekey + proof suite | G1 | epic | Mechanical form of the C10.2 rebuild requirement; DP-7 merge semantics proven by checksum-equality and property tests. | M | Outbox as per-member replay source (ratified amendment §3); merge crosswalk from G3 DP-7 build | P2
G1-E6 | Dual-mode demo-green + axe additions for the graph screen | G1 | epic | C5 registry entry; structural assertions both modes; O-9 accessibility. | S | G1-E1; C5 machinery | P2
G1-E7 | View-model registry + contract + adequacy view-model reads | G1 | epic | G7 discipline: named versioned view-models, BFF reads, O-5 report from the same rows as screens. | M | Metrics projector (G1 per amendment §1); O-2 feeds | P2
G1-E8 | C1 implementation layer: person-context projector, person-context and provider-context endpoints, metrics projector | G1 | epic | Amendment-001 §1 closes verdict S1 (largest structural gap): the C1 read side gets a build owner; MVR scores become measurable through these projectors. | L (finalizer-assigned per amendment; unsized by any specialist) | G3 domain events plus outbox library; C9.4 MVRs; O-6 shared provider model | P2
G1-E9 | Keystone ranking + hypothesis-edge confirm/reject lifecycle | G1 | epic | Amendment §5 (G1-d): deterministic scoring over BLOCKS assertions with weights as data; hypothesis review reuses the existing work queue. P2 acceptance items for trace step 7. | M (amendment-assigned) | G1-E3 BLOCKS assertions; work-queue surface | P2
G1-E10 | Query additions: around-event time-window query + household lens | G1 | epic | Amendment §5 (UC-19, UC-65): around-event query joins the lens set; household lens is the stated exception to per-lens partition scope. | S-M (amendment-assigned) | G1-E2 lens engine; household events (834 dependent linkage, G3) | P2 (household P3 depth)
G1-E11 | UC-64 break-glass serving surface + authz guard extension | G1 | epic | Amendment §4: emergency-treatment purpose; time-boxed override token, mandatory reason, policy matrix as data, break-glass audit class, post-hoc review item. Feature-flagged, disabled by default. | M (amendment-assigned) | C1 contract extension (spine); compliance review of the policy matrix before enablement | P2
G3-E1 | O-1 evidence store swap (ADR-005, first C3 proof) | G3 | epic | Append-only Postgres ledger replaces in-memory defaultEvidenceStore(); the template for every subsequent seam swap; unblocks audit for everything after. | S | Postgres in dev compose | P1 (first build step)
G3-E2 | Outbox library + relay + backbone interface consumption | G3 | epic | ADR-006 as amended (intent-commit pattern, amendment §2): the one way events are born. Binding sequence: precedes G5 E3 and agentic E5. | M | Redpanda dev compose; ADR-002; amendment §2 intent pattern | P1
G3-E3 | Pipeline core: landing catalog, staging, quarantine, reconciliation, harnesses, DAG generator | G3/X2 | epic | The five-stage skeleton every feed shares; lane-agnostic transforms packaged twice from one implementation. | L | Object-store port (S3 API); ADR-003 step contract | P1
G3-E4 | Adapter 834 + identity anchor path + survivorship | G3 | epic | Identity and coverage anchor everything; diff-load semantics (ratified amendment adjudication b); 60..90 band routes to steward review (amendment G3-b); 834 dependent linkage emits related-person.linked (amendment S6). | L | G3-E3; matchService; survivorship rules as data | P1
G3-E5 | Adapter 837/835 claims + remittance | G3 | epic | Financial facts T1 plus clinical shadows T3; two reconciliation gates including financial control totals; closes the golden thread payment hop. | L | G3-E3; claim-identity dedupe key (amendment G3-c) | P1
G3-E6 | Adapter pharmacy dispense | G3 | epic | Dispense T1 with RxNorm normalization; adherence signal substrate for the SDE MVR. | M | SP-3 feed shape; terminology service | P1
G3-E7 | Provider directory + gold-card + denial-rate loaders (O-2) | G3 | epic | NPI-anchored provider identity with survivorship; first live exercise of the existing mock seams; feeds G7. | M | G3-E1 swap template; DP-7 | P1
G3-E8 | Validation harness: runtime $validate gate + CI conformance suite | G3 | epic | US Core profile gating at stage 4; fixture suite doubles as the doctrine-6 conformance seed for any managed-FHIR swap. | M | SP-2 throughput answer; C4 profiles | P1, gating from first load
G3-E9 | Adapter CCD/QE micro-batch (golden-path proof) | G3 | epic | Hops 0..5 of golden-path.md are this adapter's acceptance walkthrough; section extractors, entry-level quarantine, T1/T2 tier split. | L | SP-1 schematron path; SP-5 QE connectivity | P2
G3-E10 | Adapter ADT HL7v2 stream | G3 | epic | Encounter events T1; 60s receipt-to-signal budget; unmatched-admit aging alarm. | M | SP-4 ingress transport; stream harness | P2
G3-E11 | Adapters: in-product screening + referral webhooks | G3 | epic | SDOH T1 with provenance; referral T1 with closed-loop status; webhook-vs-export weekly reconciliation. | M | Referral platform webhook docs; screening instrument in-product | P2
G3-E12 | Segmentation labeler + Part 2 rule set | G3 | epic | Labels at transformation time in three places atomically (canonical record, FHIR meta.security, C2 envelope); ships P1, active from first claims load; retrofitting is a rebuild, therefore banned. | M | Part 2 value sets curated with compliance input | P1 labeler; P2 record-native labels; P3 full SUD lane
G3-E13 | Match service wrapper + unmatched-identity queue items | G3 | epic | Wraps the Tier-A matchEngine unchanged; blocking keys, thresholds, work items into the existing inbox (no second inbox). | M | Work-queue item types extensible | P1
G3-E14 | Flat-file manifest engine + HMIS (CBO path) | G3 | epic | Lowest-common-denominator path engineered as a product surface: per-partner manifests as data; onboarding a CBO = manifest plus fixtures, zero code. | L | Manifest schema frozen; ops authoring | P3
G3-E15 | Screen seam swaps (rolling, per WPC screen) | G3 | epic | The G3 definition of done: each screen renders from pipeline-fed record data with the mock toggle off, per consumer MVR tier. | M total | C1 person-context projections (G1-E8) landing in step with feeds | P1 onward, rolling
G3-E16 | Part 2 egress-scrubbing library (UC-17) | G3 | epic | Amendment §4: one library scrubs every egress path; O-5 report is first consumer; binding interim rule: no population extract ships without it. | M (amendment-assigned) | G3-E12 labels; consent purposes | P2, before any population extract
G3-E17 | Record-repair DAG for unmerge re-attachment (UC-03) | G3 | epic | Amendment §4: identity.member.unmerged triggers a DAG that re-subjects every affected FHIR resource by provenance crosswalk, emits correction events, verifies the UC-03 acceptance criterion as its reconciliation gate. | M (amendment-assigned) | Crosswalk rows persisted at stage 3/4; G3-E2 outbox | P2
G3-E18 | UC-43 PA-vs-adjudication discrepancy gate | G3 | epic | Amendment §5: one reconciliation rule joining pa.* outcomes against claim adjudication, alarmed on approved-then-denied; feeds the golden thread. | S (amendment-assigned) | G3-E5 835 path; pa.* events | P1-P2
G3-E19 | Claim-identity dedupe key (UC-45) | G3 | epic | Amendment §5 (G3-c): second, claim-identity-scoped dedupe check (payer claim id + adjustment sequence) at stage 3 so resubmissions across batches converge. | S (amendment-assigned) | G3-E5 | P1
G3-E20 | PA-lifecycle persistence via internal-writer outbox (C9 #17) | G3 | epic | goldenThread output persisted with Provenance through the outbox pattern; emits pa.* events agentic E5 depends on. Adjudication (f) covers it. | S | G3-E2 outbox library | P1
G2G4-E1 | SDE engine + taxonomy + policy packs + seamed screen + BFF | G2 | epic | The decision model proven offline first (mock mode, no keys); the demo acceptance shape rendered from real engine output. | M | Backbone dev-compose for intake only; engine and screen ship first in mock mode | P1 mock mode; P2 live
G2G4-E2 | Gap-derivation projector + measure data (GSD/EED-class) | G2 (F1) | epic | Trace finding F1: the unowned measure evaluator, assigned into G2 scope by spine disposition (owner escalation still open); explicitly NOT certified HEDIS. | M | C10 record events; value-set references; backbone | P2
G2G4-E3 | Agent runtime foundation: manifest registry, journey facade, tool broker, inbox reuse, escalation engine | G4 | epic | The minimal runtime DP-3's three agents live on; a fourth agent touches only manifests plus one workflow file. | M | Temporal dev-compose (X1); additive QueueName extension; escalation as role-rank config (amendment a) | P2
G2G4-E4 | Signal intake + pending-signal projection on the backbone | G2 | epic | Canonical topology per amendment adjudication (e): consume domain-events, map via taxonomy, publish signal.raised, fold from own projection. | S | C6 topics provisioned with load-model partition counts | P2
G2G4-E5 | PA/documentation agent (O-8) | G4 | epic | First agent: exercises the runtime against the strongest Tier-A chain with zero external-channel dependency; paMachine invariants inherited verbatim. | M | pa.* events from G3-E20 (outbox library precedes this per amendment §2); G2G4-E3 | P2
G2G4-E6 | Outreach agent + templates + evals | G4 | epic | Executes SDE-approved touchpoints HITL; deterministic template path ships before any narration; injection and PHI evals. | M | S3 channel adapter spike; consent 15@T1 | P2
G2G4-E7 | Referral coordination agent | G4 | epic | Tracks referral.* events, stall timers, HITL nudges, care-team escalation, park-with-audit; never executes external bookings (F2 boundary). | S | Referral events 12@T1 (G3-E11, P2); stall windows as policy data | P2
G5-E1 | Care-plan core extraction, deterministic engine, data externalization | G5 | epic | Pure planEngine.evaluate(context, deps); keyword logic replaced by coded triggers; keeps barrier-first and modality semantics as data-driven capability. | M | Legacy semantics port as data rules (medical-lens review inside the epic) | P2
G5-E2 | Acceptance oracle: golden fixtures, property invariants P1..P6, FHIR conformance | G5 | epic | DP-4 made executable; the regression floor for a currently zero-test 1,262-line service. | M | G5-E1 (interleaved); seven journey-diverse fixture archetypes | P2
G5-E3 | BFF routes, FHIR persistence, review flow reuse | G5 | epic | Server-side generation behind /api/care-plan/*; persistence via internal-writer outbox in the route transaction (amendment adjudication f); clinician review in the existing work queue. | M | G3-E2 outbox library precedes this (binding, amendment §2); C1 mock mode until endpoint lands | P2
G5-E4 | Progress projector (golden-path hop 8) | G5 | epic | Consumes care-gap.* and domain events for members with active plans; goal progress with evidence refs; rebuildable from replay. | S | Backbone dev-compose; gap events stubbed by fixtures until G2G4-E2 | P2
G5-E5 | Contraindication gate + citation registry | G5 | epic | Class-level gating at 9@T1; data-limitation flag below; every template citation resolves or the template cannot load. | M | SP1 rule sourcing bounds the set first | P2 flag; P3 gating as 9@T1 arrives
G5-E6 | O-7 criteria extraction + smeReviewed flag lifecycle | G5 (O-7) | epic | Aetna/UHC documents into NormalizedPolicy-pattern records with provenance; auto-approval hard-gated until GB-3. | M | SP2 representation decision; GB-3 blocked (planned around) | P2, decision-support-only until GB-3
G5-E7 | Legacy delegation, dual-mode green, baseline shrink | G5 | epic | Five frozen generator files become delegates then retire; baseline shrinks by five; C5 proves both paths. | S | SP4 UI-coupling audit first | P2
X4-E1 | docs/REGISTER.md + CI checks (register lint, label audit, freshness, docs-stay-current) | X4 | epic | The C8 artifact, enforced not curated; every doc has a row, every row a done-gate. | S | Plain node/bash scripts in tools/docs joining existing CI | This run (authored-now)
X4-E2 | Authored-now set: honesty ledger, compliance posture, demo operator guide, FAQ, onboarding, skeletons | X4 | epic | Written from verified evidence plus spine outputs only; every target-state statement labeled TARGET. | S | demo-plan.md scene names reconcile without rewrites (ASSUMPTION) | This run
X4-E3 | 145-vs-223 drift fix in docs/remaining-work-and-test-plan.md | X4 | epic | Verified-pattern patch with as-of date and recurrence guard; the file lives in the canonical repo, not the staged copy. | S | Repo access; claim appears <=3 times (ASSUMPTION) | This run
X4-E4 | Template pack T1..T9 committed under docs/templates/ | X4 | epic | Build-gated doc templates handed to the other four specialists for embedding in epic acceptance criteria; no operational fiction. | S | None | This run
X4-E5 | T8 API-reference generator wiring (zod-openapi in CI) | X4 + G3 | epic | Generated from schema.ts; hand-written route docs fail freshness; covers the 21 existing routes first. | M | SP-X4-1 zod-openapi feasibility; Pipeline pair's first schemas | P1
X4-E6 | Phase-4 assembly duties: capability brief row, label audit across all D7 documents, RECONSTRUCTED label survival | X4 (finalizer-carried) | epic | Verdict item 11 carried unchanged by amendment §5: capability-brief closes at D6 assembly; label audit runs across every derivative. | M | All specialist docs-done deltas merged | Phase 4
G1-SP-1 | CTE performance at depth 3 | G1 | spike | Does a depth-3 recursive CTE over a 10^3-node subgraph with lens filtering stay under 100ms p95 on pilot Postgres, or is a closure/adjacency cache needed? Output: query plans plus k6 numbers at 10^2/10^3/10^4 nodes. | Timeboxed spike | Synthetic subgraph generator | Before G1-E2 hardening
G1-SP-2 | Per-member replay source interface (JOINT with G3-SP-7 per amendment §3) | G1 + G3 | spike | Outbox-as-replay-source mechanics: read API, sequence semantics across merged identities, retention. Ratified as contract by amendment §3; the merged joint spike executes that section. | Timeboxed spike (joint) | Amendment §3 rulings | Before G1-E5
G1-SP-3 | Part 2 presence-stub compliance | G1 | spike | Is presence-only disclosure of a restricted node acceptable, or must redaction be full omission? Output: compliance-reviewed answer recorded in the posture statement; config default set. | Timeboxed spike | Compliance input | Before G1-E4 default ships
G1-SP-4 | D3 payload compatibility | G1 | spike | Exact semantic-payload to visual mapping for the existing force layout (including whether ChildDevelopment stays a node type); confirms E1 sizing. Output: mapping table plus rendered spike branch. | Timeboxed spike | None | Before G1-E1
G1-SP-5 | asOf lens semantics | G1 | spike | Does asOf apply to edge validity only or also node property history (would need a history table)? Current design interval-only. Output: decision note; property history would be additive. | Timeboxed spike | C1 consumer expectations | Before G1-E4
G3-SP-1 | X12 + CCD tooling selection | G3 | spike | TypeScript X12 parse approach (library vs thin 5010 segment reader) and schematron execution path (Java sidecar vs precompiled XSLT) meeting cap, determinism, C7. Output: prototyped 834 and CCD stage-2 validators. | Timeboxed spike | Fixtures | Before G3-E4/E9
G3-SP-2 | $validate throughput | G3 | spike | Can batched HAPI $validate sustain the 4h/486 rec/s window (batch sizes 10/100/500)? Fallback: sidecar validator library matched against server verdicts. | Timeboxed spike | Dockerized HAPI | Before G3-E8
G3-SP-3 | Pharmacy feed shape | G3 | spike | Delimited extract vs raw NCPDP telecom from the pilot source; determines adapter complexity (M vs L). | Timeboxed spike | Source contact | Before G3-E6
G3-SP-4 | ADT ingress transport | G3 | spike | MLLP listener self-hosted vs QE REST relay: what the QE offers and where the listener lives in IaC so core stays protocol-clean. | Timeboxed spike | QE contract | Before G3-E10
G3-SP-5 | QE connectivity for CCD | G3 | spike | Query-driven pull vs push subscription: what the Hixny-class QE permits, rate limits, auth. Shapes dag-qe-ccd-microbatch cadence. | Timeboxed spike | QE contract | Before G3-E9
G3-SP-6 | Terminology service + licensing | G3 | spike | Self-hosted terminology (HAPI module vs dedicated service) and SNOMED/RxNorm/LOINC licensing posture per deployment satisfying C7 and state UMLS licensing. | Timeboxed spike | Compliance/legal input | Before G3-E6/E9
G3-SP-7 | Outbox relay ordering under merge (JOINT with G1-SP-2 per amendment §3) | G3 + G1 | spike | Prove per-member commit-order preservation across a merge event replay on two-node HAPI plus Postgres; the DP-7 non-negotiable exercised early. Merged into one joint spike executing amendment §3. | Timeboxed spike (joint) | G3-E2 | Before P2 projector scale-up
G2G4-S1 | Temporal ops posture on AWS + Azure | G4 | spike | Self-hosted Temporal deployment shape in the ADR-004 platform layer (versions, Postgres sizing at 140K open workflows, upgrade path) plus dev-compose story. | Timeboxed spike | ADR-004 layout | Before G2G4-E3
G2G4-S2 | Coordination-window semantics | G2 | spike | Per-member daily fold vs per-priority windows; decided against a week of representative signal fixtures. Output: policy-pack defaults, not code. | Timeboxed spike | G2G4-E1 engine | Before P2 go-live
G2G4-S3 | Communication channel adapter | G4 | spike | Which SMS/email path fits C7 for pilot (self-hosted gateway vs IaC-edge vendor); what consent metadata the channel needs. Blocks the outreach execution step only. | Timeboxed spike | None | Before G2G4-E6 execution
G2G4-S4 | Workforce capacity source | G2 | spike | Where care-team staffing counts come from for capacity throttles; until answered, capacity is a configured daily budget (documented ASSUMPTION). | Timeboxed spike | Operations input | P2
G2G4-S5 | Care-team hierarchy for escalation | G4 | spike | Chain-walk at 10@T3 (P1) vs 10@T1 (P2); largely resolved by amendment adjudication (a): ladders are role-rank config over membership; degraded P1 posture ratified. | Timeboxed spike | Amendment (a) rulings | P1-P2
G5-SP1 | Contraindication rule sourcing | G5 | spike | Which published class-level rule source gives clinically defensible gating at 9@T1 without pharmacy-grade licensing; exact rule schema. Must also state whether UC-28 common-pair rules fit or are a labeled scope boundary (verdict G5-a). | Timeboxed spike | Medical lens | Before G5-E5
G5-SP2 | O-7 criteria representation | G5 | spike | Structured JSON vs CQL for extracted Aetna/UHC content: which the existing DTR/CQL path actually executes; what gold-card gating needs. | Timeboxed spike | Policy corpus internals | Before G5-E6
G5-SP3 | Offline conformance depth | G5 | spike | How much C4 validation is assertable Tier-A offline vs requiring HAPI $validate; where the backbone-gated line sits in the suite. | Timeboxed spike | None | Before G5-E2 finalizes
G5-SP4 | UI coupling audit | G5 | spike | Which unstaged WPC screens import the legacy generator and with what shapes; closes the section-2 item-15 ASSUMPTION and confirms E7 scope. | Timeboxed spike | Canonical repo access | Before G5-E7
G5-SP5 | Progress-change review policy | G5 | spike | Which plan-change classes require clinician sign-off vs auto-annotation; the hop-8 no-review default for progress annotations is currently ASSUMPTION. | Timeboxed spike | Clinical policy input | Before G5-E4 defaults ship
X4-SP-1 | zod-openapi feasibility | X4 | spike | Does zod-openapi render the repo's existing schema.ts shapes, including discriminated-union Results, without rewrites? Decides the T8 generator choice. | Timeboxed spike | Repo zod version | Before X4-E5
X4-SP-2 | docs-stay-current diff heuristic | X4 | spike | Can the anchor-diff-to-register-row mapping derive mechanically from generatedFrom plus a small anchor map, or does it need per-row watch paths? Output: the check's config format. | Timeboxed spike | X4-E1 | With X4-E1
X4-SP-3 | Label-audit heuristic strength | X4 | spike | False-positive rate of the capability-noun heuristic on the committed annexes; keep, tune, or demote to advisory. | Timeboxed spike | X4-E2 annexes committed | With X4-E1

## WPC Coverage
C9 whole-person record coverage: domain x tier x phase (T1 coded, T2 document, T3 claims-inferred, T0 absent)
ACE Production Gap Assessment. Governing plan v11, gates A-L approved 2026-08-21. Source: coalition run (spine, five specialists, adversarial verdict, amendment-001).
Domain | Current Tier | P1 Tier | P2 Tier | P3 Tier | Sources | Consumer Mvrs | Notes
1. Demographics / identity | T0 (Patient seeded only; pipeline-fed coverage zero) | T1 @834 with survivorship per DP-7 (source-attributed facts; golden view is a projection) | T1 enriched @QE CCD | T1 + household links | 834 (identity-authoritative; no-match creates identity; 60..90 band to steward review per amendment G3-b), QE CCD header demographics, screening | All consumers (graph, SDE, care plan, adequacy, agents, golden thread require 1@T1) | Match engine is Tier A today; survivorship, merge/unmerge, provider identity are new build. Merge rekeys projectors by replay, never in-place.
2. Coverage / eligibility | T0 (Coverage seeded) | T1 @834 (monthly full diff-load + weekly deltas) | T1 (delta stream) | T1 | 834 full + delta over SFTP; diff-load ratified as doctrine-conformant default (amendment adjudication b); emit-all is the deviation requiring spine re-derivation | Graph, adequacy, golden thread, agents | Coverage gaps represented as coverage.terminated then coverage.enrolled, never a new person (UC-06).
3. Encounters / utilization | T0 | T3 @837 claims shadows | T1 events @ADT stream; T2 @CCD | T1 | 837 (T3 shadows, tier-stamped), ADT HL7v2 stream (T1, 60s budget), CCD (T2) | Graph (>=T3), SDE (T1 stream, ADT), care plan | T3 shadows never silently upgrade; a later T1 recording supersedes by coded identity with both provenances retained.
4. Conditions | T0 (3 seeded) | T3 @837 dx shadows | Partial T1 @CCD coded problems | T1 | 837 dx codes (ICD-10, T3), CCD Problems section (partial T1) | Graph (>=T3), care plan (partial T1), SDE | Tier labels flow into C1 sections and gap-derivation evidenceTier so T3-only gaps are weighed honestly.
5. Medications (prescribed AND dispensed) | T0 (1 MedicationRequest seeded) | Dispensed T1 @pharmacy feed; prescribed T3 @claims | Prescribed partial T1 @CCD | Both T1 | Pharmacy dispense feed (NDC to RxNorm, T1), pharmacy claim lines (T3), CCD Medications section | Care plan (5-dispense@T1), SDE (adherence signals from dispense cadence) | Adherence computation belongs to SDE/metrics, not the graph; dispense-lapse is a derived signal class.
6. Labs / vitals | T0 (1 Observation seeded) | T0 | Partial T1 @CCD/QE coded results (LOINC) | T1 @direct lab feeds (ASSUMPTION: lab-feed availability) | CCD Results section (LOINC-coded, the golden-path domain), direct lab feeds P3 | Care plan (partial T1), SDE, graph | The golden-path worked example (A1c 7.2 via QE CCD) runs on this domain; unmappable codes quarantine the entry, not the document.
7. Procedures | T0 | T3 @837 | T2 @CCD | Partial T1 | 837 procedure codes (CPT/HCPCS, T3), CCD | Graph, golden thread | Shadow resources carry a shadow provenance profile slice so consumers can filter by tier.
8. Immunizations | T0 | T0 | T2 @CCD | T1 @registry (NYSIIS-class, ASSUMPTION) | CCD Immunizations section (T2), state registry P3 | Care plan | P3 additive graph projection; no P2 lens depends on it.
9. Allergies | T0 | T0 | T2 + partial T1 @CCD | T1 | CCD Allergies section | Care plan (contraindication gate) | Honesty note binding: contraindication checking is asserted only at 9@T1; below that every plan carries the data-limitation flag and requires human approval to activate (UC-31).
10. Care team / attribution | T0 | T3 @claims attribution + provider directory T1 (NPI-anchored per DP-7); pilot roster deployments get P1 attribution via the O-2 loader (amendment adjudication a) | T1 @CCD care team | T1 | Provider directory nightly DAG (O-2), claims attribution (T3), CCD Care Team section | Graph, adequacy (10@T1 NPI-anchored), agents (escalation chains) | No C9 tier ever promises a reporting hierarchy; escalation ladders are role-rank config data over membership (amendment a).
11. Care plans / goals / tasks | T0 | T0 | T1 platform-authored (G5 output persisted to record via internal-writer outbox, amendment adjudication f) | T1 | Platform-authored (G5 engine output as CarePlan/Goal/Task/ServiceRequest per C4) | Graph, agents, golden thread | care-plan.* events emit through the same outbox, closing the loop without dual-write.
12. Referrals / service requests | T0 (1 ServiceRequest seeded) | T0 | T1 @referral platform webhook + platform-initiated | T1 incl closed-loop status | Referral platform webhooks (Unite Us-class) + flat-file export backstop (reconciled weekly), platform-initiated ServiceRequests | SDE, adequacy, agents, graph | referral.stalled has one emitter: the pipeline outbox for platform-reported stalls; internally inferred stalls are SDE signals, never record-domain events (amendment adjudication e).
13. SDOH (Gravity: screenings, Z-codes, goals, referrals) | T0 | Z-code T3 shadow @claims | T1 @in-product AHC HRSN screening (provenance-tagged patient-reported) | T1 + CBO/HMIS flat-file paths | In-product screening (stream, Gravity SDOHCC profiles), claims Z-codes (T3), CBO flat files and HMIS extracts (P3, first-class by doctrine) | Graph, SDE, care plan (all at 13@T1) | Flat-file path engineered as a product surface: per-partner manifests as data, onboarding zero-code (UC-09).
14. Behavioral health incl SUD (42 CFR Part 2) | T0 | BH T3 @claims (segmentation labeler active from the first claims load) | BH T2/partial T1 @QE where consent allows | SUD exclusively via Part 2-segmented lane, labeled at stage 3 | BH claims, QE feeds per consent, SUD content inside claims/CCD/BH feeds through the labeling discipline | Care plan, SDE (consent-gated reads only) | Labels land atomically in canonical record, FHIR meta.security, C2 envelope; non-cleared projectors drop by envelope inspection alone. Retrofitting is a rebuild, therefore banned. Egress paths scrubbed by the G3 library (amendment §4, binding interim rule).
15. Consent / directives | T0 (1 Consent seeded; mock store in code) | T1 (consent store seam swap in the ADR-005 seam-swap order; opt-out model live) | T1 + Part 2 segmentation labels record-native | T1 | Platform consent module (Tier-A seam exemplar) swapped to durable store; consent events via internal-writer outbox | Every consumer (read scoping); SDE 15@T1; care plan; agents | Read-time purpose-plus-consent evaluation stacks on transformation-time labels (C1). Member/proxy requestor classes added additively (amendment §5 UC-67); minor-consent rule content deferred to owner plus compliance.
16. Claims / financial (golden thread) | T0 (Claim/EOB seeded) | T1 @837/835 (financial facts are T1; clinical inference from them stays T3) | T1 | T1 | 837/835 weekly batch; 835 links payment to claim (payment.posted), closing the delivery-to-payment hop | Golden thread (16@T1), adequacy | Financial control totals reconciled exactly per batch; UC-43 discrepancy gate joins pa.* against adjudication (amendment §5); claim-identity dedupe prevents double payment (UC-45).
17. PA lifecycle | T0 (engine real, record not pipeline-fed) | T1 platform-native (goldenThread persisted with Provenance via the internal-writer outbox; outbox library from G3 build step 2) | T1 | T1 | Platform goldenThread output; pa.* events (submitted/pended/approved/denied/goldcard.applied) | Golden thread, agents (O-8 journey), graph | Strongest existing Tier-A chain; persistence makes it pipeline-real, not screen-real (UC-38).
18. Assessments / member-reported | T0 (1 Questionnaire seeded) | T0 | T1 @in-product questionnaires | T1 + SMS/app PGD stream | In-product QuestionnaireResponse via BFF (still passes stages 1..5 for provenance and replay), SMS/app PGD P3 | SDE, care plan | provenance=patient-reported survives through projection so consumers weight it distinctly (UC-11); caregiver-reported distinguished with RelatedPerson identified (UC-66).
19. Caregiver / household (RelatedPerson) | T0 | Partial T1 @834 dependent linkage (related-person.linked emitted from 834 dependent segments; amendment-001 §5 S6 supersedes the original T0) | Partial T1 @CCD + screening | T1 | 834 dependent segments (P1, nearly free, unblocks UC-68), CCD, screening | Graph (household lens), agents | Household edges written to both members' partitions in one transaction; household lens is the stated exception to per-lens partition scope (amendment §5 UC-65).
20. Documents (DocumentReference) | T0 | T0 | T2 @CCD-as-document with provenance | T2 at scale (T2 is this domain's terminal tier by definition) | CCD/QE whole documents alongside their discrete extractions | Care plan (human review), compliance | The whole CCD lands as DocumentReference (T2) with Provenance linking both it and its discrete T1 extractions to the landing id (UC-08 tier honesty).

## Use-Case Trace
16-step representative trace (RECONSTRUCTED; verification instance, not the specification)
ACE Production Gap Assessment. Governing plan v11, gates A-L approved 2026-08-21. Source: coalition run (spine, five specialists, adversarial verdict, amendment-001).
Step | Description | Components | C9 Domains Tiers | Phase Real | Status Note
1 | Member surfaces across fragmented systems | G3 pipelines (all five stages), X2 DAG layer, X1 substrate | 1@T1, 2@T1, 3@T3, 16@T1 | P1 | RECONSTRUCTED REPRESENTATIVE. Covered. Landing and staging make fragmentation visible and auditable.
2 | Identity resolution to one anchored identity | Match engine (Tier A, exists) + DP-7 survivorship/merge semantics (build), G3 stage 3 | 1@T1 | P1 | RECONSTRUCTED REPRESENTATIVE. Covered. Engine real today; survivorship, merge/unmerge, provider identity are new build. Amendment adds the UC-03 record-repair DAG (G3) for unmerge re-attachment.
3 | Whole-person record assembly | G3 + X2 + HAPI posture (X1), ADR-005 evidence, ADR-006 outbox (intent pattern per amendment §2) | All twenty domains per phased C9.1 targets | P1 starts; P2/P3 deepen | RECONSTRUCTED REPRESENTATIVE. Covered. Completeness reported only via D1 sheet 3 against C9.
4 | Consent established and scoped (Part 2) | Consent seam (Tier A exemplar) + store swap (ADR-005 order), G3 stage-3 labeling | 15@T1 | P1 (opt-out live); P2 (Part 2 labels) | RECONSTRUCTED REPRESENTATIVE. Covered. Segmentation at transformation time, read-time check on top (C1); egress-scrubbing library (amendment §4) closes the re-disclosure path.
5 | Care gaps detected against measures | Gap-derivation projector (G2 scope per spine F1 disposition) consuming C10 events; metrics projector build is G1, feed events G3 (ownership per amendment §1) | 3@>=T3, 4@>=T3, 6@partial T1, 5@T1 dispense | P2 | RECONSTRUCTED REPRESENTATIVE. FINDING F1: no gap-area component originally owned measure evaluation; G6 parked, SDE forbidden from computing measures. Spine disposition assigns gap derivation inside G2 scope, explicitly not certified HEDIS; the owner escalation (G2 scope growth vs unparking a G6 slice) remains open per amendment §5.
6 | SDOH screening captured as coded data | G3 in-product screening path (stream), Gravity profiles (C4) | 13@T1, 18@T1 | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. Provenance-tagged patient-reported per §4A.
7 | Knowledge graph relates context; keystone barrier legible | G1 projector + query layer (ADR-001), DP-1 lenses; explicitly including the person-context projector and endpoint build (amendment §1); keystone ranking + hypothesis-edge lifecycle assigned to G1 (amendment §5, G1-d) | Graph MVR: 1,2@T1; 3,4@>=T3; 12,13,17@T1 | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. Five lens filters are the acceptance queries plus declared additions (around-event, household); D3 screen consumes real results. Keystone-legible claim marked covered at P2 only with the G1-d assignments in place (verdict item 12).
8 | Signals raised; SDE coordinates act/suppress/delay/bundle | G2 SDE (stream lane), C6 ordering, DP-2 policy-as-data; metrics projector build G1, feed events G3 (amendment §1); canonical intake topology per amendment adjudication (e) | SDE MVR: 1@T1, 3@T1 stream, 5-dispense@T1, 12,13,15@T1 | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. The 5 approved / 3 suppressed / 1 delayed / one coordinated touchpoint screen is the acceptance shape.
9 | Intelligent care plan generated, clinician-reviewed | G5 hardening + DP-4 oracle; work-queue reuse for review; persistence via internal-writer outbox (amendment adjudication f) | Care-plan MVR incl 9@>=T2 (contraindication honesty flag below T1) | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. Generator exists (1,262 lines, zero tests); hardening plus oracle is the build.
10 | Referral initiated; network adequacy consulted | G7 adequacy logic + O-6 shared provider model; G1 serves the provider-context endpoint; G3 referral path (components superseded by amendment §1) | 12@T1, 10@T1, 2@T1 | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. Adequacy engine is Tier A today; integration is the build. Language-concordance ranking is G7 logic served through G1's endpoint (amendment §1 boundary rule).
11 | Barrier remediation arranged (NEMT-class) | SDE touchpoint -> outreach/referral agents (G4, HITL), closed-loop referral platform path (G3) | 13@T1, 12@T1 | P2 propose; P3 close loop | RECONSTRUCTED REPRESENTATIVE. PARTIAL, FINDING F2: agents propose and track; the arrangement transaction has no owning component beyond referral-platform integration. Covered only where the platform closes the loop; direct booking remains T0, a recorded scope boundary. The SDE care-team-task fallback gives UC-34's tracked-human-task path.
12 | Prior authorization cleared through golden thread | goldenThread orchestrator + stages + DTR (Tier A), O-8 stage-3 deepening (G4), PA persisted to record (C9 #17 via internal-writer outbox) | 17@T1, 16@T1 | P1 (engine real; record-persist); P2 (O-8 journey lane) | RECONSTRUCTED REPRESENTATIVE. Covered. Strongest existing Tier-A chain.
13 | Care delivered; results flow back; loop closure | G3 ADT stream + QE CCD path (the golden path itself), evidence ledger | 3@T1, 6@partial T1, 12@T1 | P2 | RECONSTRUCTED REPRESENTATIVE. Covered. This step IS golden-path.md (A1c end to end).
14 | Agent coalition executes coordinated follow-up under HITL | G4 runtime (journey lane), DP-3 named agents, work-queue reuse, agent manifests (conventions §10) | Agents MVR: 11,12,15,17@T1 | P2 first agents; P3 coalition breadth | RECONSTRUCTED REPRESENTATIVE. Covered. Three named agents only; coalition breadth beyond them is P3 scope.
15 | Outcomes measured; attribution and milestone evidence | Gap-derivation/measure engine (F1, G2 scope) + ADR-005 evidence chain + graph temporality; metrics projector build G1, feed events G3 (amendment §1) | 6@T1, 16@T1, 11@T1 | P3 | RECONSTRUCTED REPRESENTATIVE. PARTIAL, FINDINGS F1/F3: measure improvement (the A1c beat) needs the F1 engine (spine disposition stands, owner escalation open); attribution evidence covered by the ledger; the UC-46 attribution/milestone packet is DEFERRED, named, parked alongside QARR with the O-5 pattern as template (amendment §5).
16 | Financial reconciliation; golden thread ties intent to payment; program reporting | goldenThread + 835 path (G3) + ADR-005 ledger; QARR-class reporting (unowned); UC-43 discrepancy gate assigned to G3 (amendment §5) | 16@T1, 17@T1 | P1 chain; P3 reporting | RECONSTRUCTED REPRESENTATIVE. PARTIAL, FINDING F3: program reporting (QARR-class) has no owning component; parked with the O-5 generated-from-view-models pattern named as the eventual template. The thread-to-payment chain is covered. Binding interim rule (amendment §4): no population extract ships without the Part 2 egress-scrubbing library.

## Corpus 70
70-case TCOC verification corpus x design owner x supported-at-target verdict
ACE Production Gap Assessment. Governing plan v11, gates A-L approved 2026-08-21. Source: coalition run (spine, five specialists, adversarial verdict, amendment-001).
Id | Title | Family | Actor | Facets | Tcoc Lever | Acceptance | Design Owner | Supported At Target
UC-01 | Cross-source anchor at enrollment | A. Identity resolution | G3 stage-3 identity step | G3, X2, DP-7, C9 1@T1; match engine (Tier A) | Duplicate records drive redundant testing and missed history; anchoring prevents both. | The same member arriving via any two feeds yields exactly one memberId, with match score, rule path and decision persisted to the audit ledger. | Pipeline + FHIR pair (matchService over Tier-A engine) | yes
UC-02 | Possible-match steward resolution then merge | A. Identity resolution | Identity data steward | DP-7, C10, C6, G1 rebuild, ADR-005; C9 1@T1 | Unresolved duplicates fragment utilization history and inflate risk scores. | After merge, graph, SDE state and care plans reference only the surviving memberId; a lens query shows the unified journey; merge event and actor audited. | Pipeline pair (merge events) + all projector owners (rekey by replay) | yes
UC-03 | Wrong merge unmerged (twins) | A. Identity resolution | Identity data steward | DP-7, C10.2 rebuild rule, C9 1@T1, 19@T1 | Cross-contaminated records cause wrong-member interventions and liability. | Post-unmerge, no resource, signal, plan or graph node from source feeds of member A remains attached to member B, verified by source-attribution audit. | Pipeline pair: record-repair DAG under the DP-7 semantics extension (amendment-001 §4); projection rekey G1 | yes-with-amendment
UC-04 | Survivorship field conflict | A. Identity resolution | G3 stage-3 transform | DP-7, C9 1@T1, seam C3 | Bad addresses waste outreach spend and break NEMT dispatch. | Changing the survivorship ranking in config alters the golden view on reprojection with zero mutation of stored source facts. | Pipeline + FHIR pair (survivorship rules as data) | yes
UC-05 | Provider identity resolution | A. Identity resolution | Provider-directory pipeline (O-2) | DP-7, O-2, O-6, G7; C9 10@T1 | Ghost networks hide real adequacy gaps and misdirect referrals into failure. | One NPI resolves to one provider node regardless of feed count, and adequacy computations consume only resolved identities. | Pipeline + FHIR pair (O-2 loader, NPI survivorship) | yes
UC-06 | Re-entry identity continuity | A. Identity resolution | Enrollment pipeline | DP-7, G3; C9 1@T1, 2@T1, 14 per consent | Re-entry is a peak window for ED use and overdose; continuity of record is the cheapest prevention. | A re-enrollment with changed subscriber id but matching traits links to the prior record above threshold; the coverage gap is coverage.terminated then coverage.enrolled, never a new person. | Pipeline + FHIR pair (834 adapter; 60..90 band to steward review per amendment G3-b) | yes-with-amendment
UC-07 | Dual-eligible elder assembly | B. Record assembly | G3 batch lane | G3, X2, C9 3@T3, 5@T1 dispense, 16@T1 | Duals are the cost tail; unreconciled cross-payer views hide avoidable admissions. | Person-context returns medications with dispense-level T1 tier labels and claims-inferred entries marked T3, never conflated. | Pipeline + FHIR pair (claims, pharmacy, ADT adapters) | yes
UC-08 | CCD tier honesty | B. Record assembly | QE micro-batch path | G3 stage 3-4, C4, C9 4/5/6 partial T1, 20@T2 | Treating documents as computable data produces false gap closures and false assurance. | No CCD-derived datum surfaces at T1 unless it carried a code; the C1 response labels each section's tier and the D1 sheet-3 score counts T2 as T2. | Pipeline + FHIR pair (CCD/QE adapter) | yes
UC-09 | HMIS flat file for a homeless member | B. Record assembly | CBO SFTP flat-file path | G3 flat-file first-class (§4A), C9 13@T1 P3, 1@T1 | Housing instability predicts ED superutilization; visibility enables upstream spend. | A malformed row quarantines without failing the batch; a valid row yields an SDOHCC-profiled Condition with source provenance naming the HMIS feed. | Pipeline + FHIR pair (flat-file manifest engine, P3) | yes
UC-10 | ADT within the latency budget | B. Record assembly | Stream lane | G3 stream, C2, C6, DP-5; C9 3@T1 | Discharge follow-up within 48 hours is the single strongest readmission lever. | p95 ADT receipt to signal.raised <=60s at 10x pilot load, with per-member ordering preserved. | Pipeline + FHIR pair (ADT stream adapter) | yes
UC-11 | Member-reported data lands with provenance | B. Record assembly | Member via SMS questionnaire | G3 PGD stream, C9 18@T1; C4 QuestionnaireResponse | Cheap longitudinal signal replaces expensive outreach touchpoints. | provenance=patient-reported survives through projection so graph, SDE and care plan can weight it distinctly. | Pipeline + FHIR pair (screening/PGD path) | yes
UC-12 | Claims-shadow honesty in the read API | B. Record assembly | Care manager via C1 | C1, C9.4 MVRs, G5 data-limitation flag | Acting on lagged claims as if current-state clinical drives wrong interventions. | No C1 section renders without its tier label; the care plan generated from a T3-only record carries the data-limitation flag. | G1 (person-context projector and endpoint per amendment §1) + G5 flag logic | yes-with-amendment
UC-13 | Part 2 opt-in absent | C. Consent and Part 2 | G3 stage-3 labeling | §4A segmentation-at-transform, C10 bh.event restricted labels, C9 14, 15@T1 | Trust preserved keeps SUD members engaged; disclosure violations carry program-level penalty. | With opt-in absent, envelope inspection alone causes non-cleared projectors to drop the event, and no SDE signal references the SUD content. | Pipeline + FHIR pair (segmentation labeler) | yes
UC-14 | Consent revoked mid-journey | C. Consent and Part 2 | Member | C10 consent events, G2 DP-2 suppression, C1 read scoping | Consent violations end member relationships and invite audit findings. | Any read after the revocation's recordedAt excludes the revoked scope and the suppressed disposition names the consent policy that fired. | Agentic Systems Designer (immediate fold, act-time recheck) + C1 scoping | yes
UC-15 | Segmented data legitimately requested | C. Consent and Part 2 | Treating SUD provider | C1 consent enforcement, C9 15@T1, ADR-005 | Appropriate BH data access prevents contraindicated prescribing and duplicate assessment. | The identical request from a requestor without that consent scope returns the record with the segment omitted, not blanked; both accesses audited with correlation ids. | G1 (C1 serving, read-time evaluation) | yes
UC-16 | Provider-access opt-out | C. Consent and Part 2 | Provider portal request | Consent seam (C3 exemplar), C1, authz guard | Opt-out integrity is the floor of member trust in data sharing. | isOptedOut=true yields 403 with no PHI in the response and an attributed audit event. | Existing Tier-A consent seam + G1 C1 route | yes
UC-17 | Re-disclosure blocked in reporting | C. Consent and Part 2 | Quality-reporting analyst | F3 reporting path, C9 14, C8 compliance audience | One re-disclosure incident outweighs years of reporting efficiency gains. | A generated extract for a mixed population contains zero Part 2-labeled data elements, proven by an automated label scan in the report test suite. | Pipeline + FHIR pair: egress-scrubbing library (amendment §4; binding interim rule: no population extract ships without it) | yes-with-amendment
UC-18 | Keystone barrier legibility | D. Graph and keystone reasoning | Care manager via lens query | G1, DP-1 rules 2-3, C9 13@T1, 4@>=T3 | One barrier fix closes multiple gaps; keystone targeting maximizes yield per intervention dollar. | The lens query returns the barrier ranked first with each causal edge citing its asserting source, and removing the barrier assertion demotes it on requery. | Graph & Context Architect (keystone ranking as query-layer capability, weights as data; amendment §5 G1-d) | yes-with-amendment
UC-19 | Temporal journey reconstruction | D. Graph and keystone reasoning | Clinician reviewing an ED visit | DP-1 temporality, G1, C10 event catalog breadth | Understanding the causal run-up converts reactive ED spend into preventable-pattern insight. | The around-event query returns time-ordered related events across at least four C9 domains with p95 <=2s. | Graph & Context Architect (around-event time-window query joins the lens set; amendment §5) | yes-with-amendment
UC-20 | Graph rebuild after merge | D. Graph and keystone reasoning | G1 projector | C10.2 rebuild, DP-7, ADR-001 seam | A graph that drifts from the record produces confidently wrong coordination. | Post-rebuild lens results are identical to a from-scratch projection of the merged record, verified by automated diff. | Graph & Context Architect (rekey-by-replay, rebuild proof suite) | yes
UC-21 | Hypothesis edge governance | D. Graph and keystone reasoning | G4 agent | DP-1 rule 2, G4 HITL, C10 | Unvalidated inferences steering outreach waste touchpoints and erode clinician trust. | Hypothesis edges are visually and queryably distinct, and the keystone lens excludes them unless the caller opts in. | Graph & Context Architect (hypothesis confirm/reject lifecycle, work-queue review surface; amendment §5 G1-d) | yes-with-amendment
UC-22 | Coordinated bundle for a BH-primary member | E. Signal disposition | G2 SDE | G2, DP-2 acceptance shape, C6 ordering, C9 SDE MVR | Fragmented contact drives disengagement; engagement is the multiplier on every other lever. | The batch yields exactly one touchpoint whose disposition record enumerates every input signal with its decision and the policy that fired. | Agentic Systems Designer (disposition engine fold) | yes
UC-23 | Fatigue suppression | E. Signal disposition | G2 SDE | DP-2 policy-as-data, C9 15@T1 | Over-contacted members opt out; each burned channel raises future engagement cost. | The suppression record names the cap policy and version, and the signal re-enters candidacy when the window reopens. | Agentic Systems Designer (policy packs as versioned data) | yes
UC-24 | Conflicting signals resolved by priority | E. Signal disposition | G2 SDE | DP-2, journey-lane timers (X1), C9 3@T1 stream | Post-discharge contact timing is worth more than any other single touchpoint. | The urgent signal dispatches within its budget while the delayed one carries a scheduled window and executes exactly once. | Agentic Systems Designer (priority scoring, immediate fold) | yes
UC-25 | Disposition policy tuned without deploy | E. Signal disposition | State program administrator | DP-2 data-not-code, conventions adapter pattern | State-tunable policy converts a change request from an engineering cost to a configuration action. | Dispositions before and after the change cite different policy versions in their audit records, with zero deployment events between. | Agentic Systems Designer (sde-policy-store seam, attributed publish) | yes
UC-26 | Out-of-order redelivery handled | E. Signal disposition | Stream consumers | C6, C10.2, C2 sequence | Ordering bugs generate wrong outreach that costs trust and rework. | Injected duplicate and late events at 10x load produce zero duplicate touchpoints and zero state regressions in a chaos test. | Agentic Systems Designer (intake dedupe) + Pipeline pair (relay ordering per amendment §2) | yes
UC-27 | Contraindication blocks an intervention | F. Care planning | G5 generator | DP-4 invariant 2, C9 9@T1, C4 | Adverse events are the most expensive preventable claims class. | Golden-fixture regression shows no generated plan ever contains an intervention contradicting an active coded contraindication. | Care Plan pair (contraindication gate at 9@T1) | yes
UC-28 | Polypharmacy in a dual-eligible elder | F. Care planning | G5 with pharmacist lens | G5, C9 5@T1 dispense, O-7 content, DP-4 | Polypharmacy drives falls and admissions in the dual population. | A fixture with a known interaction pair yields a plan containing a medication-review intervention citing its source, flagged not-SME-reviewed until GB-3. | Care Plan pair; SP1 must state whether common-pair rules fit the class-rule set or UC-28 is a labeled scope boundary (verdict G5-a, unresolved) | gap
UC-29 | Pregnancy plan with barriers addressed | F. Care planning | G5 | DP-4 invariants 1 and 4, C9 13@T1, 4@T1 | Prenatal SDOH remediation is the highest-ROI window in Medicaid. | Every barrier in context appears in the plan as addressed or as an explicit deferral with reason; no orphan goals exist. | Care Plan pair (barrierPlanner, invariants P1/P4) | yes
UC-30 | Caregiver-involved pediatric plan | F. Care planning | G5 plus caregiver | C9 19@T1, C4 RelatedPerson/Task, G5 | Caregiver activation is the delivery mechanism for pediatric adherence. | Generated Tasks carry the caregiver as performer where designated, and removal of the RelatedPerson link reroutes tasks without regenerating the plan. | Care Plan pair (task rerouting posture per G5-b, carried finding) | yes
UC-31 | Data-limitation honesty flag | F. Care planning | G5 | C9.4 honesty note, DP-4, C5 demo-green | False safety assurance is costlier than admitted uncertainty. | Any plan generated below 9@T1 renders the limitation flag in the review surface and cannot activate without a recorded human approval. | Care Plan pair (contextAdapter never upgrades tiers; activation always HITL). Verdict: COVERED | yes
UC-32 | Specialist desert with telehealth fallback | G. Referrals and network adequacy | G7 adequacy engine | G7, DP-6, O-6, C9 10@T1, 12@T1 | Unfilled specialist referrals resurface as ED visits and progression cost. | The referral candidate list marks each option with the adequacy standard it satisfies, and threshold config changes alter results without deploy. | G7 adequacy logic (Tier-A engine + thresholds as data) | yes
UC-33 | Closed-loop referral failure escalates | G. Referrals and network adequacy | Referral coordination agent | C10 referral events, G2, G4 DP-3 agent 2, O-8 pattern | Silent referral death is the largest leak in coordination programs. | No referral remains in initiated state past its SLA without a stall event, a disposition and a queue item, verified by an aging report of zero silent expiries. | Agentic Systems Designer (referral agent; stall topology per amendment adjudication e) | yes
UC-34 | Remediation booking boundary (F2) | G. Referrals and network adequacy | Outreach agent plus human coordinator | F2 scope boundary, G3 referral-platform path, G4 HITL, C9 12@T1, 13@T1 | A missed ride wastes the appointment, the auth and the provider slot simultaneously. | Every remediation need terminates in either a platform-confirmed booking or an open human task with SLA; zero needs reach a terminal state of untracked. | G4 agents + G3 platform path; SDE care-team-task touchpoints give the tracked-human-task fallback (verdict S7: F2 boundary workable) | yes
UC-35 | Provider-context join in one call | G. Referrals and network adequacy | Care manager | C1, O-6, G7, DP-7 provider identity, C9 2/10/12@T1 | Pre-joined referral intelligence collapses days of coordination into one decision. | The endpoint returns candidates with adequacy standing and PA posture populated, p95 <=300ms. | G1 serves the provider-context endpoint; G7 supplies ranking logic as a shared view-model (amendment §1) | yes-with-amendment
UC-36 | Language-concordant referral for an LEP member | G. Referrals and network adequacy | G7 filtered by member preference | G7, C9 1@T1 preference, 10@T1, member-experience lens | Language-discordant care lowers adherence and raises repeat utilization. | For a member with a recorded language preference, concordant providers rank above non-concordant peers under equal adequacy standing, verified by fixture. | G7 adequacy logic per DP-6, delivered as a shared view-model served by G1's endpoint (amendment §1) | yes-with-amendment
UC-37 | CBO housing referral closes the loop | G. Referrals and network adequacy | Closed-loop platform webhook | G3 webhook path, C10 sdoh.barrier.resolved, G1, G2 | Proven barrier closure is what converts SDOH spend from cost to investment. | Barrier resolution propagates to graph and SDE within the stream budget and the member's keystone ranking recomputes. | Pipeline pair (webhook path) + G1 (edge closure, ranking) + G2 (disposition) | yes
UC-38 | Standard PA through the golden thread | H. Prior auth and gold carding | goldenThread orchestrator | goldenThread (Tier A), C9 17@T1, C4 Da Vinci, ADR-005 | Clean first-pass PA eliminates rework and delayed-care cost. | The approved PA exists as record resources with Provenance and appears in person-context without any mock source. | goldenThread (Tier A) + Pipeline pair (PA-lifecycle persistence via internal-writer outbox, adjudication f) | yes
UC-39 | Gold card earned from real feeds | H. Prior auth and gold carding | Payer UM analyst | O-2, C10 pa events, goldenThread gold-card path | Gold carding removes admin cost from the highest-trust segment of utilization. | A submission from a gold-carded provider approves without manual review, and threshold-crossing in either direction changes the path on the next submission without deploy. | Pipeline pair (O-2 denial-rate and roster feeds) + goldenThread gold-card path | yes
UC-40 | Denial then successful appeal | H. Prior auth and gold carding | Appeals coordinator | ADR-005, C10, golden thread, C9 17@T1 | Appeal cycle time is pure admin cost; evidence reuse collapses it. | The appeal packet is generated from ledger entries alone (no manual re-collection) and post-overturn state shows denial and reversal as distinct audited events. | Pipeline pair (O-1 ledger) + G4 PA agent (appeal packet proposal) | yes
UC-41 | Agent-driven stage-3 PA | H. Prior auth and gold carding | PA/documentation agent (DP-3 agent 3) | O-8, G4, DP-3 reuse rule, journey lane X1 | PA labor is the largest automatable admin block in UM. | The agent completes the flow with every mutation human-approved through the existing inbox (no second inbox exists) and the full action chain audited. | Agentic Systems Designer (PA agent wrapping paMachine) | yes
UC-42 | Intent-to-payment chain complete | I. Golden thread financial | Golden thread | C9 16@T1, 17@T1, G3 835 path, ADR-005 | A provable thread is what converts care coordination from asserted value to auditable value. | Given a paid claim, a single query reconstructs the complete chain with every link carrying its evidence reference. | Pipeline pair (835 path, ledger) + goldenThread | yes
UC-43 | Payment contradicts authorization | I. Golden thread financial | Payment-integrity analyst | G3 835, golden thread, C10 claim events | Approved-then-denied leakage is recoverable revenue and provider-abrasion cost. | Every PA-approved service with a non-matching adjudication generates a flagged discrepancy item within one reconciliation cycle. | Pipeline pair: discrepancy gate joining pa.* against adjudication outcomes, alarmed (amendment §5, assigned) | yes-with-amendment
UC-44 | Appeal outcome re-reconciled | I. Golden thread financial | Golden thread ledger | ADR-005 append-only, C10 payment.posted | Clean audit history removes recoupment-dispute cost. | No ledger entry is ever mutated; the reconstructed timeline shows all three states in order with actors. | Pipeline pair (O-1 append-only ledger) | yes
UC-45 | Duplicate claim detection | I. Golden thread financial | Payment-integrity analyst | C2 idempotencyKey, G3 stage 2, C9 16@T1 | Duplicate payment is direct dollar loss plus recovery cost. | A resubmitted identical claim produces one financial fact and one flagged duplicate, never two payments. | Pipeline pair: claim-identity-scoped dedupe (payer claim id + adjustment sequence) at stage 3 (amendment §5 G3-c) | yes-with-amendment
UC-46 | Outcome attribution evidence | I. Golden thread financial | Program evaluator | ADR-005, DP-1 temporality, C9 6@T1, 11@T1, F1-adjacent | Attribution evidence is what sustains program funding and value-based payment. | The milestone packet links outcome observation to preceding plan interventions through dated evidence, generated without manual assembly. | Unowned; DEFERRED and named (amendment §5): parked alongside QARR with the O-5 generated-from-view-models pattern as template; ledger and graph primitives exist | deferred
UC-47 | Outreach agent proposes, human disposes | J. Agents and HITL | Outreach agent (DP-3 agent 1) | G4, DP-3 reuse rule, C10 touchpoint.executed | Agent-drafted outreach multiplies coordinator caseload capacity. | No member-facing action executes without a recorded human approval, and the queue is the same component the PA flow uses. | Agentic Systems Designer (outreach agent, inbox reuse) | yes
UC-48 | HITL escalation ladder | J. Agents and HITL | Agent runtime | DP-3 escalation defaults, conventions §10 manifests | Silent expiry converts near-miss coordination into missed care. | A fixture item aged past SLA shows escalation events at each rung and a parked terminal state; zero items reach deletion without audit. | Agentic Systems Designer; ladders are role-rank config over care-team membership, degraded P1 posture ratified (amendment adjudication a) | yes
UC-49 | Autonomy promotion by configuration | J. Agents and HITL | Operations owner | DP-3 autonomy dial, AI guardrail 3 | Graduated autonomy captures labor savings without surrendering governance. | Post-promotion, reminder-class actions execute without queue gating while all other classes still require approval, with the manifest change itself audited. | Agentic Systems Designer (manifest registry, deployment overlay) | yes
UC-50 | PHI-safe model calls | J. Agents and HITL | Any agent with LLM narration | AI guardrail 4, conventions §10, DP-2 explainability | A PHI leak in a model call is breach cost plus program credibility. | An automated assertion over captured model-call payloads finds zero free-text clinical narrative and zero direct identifiers. | Agentic Systems Designer (eval suites, PHI-leak assertions; narration gated on GB-2) | yes
UC-51 | Graceful degradation without the LLM | J. Agents and HITL | Agent runtime | AI guardrail 6, Tier-A/B honesty, X1 | Resilience keeps the labor-saving core running through vendor outages. | With the model endpoint down, all deterministic acceptance tests still pass and degraded surfaces state their condition honestly. | Agentic Systems Designer (deterministic template path as the product) | yes
UC-52 | Gap derivation as a named projector (F1) | K. Dashboards and measures | Measure/gap projector (assigned inside G2 scope per spine disposition) | F1, C10 care-gap events, DP-2 role separation, C9 6@T1 | Computable gap status is the substrate of every quality-revenue lever. | Gap events are emitted by a projector distinct from disposition logic, rebuild from replay, and the not-certified boundary is documented on the surface. | Agentic Systems Designer (gapDerivation domain); owner escalation on G2 scope growth remains open (amendment §5). Verdict: COVERED | yes
UC-53 | Gap closure to dashboard within budget | K. Dashboards and measures | Quality manager | O-3 pattern, G6 lesson, DP-5 1s read budget | Current gap status directs outreach spend to still-open gaps only. | Dashboard view-model read p95 <=1s and the number shown equals the projector's count exactly (one source of truth). | G1 (metrics projector build per amendment §1) + G3 (feed events) | yes-with-amendment
UC-54 | QARR-class report generated (F3) | K. Dashboards and measures | Quality-reporting analyst | F3, O-5 pattern, C8 compliance audience, C9 16@T1 | Reporting integrity protects quality withhold dollars and avoids resubmission cost. | For any shared measure, the report value and the dashboard value derive from one view-model, proven by a consistency test, with the F3 parked-scope boundary labeled. | Unowned; F3 parked with the O-5 pattern named as template; X4 carries the boundary label; interim exposure bounded by the amendment §4 scrubbing rule | deferred
UC-55 | County drill-down for a rural program officer | K. Dashboards and measures | State program officer | O-3, O-4, G7, X5 accessibility | County-level targeting is how rural transformation dollars get allocated. | Drill-down renders from view-models with no inline aggregation and passes axe-core checks per O-9. | G1 (view-model registry, metrics projector per amendment §1) + G7 + Pipeline pair feeds | yes-with-amendment
UC-56 | Quarantine and remediation | L. Operational | Pipeline operator (SRE) | §4A stage 2, DP-5 quarantine TTL, D7 runbooks | Silently vanished records become missed gaps and phantom completeness. | Counts satisfy in = loaded + rejected per batch; every quarantined record reaches resolved or alarmed-expiry, never silent deletion. | Pipeline + FHIR pair (staging, quarantine, remediation workflow) | yes
UC-57 | Reconciliation gate blocks a bad load | L. Operational | Batch lane | §4A stages 1 and 4, C6 replay, idempotent upsert | Partial loads corrupt adherence signals and the interventions built on them. | Replay of a corrected batch yields exact target counts with zero duplicates, verified by resource-level reconciliation. | Pipeline + FHIR pair (reconciliation engine, dag-replay) | yes
UC-58 | DLQ replay after a poison event | L. Operational | SRE | C6 DLQ contract, C10.2 idempotency, D7 replay runbook | Consumer outages that require manual data surgery are the expensive kind. | Post-replay, projector state matches a clean-run baseline and no consumer processed the event twice. | Pipeline pair (relay, DLQ tooling) + projector owners (idempotent consumers) | yes
UC-59 | Annual enrollment surge | L. Operational | X1 substrate | DP-5 budgets, C6 traffic classes, load gates 1K/5K/10K per min | Surge failures during enrollment are member-facing at the worst moment. | At the 5K/min burst gate, stream p95 budgets hold and the 834 completes inside budget, demonstrated in the D4 k6 scenario. | Spine X1 (traffic classes, gates) + Pipeline pair (window budgets) | yes
UC-60 | Projector store rebuilt from offset zero | L. Operational | SRE | C10.2 rebuild, C6 replay, C5 dual-mode | Rebuildability turns a data-store disaster into a routine operation. | Rebuild completes within the documented window and post-rebuild lens results diff clean against record-derived truth. | Graph & Context Architect (rebuild harness); full rebuild streams from the outbox table through a rebuild publisher (amendment §3) | yes
UC-61 | Purpose-scoped projection | M. Privacy and security | Operations staff via C1 | C1 consent enforcement, authz guard (Tier A), ADR-005 | Minimum-necessary discipline is the audit-penalty firewall. | The operations-purpose response contains no clinical sections and the audit ledger shows the access with purpose recorded. | G1 (person-context endpoint build per amendment §1) over the Tier-A authz guard | yes-with-amendment
UC-62 | Full access-trail reconstruction | M. Privacy and security | Compliance auditor | ADR-005, GB-7 consumer, C8 compliance docs | Audit readiness converts regulator interactions from crisis to routine. | The trail query returns a complete, chronologically ordered access history whose completeness is proven by injecting known accesses in test. | Pipeline pair (O-1 ledger) + every read surface emitting audit events | yes
UC-63 | BFF invariant holds | M. Privacy and security | Adversarial client | BFF-only invariant, D4 absorbed test plan, X5 | Perimeter integrity is the precondition of every other privacy claim. | The D4 route-test suite passes on every BFF route and a repo scan finds zero secret-bearing NEXT_PUBLIC variables. | All specialists (invariant on every new surface); D4 route matrix suite | yes
UC-64 | Part 2 emergency access (break-glass) | M. Privacy and security | ED clinician | C1 read-time evaluation, C9 14/15, ADR-005 | Emergency-blind records cause contraindicated treatment; ungoverned break-glass causes violations; both are expensive. | Emergency access requires a recorded invoking actor and reason, expires by policy, and appears in a dedicated audit report for review. | Spine C1 contract + G1 build + authz extension (amendment §4): emergency-treatment purpose, 4h token, policy matrix as data, break-glass audit class, post-hoc review item; feature-flagged, disabled by default | yes-with-amendment
UC-65 | Household keystone resolved once | N. Household and pediatric-adjacent | Care coordinator | C9 1 household, 19@T1, G1, DP-1, F2 boundary | Household-level remediation triples the yield of one intervention. | The household lens surfaces the shared barrier across member subgraphs and one resolution event closes the related edge on each. | Graph & Context Architect (household lens added as the stated exception to per-lens partition scope; amendment §5) | yes-with-amendment
UC-66 | Caregiver-reported screening | N. Household and pediatric-adjacent | Pediatric caregiver | G3 screening path, C9 18@T1, 19@T1, C4 | Caregiver-sourced SDOH data is the only screening path for young children. | Provenance distinguishes reporter from subject and the caregiver link is queryable from the child's person-context. | Pipeline pair (screening path with reporter provenance) | yes
UC-67 | Adolescent confidential services shielded | N. Household and pediatric-adjacent | Consent engine | C9 15@T1 segmentation, C1 purpose scoping | Confidentiality failures end adolescent engagement with care entirely. | The same record read under three requestor contexts (proxy, member, clinician) returns three correctly scoped projections, each audited. | Spine C1 (member/proxy requestor classes added additively, amendment §5) + G3 label machinery; minor-consent rule-set CONTENT deferred to owner plus compliance input | deferred
UC-68 | Newborn onto the household record | N. Household and pediatric-adjacent | Enrollment pipeline | DP-7 (new identity, not a merge), C10 household events, G5 | First-year well-child adherence sets the lifetime utilization trajectory. | The newborn record exists with the household link inside the enrollment cycle and no clinical content from the mother's record attaches to the child. | Pipeline pair (834 dependent linkage pulled into P1 per amendment §5 S6) + Care Plan pair (plan-initiation trigger posture, carried finding G5-b) | yes-with-amendment
UC-69 | Winter distance barrier reshapes the plan | O. Rural-specific | G2 plus G7 | DP-2 delay, G7 telehealth, DP-6 configurable thresholds, F2 | Winter no-shows in rural counties waste slots and cascade into exacerbation admissions. | The rescheduling disposition records the barrier-informed reason and the substituted modality satisfies the applicable adequacy standard. | Agentic Systems Designer (delay dispositions) + G7 (telehealth substitution, thresholds as data) | yes
UC-70 | Broadband-poor engagement path | O. Rural-specific | G2 channel policy | DP-2 policy-as-data, C9 13@T1 digital-access barrier, member experience | Unreachable members accrue silent gaps until they arrive by ambulance. | Channel fallback follows the configured ladder with each attempt and outcome audited, and no member is marked unreachable while ladder rungs remain untried. | Agentic Systems Designer (channel-preference ladder as policy data) | yes