## Dev Plan — Gap Closure
Development Plan — Closing Gaps to Full Functional Compliance (Progress Update)
Status as of August 7, 2026: 14 of 28 tasks complete and verified (code written, automated tests passing), 1 partially complete, 13 not started. Workstreams A (MPI identity resolution + Provider Access opt-out consent), B (DTR CDex conformance), and E (risk-flag remediation) are fully done. Remaining scope: C, D, F (partial), G, H. Certification path/timeline (other tabs) is unchanged by this update. Rates from the same standard rate card used throughout this workbook.
Status Key
Done | Code written, automated tests passing, verified this session. (14 tasks)
Partial | Meaningful progress made; scope not fully closed. (1 task)
Remaining | Not yet started. (13 tasks)
AI Feasibility Categories
Full Automation | Claude can build/test the feature end-to-end with only light human review.
AI-Assisted | Claude materially speeds up the work, but a human must still decide, validate against real data, or coordinate externally.
Human-Required | Inherently human: business/architecture decisions, external coordination.
Task-Level Plan (Status + Remaining Cost)
ID | Workstream | Task | Owner Role | AI Feasibility | Status | Remaining Days (No AI) | Remaining Days (With AI) | Remaining Cost (No AI, $) | Remaining Cost (With AI, $) | Remaining Savings ($)
A1 | A — Identity Resolution (MPI) | Design cross-source identity-resolution (MPI) matching approach | Tech Lead | AI-Assisted | Done | 0 | 0 | 0 | 0 | 0
A2 | A — Identity Resolution (MPI) | Build MPI matching engine (deterministic + probabilistic rules) | Data/Integration Engineer | AI-Assisted | Done | 0 | 0 | 0 | 0 | 0
A3 | A — Identity Resolution (MPI) | Integrate MPI layer with existing $member-match + audit trail | Backend/FHIR Engineer 1 | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A4 | A — Identity Resolution (MPI) | MPI automated test suite | QA Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A5 | A — Identity Resolution (MPI) | Decide MPI integration mode (HCA's existing MPI vs. standalone) | Product/Clinical SME | Human-Required | Remaining | 2 | 1.5 | 2600 | 1950 | 650
A6 | A — Identity Resolution (MPI) | Build MPI integration-mode adapter layer | Data/Integration Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A7 | A — Provider Access Opt-Out Consent | Build consent capture UI for Provider Access opt-out | Frontend Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A8 | A — Provider Access Opt-Out Consent | Integrate consent gate into canReadMemberData() authorization check | Backend/FHIR Engineer 2 | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A9 | A — Provider Access Opt-Out Consent | Build consent revocation flow | Backend/FHIR Engineer 2 | Full Automation | Done | 0 | 0 | 0 | 0 | 0
A10 | A — Provider Access Opt-Out Consent | Consent flow automated test suite | QA Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
B1 | B — DTR CDex Conformance | Implement CDex-conformant DocumentReference construction (replace plain file upload) | Backend/FHIR Engineer 1 | Full Automation | Done | 0 | 0 | 0 | 0 | 0
B2 | B — DTR CDex Conformance | CDex DocumentReference conformance tests | QA Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
C1 | C — Provider Access Bulk Export Hardening | Exercise SMART Backend Services bulk export end-to-end against staging | Backend/FHIR Engineer 2 | AI-Assisted | Remaining | 5 | 2.5 | 5500 | 2750 | 2750
C2 | C — Provider Access Bulk Export Hardening | Volume/load testing for 5-year look-back scoped exports | QA Engineer | Full Automation | Remaining | 3 | 1 | 2700 | 900 | 1800
C3 | C — Provider Access Bulk Export Hardening | Add monitoring/alerting hooks for bulk export jobs | Backend/FHIR Engineer 2 | Full Automation | Remaining | 2 | 0.5 | 2200 | 550 | 1650
D1 | D — Policy Monitoring Mode | Build policy-library change watcher | Data/Integration Engineer | Full Automation | Remaining | 5 | 1.5 | 5500 | 1650 | 3850
D2 | D — Policy Monitoring Mode | Build proposed-update workflow (structured-resource diffs for human approval) | Backend/FHIR Engineer 1 | Full Automation | Remaining | 4 | 1 | 4400 | 1100 | 3300
D3 | D — Policy Monitoring Mode | Build human-approval UI for proposed policy updates | Frontend Engineer | Full Automation | Remaining | 4 | 1 | 4000 | 1000 | 3000
D4 | D — Policy Monitoring Mode | Policy monitoring automated test suite | QA Engineer | Full Automation | Remaining | 3 | 1 | 2700 | 900 | 1800
E1 | E — Risk-Flag Remediation | Fix "Propensity-to-deny" UI copy across 4 screens to "submission-readiness (completeness) score" | Frontend Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
E2 | E — Risk-Flag Remediation | Scope & exclude unrelated client modules (uhg-orchestrate, md-smart-launch) from any HCA-facing build | Tech Lead | AI-Assisted | Done | 0 | 0 | 0 | 0 | 0
E3 | E — Risk-Flag Remediation | Restore missing Postman contract-test collection referenced by test:contract script | QA Engineer | Full Automation | Done | 0 | 0 | 0 | 0 | 0
F1 | F — Test Coverage Hardening | Expand PA-Standalone-SmartApp test suite (was 1 test) to match main-app rigor | QA Engineer | Full Automation | Partial | 3.5 | 1 | 3150 | 900 | 2250
G1 | G — Environment & Cutover Readiness | Live backbone staging integration — engineering | Backend/FHIR Engineer 1 | AI-Assisted | Remaining | 6 | 3.5 | 6600 | 3850 | 2750
G2 | G — Environment & Cutover Readiness | Live backbone staging integration — data mapping | Data/Integration Engineer | AI-Assisted | Remaining | 4 | 2 | 4400 | 2200 | 2200
G3 | G — Environment & Cutover Readiness | End-to-end Golden Thread regression pass after all gap-closure changes | QA Engineer | Full Automation | Remaining | 4 | 1 | 3600 | 900 | 2700
H1 | H — Documentation & Evidence Refresh | Update conformance-plan.md and internal docs to reflect closed gaps | Tech Lead | Full Automation | Remaining | 2 | 0.5 | 2900 | 725 | 2175
H2 | H — Documentation & Evidence Refresh | Regenerate RFI evidence citations for a V5 pass | Tech Lead | Full Automation | Remaining | 2 | 0.5 | 2900 | 725 | 2175
What Shipped / What's Left, by Task
ID | Evidence
A1 | Shipped: deterministic-then-probabilistic design implemented in lib/identity/matchEngine.ts.
A2 | Shipped: lib/identity/matchEngine.ts — exact-ID/name+DOB deterministic rules + weighted (name/DOB/sex/zip/phone) probabilistic scoring. 13 tests passing.
A3 | Shipped: lib/identity/resolveIdentity.ts + lib/server/identityResolution.ts — cross-source resolution, PHI-safe audit events. 8 tests passing.
A4 | Shipped: 21 automated tests across matchEngine.test.ts, resolveIdentity.test.ts, resolveIdentityWithAudit.test.ts.
A5 | Not yet decided — awaiting joint decision with HCA. Blocks final wiring of the mode-specific adapter, not the adapter interface itself.
A6 | Shipped: lib/identity/identitySource.ts — adapter interface + mock implementation, swappable for a real production source once A5 is decided.
A7 | Shipped: consent capture + amber warning block in provider-access page.
A8 | Shipped: providerAccessOptedOut check wired into src/lib/authz/guard.ts (break-glass still overrides, as required).
A9 | Shipped: GET/POST /api/consent/provider-access + ProviderAccessConsentStore.
A10 | Shipped: 8 tests (3 in guard.test.ts + 5 in providerAccessOptOut.test.ts).
B1 | Shipped: PA-Standalone-SmartApp/src/lib/dtr/cdexDocumentReference.ts, wired into the DTR upload flow. This clears the one hard blocker to DTR conformance testing.
B2 | Shipped: 6 tests in cdexDocumentReference.test.ts.
C1 | Not started.
C2 | Not started.
C3 | Not started.
D1 | Not started.
D2 | Not started.
D3 | Not started.
D4 | Not started.
E1 | Shipped: copy corrected in MedicalNecessityPanel, EvidenceTimeline, financial-clearance page (3 spots), work-queue page.
E2 | Shipped: src/middleware.ts scope-gates non-CMS-0057-F routes behind DEPLOYMENT_SCOPE env var. 4 tests passing.
E3 | Shipped: tools/contract/cms0057f.postman_collection.json (8 requests) + local environment file; newman added to package.json.
F1 | Partial: suite grew 1 -> 7 tests (CDex module fully covered). Remaining: OrderView, CrdChecklistView, ReviewSubmitView, PaPortalView, WorklistView, CaseDetailView still need coverage.
G1 | Not started.
G2 | Not started.
G3 | Not started. (Baseline already re-verified once this session: 146 -> 185 tests passing, zero regressions, as Workstreams A/B/E landed.)
H1 | Not started.
H2 | Not started.
Remaining Dev Plan Cost (Go-Forward, as of Aug 7, 2026)
| Without AI | With AI | Savings | Savings %
Remaining Development Labor | 53150 | 20100 | 33050 | 62.18%
Incremental Infrastructure / Third-Party Cost | 0 | 0 | 0 | —
Assumes existing staging/reference environment already budgeted in Prior_Auth_Cost_Model V2.0.xlsx; no incremental hosting cost assumed.
REMAINING DEV PLAN TOTAL | 53150 | 20100 | 33050 | 62.18%
Delivered to Date (Original Full-Scope Total Minus Remaining)
| Without AI basis | With AI basis
Value Delivered This Session | 57850 | 20175
Baseline: original full-scope Dev Plan totaled $111,000 (No AI) / $40,275 (With AI) across all 28 tasks. This session closed Workstreams A, B, and E in full (14 tasks) plus partial progress on F1, using AI-assisted development end-to-end.
Task Count by Status (of 28 tasks)
Done | 14
Partial | 1
Remaining | 13
Combined Total to Reach Certification-Ready + Certified (Remaining Dev + Standards-Conformance Testing tabs)
| Without AI | With AI | Savings | Savings %
Combined Remaining Total | 234350 | 127850 | 106500 | 45.44%
Path to certification is unchanged (see Project Plan / Gantt Chart / Time & Cost Summary / AI Impact Analysis tabs) — those figures are not modified by this update. One planning note: Workstream B (the former hard blocker for clean Da Vinci DTR conformance testing) is now complete, so DTR conformance testing can proceed on its originally scheduled track with no code dependency outstanding. Remaining Dev Plan elapsed schedule: ~7 weeks — see Dev Plan Gantt tab.
All person-day estimates are illustrative planning-level judgments, not a delivery commitment. This tab covers development labor only — testing/certification fees are tracked separately in the Time & Cost Summary and AI Impact Analysis tabs. "Done" status reflects code written and automated tests passing in this engagement's working repository; it is not itself a certification or a production deployment.

## Dev Plan Gantt
Development Plan — Gantt Chart (Progress Update: 7-Week Remaining Schedule)
Completed tasks (green "DONE" bar) are shown for continuity but no longer consume schedule. Week numbers for remaining tasks are relative to a fresh kickoff of the go-forward plan (kickoff date TBD), not the original 11-week baseline. Bars colored by workstream; AI Feasibility: Green = Claude can execute end-to-end · Yellow = AI-assisted, human decides/validates · Red = inherently human.
ID | Task | Owner | AI Feasibility | Status | Dur (wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7
A — Identity Resolution (MPI)
A1 | Design cross-source identity-resolution (MPI) matching approach | Tech Lead | AI-Assisted | Done | — | ✓ DONE
A2 | Build MPI matching engine (deterministic + probabilistic rules) | Data/Integration Engineer | AI-Assisted | Done | — | ✓ DONE
A3 | Integrate MPI layer with existing $member-match + audit trail | Backend/FHIR Engineer 1 | Full Automation | Done | — | ✓ DONE
A4 | MPI automated test suite | QA Engineer | Full Automation | Done | — | ✓ DONE
A5 | Decide MPI integration mode (HCA's existing MPI vs. standalone) | Product/Clinical SME | Human-Required | Remaining | 1
A6 | Build MPI integration-mode adapter layer | Data/Integration Engineer | Full Automation | Done | — | ✓ DONE
A — Provider Access Opt-Out Consent
A7 | Build consent capture UI for Provider Access opt-out | Frontend Engineer | Full Automation | Done | — | ✓ DONE
A8 | Integrate consent gate into canReadMemberData() authorization check | Backend/FHIR Engineer 2 | Full Automation | Done | — | ✓ DONE
A9 | Build consent revocation flow | Backend/FHIR Engineer 2 | Full Automation | Done | — | ✓ DONE
A10 | Consent flow automated test suite | QA Engineer | Full Automation | Done | — | ✓ DONE
B — DTR CDex Conformance
B1 | Implement CDex-conformant DocumentReference construction (replace plain file upload) | Backend/FHIR Engineer 1 | Full Automation | Done | — | ✓ DONE
B2 | CDex DocumentReference conformance tests | QA Engineer | Full Automation | Done | — | ✓ DONE
C — Provider Access Bulk Export Hardening
C1 | Exercise SMART Backend Services bulk export end-to-end against staging | Backend/FHIR Engineer 2 | AI-Assisted | Remaining | 2
C2 | Volume/load testing for 5-year look-back scoped exports | QA Engineer | Full Automation | Remaining | 2
C3 | Add monitoring/alerting hooks for bulk export jobs | Backend/FHIR Engineer 2 | Full Automation | Remaining | 2
D — Policy Monitoring Mode
D1 | Build policy-library change watcher | Data/Integration Engineer | Full Automation | Remaining | 2
D2 | Build proposed-update workflow (structured-resource diffs for human approval) | Backend/FHIR Engineer 1 | Full Automation | Remaining | 2
D3 | Build human-approval UI for proposed policy updates | Frontend Engineer | Full Automation | Remaining | 2
D4 | Policy monitoring automated test suite | QA Engineer | Full Automation | Remaining | 2
E — Risk-Flag Remediation
E1 | Fix "Propensity-to-deny" UI copy across 4 screens to "submission-readiness (completeness) score" | Frontend Engineer | Full Automation | Done | — | ✓ DONE
E2 | Scope & exclude unrelated client modules (uhg-orchestrate, md-smart-launch) from any HCA-facing build | Tech Lead | AI-Assisted | Done | — | ✓ DONE
E3 | Restore missing Postman contract-test collection referenced by test:contract script | QA Engineer | Full Automation | Done | — | ✓ DONE
F — Test Coverage Hardening
F1 | Expand PA-Standalone-SmartApp test suite (was 1 test) to match main-app rigor | QA Engineer | Full Automation | Partial | 2
G — Environment & Cutover Readiness
G1 | Live backbone staging integration — engineering | Backend/FHIR Engineer 1 | AI-Assisted | Remaining | 3
G2 | Live backbone staging integration — data mapping | Data/Integration Engineer | AI-Assisted | Remaining | 3
G3 | End-to-end Golden Thread regression pass after all gap-closure changes | QA Engineer | Full Automation | Remaining | 2
H — Documentation & Evidence Refresh
H1 | Update conformance-plan.md and internal docs to reflect closed gaps | Tech Lead | Full Automation | Remaining | 1
H2 | Regenerate RFI evidence citations for a V5 pass | Tech Lead | Full Automation | Remaining | 1
Workstream Legend:
A — Identity Resolution (MPI)
A — Provider Access Opt-Out Consent
B — DTR CDex Conformance
C — Provider Access Bulk Export Hardening
D — Policy Monitoring Mode
E — Risk-Flag Remediation
F — Test Coverage Hardening
G — Environment & Cutover Readiness
H — Documentation & Evidence Refresh
AI Feasibility Legend:
Full Automation
AI-Assisted
Human-Required
Status Legend:
Done
Partial
Remaining

## Project Plan
Standards-Conformance Testing — Project Plan
CMS-0057-F prior-authorization platform — closing the Section 5.6 Testing Approach gap identified in the RFI code audit
Phase | Task ID | Task | Owner | Duration | Dependencies | Deliverable / Exit Criteria | Status
Phase 0 — Governance & Scoping (Week 1–2)
Phase 0 | 0.1 | Confirm target IG versions to test against (CRD 2.2.1, DTR 2.0.1, PAS 2.0.1, US Core 6.1.0/7.0.0, CARIN BB 2.0.0/2.1.0, SMART App Launch STU2.2) and lock scope | Solution Architect | 3 days | — | Signed-off conformance scope memo | Not started
Phase 0 | 0.2 | Stand up a dedicated conformance test environment pointed at the live/staging backbone (not the mock reference environment) using the existing config-based cutover | Platform Engineering | 1 week | 0.1 | isBackboneConfigured() = true in a stable staging tenancy | Not started
Phase 0 | 0.3 | Identify and engage one real or sandbox trading-partner payer/clearinghouse for X12 278/275 round-trip testing | Delivery Lead | 1–2 weeks | — | Signed trading-partner test agreement | Not started
Phase 0 | 0.4 | Assign an internal conformance owner per suite (CRD/DTR/PAS, US Core, CARIN BB, SMART, X12) accountable for pass/fail and remediation | Delivery Lead | 2 days | — | RACI published | Not started
Phase 1 — FHIR Conformance: Foundational IGs (Week 2–5, parallel)
Phase 1 | 1.1 | Run Inferno US Core Test Kit (server suite) against staging FHIR endpoints for Coverage, Condition, Claim/ClaimResponse, QuestionnaireResponse, Consent, Provenance | Platform Engineering | 1 week | 0.2 | Inferno results export — 0 required-test failures | Not started
Phase 1 | 1.2 | Run Inferno SMART App Launch Test Kit against the DTR SMART app's authorization flow | Platform Engineering | 3 days | 0.2 | Inferno results export — passing launch + token flows | Not started
Phase 1 | 1.3 | Run Inferno CARIN IG for Blue Button Test Kit against the Patient Access API server | Platform Engineering | 1 week | 0.2, 1.1 | Inferno results export — passing server suite | Not started
Phase 1 | 1.4 | Remediate and re-run any failing US Core / SMART / CARIN required tests | Platform Engineering | 1–2 weeks | 1.1–1.3 | Clean re-test with 0 required-test failures | Not started
Phase 2 — FHIR Conformance: Da Vinci Prior-Auth IGs (Week 4–8, parallel with Phase 1 tail)
Phase 2 | 2.1 | Run Inferno Da Vinci CRD Test Kit against the CDS Hooks order-select/order-sign services | Platform Engineering | 1–2 weeks | 0.2 | Inferno results export — passing CRD client/server suite | Not started
Phase 2 | 2.2 | Run Inferno Da Vinci DTR Test Kit against the DTR SMART app + Questionnaire Package retrieval | Platform Engineering | 1–2 weeks | 1.2, 0.2 | Inferno results export — passing DTR suite | Not started
Phase 2 | 2.3 | Run Inferno Da Vinci PAS Test Kit against PASBundle submission and status-update handling (note: ONC's PAS kit is published in draft/preliminary status — expect to log implementer feedback to HL7/ONC as part of this run) | Platform Engineering | 2 weeks | 0.2 | Inferno results export — passing PAS suite; feedback filed with ONC if gaps found in the kit itself | Not started
Phase 2 | 2.4 | Remediate and re-run any failing CRD / DTR / PAS required tests | Platform Engineering | 2–3 weeks | 2.1–2.3 | Clean re-test with 0 required-test failures | Not started
Phase 2 | 2.5 | (Optional, recommended) Register for an upcoming HL7 Da Vinci Connectathon track (CRD/DTR/PAS) to test interoperability against independent implementers, not just Inferno's simulated client/server | Solution Architect | 1 connectathon cycle (~1 week event + prep) | 2.4 | Published connectathon participation / track results | Not started
Phase 3 — X12 278/275 Conformance (Week 3–8, parallel)
Phase 3 | 3.1 | Execute X12 278 (request/response) transaction testing against the engaged trading partner per Phase 0.3, validating against the TR3 companion guide | Integration Engineering | 2–3 weeks | 0.3, 0.2 | Clean 278 request/response pairs, no syntax or balancing errors | Not started
Phase 3 | 3.2 | Execute X12 275 (attachment) transaction testing for DTR-equivalent documentation exchange over the EDI channel | Integration Engineering | 1–2 weeks | 3.1 | Clean 275 exchange validated by trading partner | Not started
Phase 3 | 3.3 | Validate conformance to CAQH CORE Prior Authorization & Referrals (278) Infrastructure Rule (vPA.3.0) and Data Content Rule (vPA.1.0) | Integration Engineering | 2 weeks | 3.1, 3.2 | Internal conformance checklist passed against both CORE rules | Not started
Phase 3 | 3.4 | Remediate and re-test any X12/CORE gaps | Integration Engineering | 1–2 weeks | 3.3 | Clean re-test | Not started
Phase 4 — Formal Certification Pursuit (Week 8–16, gated on Phases 1–3 passing)
Phase 4 | 4.1 | Legal/product review: determine which side of each Da Vinci transaction (provider-facing vs. payer-facing) the platform should certify under the new ONC §170.315(g)(31)/(g)(32)/(g)(33) Provider Prior Authorization API criteria, given the platform's role varies by provision | Product + Legal | 1–2 weeks | 2.4 | Written scoping decision on which components pursue ONC certification | Not started
Phase 4 | 4.2 | Engage an ONC-Authorized Certification Body (e.g., Drummond Group, SLI Compliance, or CCHIT/ICSA) for formal §170.315(g)(31)/(g)(32)/(g)(33) certification testing | Delivery Lead | 2–4 weeks (ACB-dependent) | 4.1 | Signed ONC-ACB testing engagement | Not started
Phase 4 | 4.3 | Complete ONC-ACB witnessed testing and remediation cycles | Platform Engineering | 4–6 weeks | 4.2 | ONC-ACB certification decision issued | Not started
Phase 4 | 4.4 | Confirm listing on the federal Certified Health IT Product List (CHPL) | Delivery Lead | 1 week (post-decision) | 4.3 | Public CHPL listing — verifiable by any evaluator, including HCA | Not started
Phase 4 | 4.5 | Pursue CAQH CORE Certification for the Prior Authorization & Referrals (278) Operating Rules through an approved CORE certification testing vendor | Integration Engineering | 4–6 weeks | 3.4 | CAQH CORE Certification Seal issued | Not started
Phase 4 | 4.6 | Sign the CARIN Alliance Code of Conduct for the Patient Access API and register on MyHealthApplication.com | Product + Legal | 1–2 weeks | 1.4 | Public listing under the CARIN Code of Conduct | Not started
Phase 5 — Publish & Report (Week 16–17)
Phase 5 | 5.1 | Compile a public-facing conformance summary (Inferno pass results, connectathon participation, CHPL listing, CAQH CORE seal, CARIN attestation) for use in proposals and demos | Delivery Lead | 3 days | 4.1–4.6 | Conformance & Certification one-pager | Not started
Phase 5 | 5.2 | Update the RFI/proposal Testing Approach section and internal conformance-plan.md to reflect completed (not planned) conformance status | Solution Architect | 2 days | 5.1 | Updated response language, code-evidence-accurate | Not started
Phase 5 | 5.3 | Establish a recurring re-test cadence (e.g., on each IG version bump or annually) to keep conformance evidence current | Delivery Lead | 2 days | 5.1 | Documented re-test schedule | Not started

## Certifications & Recognition
Certification & Recognition Options — What Actually Exists Today (Aug 2026)
Option | What it proves | Status / availability | Path to obtain | Est. cost/effort | Recommendation
ONC Health IT Certification — §170.315(g)(31)/(g)(32)/(g)(33) Provider Prior Authorization API (CRD/DTR/PAS) | Federal, government-run certification that the platform's CRD/DTR/PAS implementation conforms to the Da Vinci IGs — the same standard CMS-0057-F cites. Results in a public listing anyone (including HCA) can verify. | REAL and current. Finalized in the HTI-4 Final Rule, effective Oct 1, 2025. Very new — few vendors have pursued it yet. | Engage an ONC-Authorized Certification Body (ONC-ACB, e.g., Drummond Group, SLI Compliance) for witnessed testing; passing results in listing on the federal Certified Health IT Product List (CHPL). | Moderate — typically weeks to a few months and a mid-five-figure testing fee, ACB-dependent | PURSUE — strongest, most credible, government-issued proof available; being early is a differentiator
Payer-side FHIR API certification (was proposed under HTI-2) | Would have been the direct federal certification for a payer/state-agency-facing PA platform's FHIR APIs. | DOES NOT EXIST. ASTP/ONC withdrew the unfinalized HTI-2 payer-API certification proposals in Dec 2025, pivoting to a deregulatory HTI-5 proposal instead. | Not currently obtainable — no application path exists. Monitor HTI-5 rulemaking in case a voluntary payer pathway re-emerges. | N/A | DO NOT CLAIM — be explicit in the RFI that no such certification currently exists; this is a fact about the regulatory landscape, not a platform gap
Inferno conformance test results (self-service) | Verifiable, third-party-tool pass/fail evidence against US Core, SMART App Launch, CARIN Blue Button, Da Vinci CRD/DTR/PAS. | REAL, free, and operational today at inferno.healthit.gov — the same tool ONC itself uses for certification testing. | Run directly — no application or fee. Publish the results export. | Low — engineering time only (see Project Plan, Phases 1–2) | PURSUE FIRST — fastest, cheapest, most direct way to close the current Testing Approach gap
CAQH CORE Certification — Prior Authorization & Referrals (278) Operating Rules | Industry-standard certification for the X12 278/275 legacy EDI channel; real trading partners (e.g., Availity) hold this seal. | REAL and current (Infrastructure Rule vPA.3.0, Data Content Rule vPA.1.0). | Certification testing through a CAQH CORE-approved testing vendor. | Moderate — several weeks and a testing-vendor fee | PURSUE — closes the X12 278/275 half of the conformance scope with a recognized industry seal
HL7 Da Vinci Connectathon participation (CRD/DTR/PAS tracks) | Real-world interoperability testing against independent implementers, not a simulated test client. | REAL — ongoing HL7 FHIR Connectathons run these tracks regularly. | Register for an upcoming connectathon; HL7 tracks and can publish participation/results. | Low — mainly staff time for a ~1-week event | RECOMMENDED complement — strong signal to standards-literate evaluators, cheap to obtain
CARIN Alliance Code of Conduct attestation | Public, voluntary attestation to consumer-data-sharing best practices for the Patient Access API. | REAL — administered by the CARIN Alliance; attestors listed at MyHealthApplication.com. | Sign the Code of Conduct and register the application. | Low | RECOMMENDED — low-cost, relevant specifically to Patient Access
SOC 2 Type II | Independent audit of security controls (not FHIR/interoperability conformance). | Already referenced in the RFI as an open item — [IBM to insert current SOC 2 report date]. | Standard annual audit cycle via IBM's existing compliance program. | N/A — existing program | ALREADY IN PLAN — close the placeholder with the current report date
HITRUST CSF certification | Higher-bar security/privacy certification, common in healthcare. | Already referenced in the RFI as available if HCA requires it. | Optional add-on assessment. | Higher — significant assessment effort | OPTIONAL — offer only if HCA specifically requires it

## Test Kit Reference
Inferno Test Kit Reference (inferno.healthit.gov)
Test Kit | IG Version(s) Supported | What It Tests | Kit Status | Link
US Core | v3.1.1, v4.0.0, v5.0.1, v6.1.0, v7.0.0, v8.0.0 | Server/client conformance for Coverage, Condition, Claim/ClaimResponse, and other US Core profiles underlying Patient/Provider Access | Stable | https://inferno.healthit.gov/test-kits/us-core/
SMART App Launch | STU1, STU2, STU2.2 | Authorization-server and client conformance for the DTR SMART app launch flow | Stable | https://inferno.healthit.gov/test-kits/smart-app-launch/
CARIN IG for Blue Button | v2.0.0 / v2.1.0 | Server/client conformance for the Patient Access consumer-directed data API | Stable | https://inferno.healthit.gov/test-kits/carin-for-blue-button/
Da Vinci CRD | STU 2.0.1, STU 2.2.1 | Coverage Requirements Discovery client/server conformance (CDS Hooks order-select/sign) | Stable, actively updated (2026 US Quality Core IG update noted) | https://inferno.healthit.gov/test-kits/davinci-crd/
Da Vinci DTR | v2.0.1 | Documentation Templates & Rules SMART app client and payer server conformance | Stable | https://inferno.healthit.gov/test-kits/davinci-dtr/
Da Vinci PAS | v2.0.1 | Prior Authorization Support client/server conformance (PASBundle submission) | Draft / preliminary — ONC invites implementer feedback | https://inferno.healthit.gov/test-kits/davinci-pas/
ONC Certification (g)(10) Standardized API | Per ONC Certification Program | Combined suite used in formal ONC certification testing | Stable | https://inferno.healthit.gov/test-kits/onc-certification-g10/
Sources: inferno.healthit.gov/test-kits/ ; healthit.gov HTI-4 Final Rule fact sheets (Oct 2025) ; Federal Register HTI-2 Withdrawal notice (Dec 29, 2025) ; caqh.org/core ; carinalliance.com/code-of-conduct. Verified via web search, Aug 2026.

## Gantt Chart
Standards-Conformance Testing — Gantt Chart (18-Week Illustrative Schedule)
Week numbers are relative to project kickoff (kickoff date TBD). Bars are colored by phase. AI Feasibility: Green = Claude can execute end-to-end · Yellow = AI-assisted, human decides/reviews · Red = inherently human (relationship, signature, witnessed session). See AI Impact Analysis tab for detail.
ID | Task | Owner | AI Feasibility | Dur (wks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Phase 0 — Governance & Scoping
0.1 | Confirm target IG versions & lock scope | Tech Lead | AI-Assisted | 1 | bar: W1
0.2 | Stand up dedicated conformance test environment | Backend/FHIR Engineer 1 | Full Automation | 2 | bar: W1 to W2
0.3 | Engage trading partner for X12 278/275 testing | Project Manager | Human-Required | 2 | bar: W1 to W2
0.4 | Assign conformance owner per suite | Project Manager | Human-Required | 1 | bar: W1
Phase 1 — Foundational IGs
1.1 | Run Inferno US Core Test Kit | Backend/FHIR Engineer 1 | Full Automation | 2 | bar: W2 to W3
1.2 | Run Inferno SMART App Launch Test Kit | Backend/FHIR Engineer 1 | Full Automation | 2 | bar: W2 to W3
1.3 | Run Inferno CARIN Blue Button Test Kit | Backend/FHIR Engineer 2 | Full Automation | 2 | bar: W3 to W4
1.4 | Remediate & re-run foundational IG failures | Backend/FHIR Engineer 2 | Full Automation | 2 | bar: W4 to W5
Phase 2 — Da Vinci Prior-Auth IGs
2.1 | Run Inferno Da Vinci CRD Test Kit | Backend/FHIR Engineer 1 | Full Automation | 3 | bar: W3 to W5
2.2 | Run Inferno Da Vinci DTR Test Kit | Backend/FHIR Engineer 2 | Full Automation | 3 | bar: W4 to W6
2.3 | Run Inferno Da Vinci PAS Test Kit | Backend/FHIR Engineer 1 | AI-Assisted | 3 | bar: W4 to W6
2.4 | Remediate & re-run CRD/DTR/PAS failures | Backend/FHIR Engineer 2 | AI-Assisted | 3 | bar: W6 to W8
2.5 | Participate in CMS HL7 FHIR Connectathon (CRD/DTR/PAS tracks) | Tech Lead | Human-Required | 2 | bar: W7 to W8
Phase 3 — X12 278/275 Conformance
3.1 | X12 278 request/response testing with trading partner | Data/Integration Engineer | AI-Assisted | 4 | bar: W3 to W6
3.2 | X12 275 attachment testing | Data/Integration Engineer | AI-Assisted | 2 | bar: W6 to W7
3.3 | Validate against CAQH CORE 278 Infrastructure & Data Content Rules | Data/Integration Engineer | Full Automation | 3 | bar: W7 to W9
3.4 | Remediate & re-test X12/CORE gaps | Data/Integration Engineer | AI-Assisted | 2 | bar: W9 to W10
Phase 4 — Formal Certification Pursuit
4.1 | Legal/product scoping — which side of each transaction to certify | Product/Clinical SME | AI-Assisted | 2 | bar: W8 to W9
4.2 | Engage ONC-Authorized Certification Body (ONC-ACB) | Project Manager | Human-Required | 4 | bar: W9 to W12
4.3 | Complete ONC-ACB witnessed testing & remediation | Backend/FHIR Engineer 1 | AI-Assisted | 6 | bar: W12 to W17
4.4 | Confirm CHPL listing | Project Manager | Human-Required | 2 | bar: W17 to W18
4.5 | Pursue CAQH CORE Certification (278 Operating Rules) | Data/Integration Engineer | AI-Assisted | 5 | bar: W10 to W14
4.6 | Sign CARIN Alliance Code of Conduct | Product/Clinical SME | Human-Required | 2 | bar: W6 to W7
Phase 5 — Publish & Report
5.1 | Compile public conformance & certification summary | Project Manager | Full Automation | 2 | bar: W17 to W18
5.2 | Update RFI/proposal Testing Approach language | Tech Lead | Full Automation | 1 | bar: W18
5.3 | Establish recurring re-test cadence | Project Manager | AI-Assisted | 1 | bar: W18
Phase Legend:
Phase 0 — Governance & Scoping
Phase 1 — Foundational IGs
Phase 2 — Da Vinci Prior-Auth IGs
Phase 3 — X12 278/275 Conformance
Phase 4 — Formal Certification Pursuit
Phase 5 — Publish & Report
AI Feasibility Legend:
Full Automation
AI-Assisted
Human-Required

## Time & Cost Summary
Standards-Conformance Testing — Time & Cost Summary
Labor priced against IBM's standard blended rate card (Source: Prior_Auth_Cost_Model V2.0.xlsx, Assumptions tab). Third-party fees are publicly sourced where available; unpublished vendor fees are labeled as request-a-quote placeholders — replace before using in a firm proposal.
Standard Rate Card ($/day, blended)
Role | Daily Rate ($)
Tech Lead | 1450
Backend/FHIR Engineer 1 | 1100
Backend/FHIR Engineer 2 | 1100
Data/Integration Engineer | 1100
Frontend Engineer | 1000
QA Engineer | 900
Security Engineer | 1250
Product/Clinical SME | 1300
Project Manager | 1050
Clinical Policy Reviewer | 950
Task-Level Cost Detail
ID | Phase | Task | Owner Role | Person-Days | Daily Rate ($) | Task Cost ($)
0.1 | Phase 0 — Governance & Scoping | Confirm target IG versions & lock scope | Tech Lead | 2 | 1450 | 2900
0.2 | Phase 0 — Governance & Scoping | Stand up dedicated conformance test environment | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
0.3 | Phase 0 — Governance & Scoping | Engage trading partner for X12 278/275 testing | Project Manager | 2 | 1050 | 2100
0.4 | Phase 0 — Governance & Scoping | Assign conformance owner per suite | Project Manager | 1 | 1050 | 1050
1.1 | Phase 1 — Foundational IGs | Run Inferno US Core Test Kit | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
1.2 | Phase 1 — Foundational IGs | Run Inferno SMART App Launch Test Kit | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
1.3 | Phase 1 — Foundational IGs | Run Inferno CARIN Blue Button Test Kit | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
1.4 | Phase 1 — Foundational IGs | Remediate & re-run foundational IG failures | Backend/FHIR Engineer 2 | 6 | 1100 | 6600
2.1 | Phase 2 — Da Vinci Prior-Auth IGs | Run Inferno Da Vinci CRD Test Kit | Backend/FHIR Engineer 1 | 6 | 1100 | 6600
2.2 | Phase 2 — Da Vinci Prior-Auth IGs | Run Inferno Da Vinci DTR Test Kit | Backend/FHIR Engineer 2 | 6 | 1100 | 6600
2.3 | Phase 2 — Da Vinci Prior-Auth IGs | Run Inferno Da Vinci PAS Test Kit | Backend/FHIR Engineer 1 | 8 | 1100 | 8800
2.4 | Phase 2 — Da Vinci Prior-Auth IGs | Remediate & re-run CRD/DTR/PAS failures | Backend/FHIR Engineer 2 | 10 | 1100 | 11000
2.5 | Phase 2 — Da Vinci Prior-Auth IGs | Participate in CMS HL7 FHIR Connectathon (CRD/DTR/PAS tracks) | Tech Lead | 5 | 1450 | 7250
3.1 | Phase 3 — X12 278/275 Conformance | X12 278 request/response testing with trading partner | Data/Integration Engineer | 8 | 1100 | 8800
3.2 | Phase 3 — X12 278/275 Conformance | X12 275 attachment testing | Data/Integration Engineer | 5 | 1100 | 5500
3.3 | Phase 3 — X12 278/275 Conformance | Validate against CAQH CORE 278 Infrastructure & Data Content Rules | Data/Integration Engineer | 6 | 1100 | 6600
3.4 | Phase 3 — X12 278/275 Conformance | Remediate & re-test X12/CORE gaps | Data/Integration Engineer | 5 | 1100 | 5500
4.1 | Phase 4 — Formal Certification Pursuit | Legal/product scoping — which side of each transaction to certify | Product/Clinical SME | 4 | 1300 | 5200
4.2 | Phase 4 — Formal Certification Pursuit | Engage ONC-Authorized Certification Body (ONC-ACB) | Project Manager | 2 | 1050 | 2100
4.3 | Phase 4 — Formal Certification Pursuit | Complete ONC-ACB witnessed testing & remediation | Backend/FHIR Engineer 1 | 10 | 1100 | 11000
4.4 | Phase 4 — Formal Certification Pursuit | Confirm CHPL listing | Project Manager | 1 | 1050 | 1050
4.5 | Phase 4 — Formal Certification Pursuit | Pursue CAQH CORE Certification (278 Operating Rules) | Data/Integration Engineer | 8 | 1100 | 8800
4.6 | Phase 4 — Formal Certification Pursuit | Sign CARIN Alliance Code of Conduct | Product/Clinical SME | 1 | 1300 | 1300
5.1 | Phase 5 — Publish & Report | Compile public conformance & certification summary | Project Manager | 2 | 1050 | 2100
5.2 | Phase 5 — Publish & Report | Update RFI/proposal Testing Approach language | Tech Lead | 2 | 1450 | 2900
5.3 | Phase 5 — Publish & Report | Establish recurring re-test cadence | Project Manager | 1 | 1050 | 1050
[5 empty] | Labor Subtotal: | 130200
|  |  | Total Person-Days: | 115
External / Third-Party Certification Fees
Item | Est. Fee ($) | Basis / Source
ONC-ACB certification testing — §170.315(g)(31)/(g)(32)/(g)(33) | 35000 | Quote-based; not publicly published. Illustrative placeholder based on reported minimum engagements (~$5,000+) and hourly rates (~$200–300/hr) scaled for a 3-criteria FHIR API scope. Request formal quote from an ONC-ACB (e.g., Drummond Group, SLI Compliance).
CAQH CORE Certification Seal — Prior Authorization & Referrals (278) | 6000 | Published CAQH fee schedule: $4,000 (entities <$75M net annual revenue) or $6,000 (>=$75M); no charge for federal/state government entities. IBM assumed at the $6,000 tier.
CAQH CORE-authorized testing vendor fee | 10000 | Set independently by the CORE-authorized testing vendor, not published by CAQH CORE. Illustrative placeholder — request vendor quote.
HL7 CMS FHIR Connectathon (CRD/DTR/PAS tracks) | 0 | The CMS HL7 FHIR Connectathon is a free, virtual event (confirmed 2026 dates: July 14–16, 2026). No registration fee; only staff time, already captured in labor above.
CARIN Alliance Code of Conduct attestation | 0 | Voluntary, no-fee attestation administered by the CARIN Alliance.
Incremental test-environment infrastructure | 0 | Assumes use of the existing reference/staging environment already budgeted in the platform cost model (Prior_Auth_Cost_Model V2.0.xlsx); no incremental hosting cost assumed.
External Fees Subtotal: | 51000
GRAND TOTAL — Standards-Conformance Testing & Certification Program |  |  | 181200
Elapsed schedule: ~18 weeks (~4.1 months) — see Gantt Chart tab. Labor and elapsed time are not the same: several tasks (ONC-ACB witnessed testing, CAQH CORE certification) are vendor-paced and run largely in parallel with other work, so elapsed weeks exceed total person-days converted to weeks.
All labor figures are illustrative planning-level estimates using IBM's standard blended rate card, consistent with the existing Prior_Auth_Cost_Model. Replace person-day estimates with actuals once a delivery team and detailed work breakdown are confirmed. Third-party fees marked as placeholders must be replaced with real vendor quotes before use in a priced proposal.

## AI Impact Analysis
AI Impact Analysis — Cost & Effort With vs. Without Claude
Each task rated on how much of the work an AI agent (Claude) can execute directly, vs. requires a human owner. Rates pulled from the Time & Cost Summary tab. Third-party/vendor fees are unaffected by AI use and are not shown here.
AI Feasibility Categories
Full Automation | Claude can execute the task end-to-end (run tests, write/fix code, generate reports) with only light human review.
AI-Assisted | Claude materially speeds up the work, but a human must still decide, judge, or coordinate part of it.
Human-Required | Inherently human: signatures, contracts, vendor relationships, live witnessed sessions. Claude can draft supporting material only.
Task-Level Comparison
ID | Task | Owner Role | AI Feasibility | Days (No AI) | Days (With AI) | Cost (No AI, $) | Cost (With AI, $) | Savings ($)
0.1 | Confirm target IG versions & lock scope | Tech Lead | AI-Assisted | 2 | 0.5 | 2900 | 725 | 2175
0.2 | Stand up dedicated conformance test environment | Backend/FHIR Engineer 1 | Full Automation | 4 | 1 | 4400 | 1100 | 3300
0.3 | Engage trading partner for X12 278/275 testing | Project Manager | Human-Required | 2 | 1.5 | 2100 | 1575 | 525
0.4 | Assign conformance owner per suite | Project Manager | Human-Required | 1 | 0.75 | 1050 | 787.5 | 262.5
1.1 | Run Inferno US Core Test Kit | Backend/FHIR Engineer 1 | Full Automation | 4 | 1 | 4400 | 1100 | 3300
1.2 | Run Inferno SMART App Launch Test Kit | Backend/FHIR Engineer 1 | Full Automation | 2 | 0.5 | 2200 | 550 | 1650
1.3 | Run Inferno CARIN Blue Button Test Kit | Backend/FHIR Engineer 2 | Full Automation | 4 | 1 | 4400 | 1100 | 3300
1.4 | Remediate & re-run foundational IG failures | Backend/FHIR Engineer 2 | Full Automation | 6 | 2 | 6600 | 2200 | 4400
2.1 | Run Inferno Da Vinci CRD Test Kit | Backend/FHIR Engineer 1 | Full Automation | 6 | 1.5 | 6600 | 1650 | 4950
2.2 | Run Inferno Da Vinci DTR Test Kit | Backend/FHIR Engineer 2 | Full Automation | 6 | 1.5 | 6600 | 1650 | 4950
2.3 | Run Inferno Da Vinci PAS Test Kit | Backend/FHIR Engineer 1 | AI-Assisted | 8 | 3 | 8800 | 3300 | 5500
2.4 | Remediate & re-run CRD/DTR/PAS failures | Backend/FHIR Engineer 2 | AI-Assisted | 10 | 4 | 11000 | 4400 | 6600
2.5 | Participate in CMS HL7 FHIR Connectathon (CRD/DTR/PAS tracks) | Tech Lead | Human-Required | 5 | 4 | 7250 | 5800 | 1450
3.1 | X12 278 request/response testing with trading partner | Data/Integration Engineer | AI-Assisted | 8 | 4 | 8800 | 4400 | 4400
3.2 | X12 275 attachment testing | Data/Integration Engineer | AI-Assisted | 5 | 2.5 | 5500 | 2750 | 2750
3.3 | Validate against CAQH CORE 278 Infrastructure & Data Content Rules | Data/Integration Engineer | Full Automation | 6 | 2 | 6600 | 2200 | 4400
3.4 | Remediate & re-test X12/CORE gaps | Data/Integration Engineer | AI-Assisted | 5 | 2.5 | 5500 | 2750 | 2750
4.1 | Legal/product scoping — which side of each transaction to certify | Product/Clinical SME | AI-Assisted | 4 | 2 | 5200 | 2600 | 2600
4.2 | Engage ONC-Authorized Certification Body (ONC-ACB) | Project Manager | Human-Required | 2 | 1.5 | 2100 | 1575 | 525
4.3 | Complete ONC-ACB witnessed testing & remediation | Backend/FHIR Engineer 1 | AI-Assisted | 10 | 6 | 11000 | 6600 | 4400
4.4 | Confirm CHPL listing | Project Manager | Human-Required | 1 | 0.75 | 1050 | 787.5 | 262.5
4.5 | Pursue CAQH CORE Certification (278 Operating Rules) | Data/Integration Engineer | AI-Assisted | 8 | 4 | 8800 | 4400 | 4400
4.6 | Sign CARIN Alliance Code of Conduct | Product/Clinical SME | Human-Required | 1 | 0.75 | 1300 | 975 | 325
5.1 | Compile public conformance & certification summary | Project Manager | Full Automation | 2 | 0.5 | 2100 | 525 | 1575
5.2 | Update RFI/proposal Testing Approach language | Tech Lead | Full Automation | 2 | 0.5 | 2900 | 725 | 2175
5.3 | Establish recurring re-test cadence | Project Manager | AI-Assisted | 1 | 0.5 | 1050 | 525 | 525
Rationale by Task
ID | Rationale
0.1 | Claude can research current IG versions and draft the scope memo; a human still locks scope.
0.2 | Environment/config work an agent can execute directly (env vars, cutover config, verification checks); engineer reviews before touching a live-adjacent backbone.
0.3 | Business relationship/outreach; Claude can draft the engagement email and test agreement.
0.4 | Internal people/organizational decision.
1.1 | Claude can run the test kit, parse results, and produce the pass/fail report end-to-end.
1.2 | Same as above — mechanical test execution and reporting.
1.3 | Same as above.
1.4 | Claude can diagnose failures, write and test fixes, and re-run the suite; engineer reviews non-trivial fixes.
2.1 | Mechanical test execution and reporting.
2.2 | Mechanical test execution and reporting.
2.3 | PAS kit is still in draft/preliminary status on ONC's side — expect kit quirks that need engineer judgment alongside AI execution.
2.4 | Most fixes are AI-draftable; triage/prioritization of complex prior-auth logic failures needs engineer judgment.
2.5 | Live, real-time interoperability testing with independent implementers; Claude can prep test scripts and scenarios beforehand.
3.1 | Claude can generate/validate transactions and automate comparisons; live coordination with the trading partner needs a human.
3.2 | Same pattern as 3.1.
3.3 | Rule-by-rule conformance checking against a published checklist — well suited to direct AI execution; human confirms sign-off.
3.4 | Fix drafting is automatable; final validation needs engineer judgment.
4.1 | Claude can draft the options analysis; the certification-scope decision itself needs human legal/product judgment.
4.2 | Vendor engagement and contracting; Claude can draft outreach and RFP materials.
4.3 | Remediation work is AI-assisted, but the ACB's witnessed session itself requires a human present and is vendor-scheduled — the real bottleneck isn't raw labor.
4.4 | Official administrative confirmation step.
4.5 | Documentation/prep heavily automatable; the certification testing session itself is vendor-coordinated.
4.6 | Requires an authorized human signatory; Claude can draft the submission.
5.1 | Drafting/compiling a summary report from already-gathered evidence — direct AI output.
5.2 | Direct document-editing task — the same class of work already demonstrated on the V4 RFI redline.
5.3 | Claude can draft the schedule/automation; a human approves the cadence policy.
Cost Comparison Summary
| Without AI | With AI | Savings | Savings %
Internal Labor | 130200 | 56750 | 73450 | 56.41%
External / Third-Party Fees (unaffected by AI) | 51000 | 51000 | 0 | —
GRAND TOTAL | 181200 | 107750 | 73450 | 40.54%
Task Count by AI Feasibility (of 26 tasks)
Full Automation | 10
AI-Assisted | 10
Human-Required | 6
Schedule note: internal-labor compression does not shrink elapsed calendar time proportionally. Phases 0–3 are engineering-labor-bound and could plausibly compress; Phase 4 (ONC-ACB witnessed testing, CAQH CORE certification) is vendor-paced and stays the critical path regardless of AI use — expect the 18-week elapsed schedule to compress modestly (illustratively, to roughly 14–15 weeks), not in proportion to the labor-cost savings.
All person-day and rationale judgments are illustrative planning estimates, not a delivery commitment. External/third-party fees (ONC-ACB, CAQH CORE) do not change with AI use since they are paid to independent bodies performing witnessed/independent testing.